## Sheet1
Project ID | Cycle | Stage | Name | Commercial Name | Developer | State | County | Status | Project Type | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Fuel | Submitted Date | Requested In-Service Date | Revised In-Service Date | Actual In-Service Date | Commercial Operation Milestone | Backfeed Date | Test Energy Date | Last Updated | Withdrawn Date | Withdrawn Remarks | Phase 1 SIS Report | Phase 1 SIS Report Status | Phase 2 SIS Report | Phase 2 SIS Report Status | Phase 3 SIS Report | Phase 3 SIS Report Status | GIA/WMPA Report | GIA/WMPA Report Status | CSA/USCA Report | CSA/USCA Report Status | Transmission Type | Rights (MW) | Long-Term Firm Service Start Date | Long-Term Firm Service End Date
AH1-563 | TC2 | PHASE 1 | Aurora E.C. 138kV | Aurora Battery Storage II | Aurora | IL |  | Active | Generation Interconnection | ComEd | 1206 | 150 | 150 |  | Capacity | Storage | 9/11/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-344 | TC2 | PHASE 1 | Dequine 345 bkV |  | Rainbow Trout Solar LLC | IN |  | Active | Generation Interconnection | AEP | 100 | 100 | 78 |  | Capacity | Storage | 3/26/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-570 | TC2 | PHASE 1 | Millersburg 69 kV |  | South Fork Solar, LLC | KY |  | Active | Generation Interconnection | EKPC | 25 | 25 | 15.6 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-571 | TC2 | PHASE 1 | Millersburg 69 kV |  | South Fork Solar, LLC | KY |  | Active | Generation Interconnection | EKPC | 45 | 20 | 12.5 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-617 | TC2 | PHASE 1 | Harbert Metering 138 kV |  | STMO bn, LLC | KY |  | Active | Generation Interconnection | AEP | 200 | 200 | 120 |  | Capacity | Solar | 9/10/2021 | 9/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-644 | TC2 | PHASE 1 | Spicewood Metering 138 kV |  | Kentucky Power Company | KY |  | Active | Generation Interconnection | AEP | 100 | 100 | 65 |  | Capacity | Solar | 9/15/2021 | 1/1/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-427 | TC2 | PHASE 1 | Tommy Gooch - Garrard County 69 kV |  | ACE | KY |  | Active | Generation Interconnection | EKPC | 100 | 100 | 60 |  | Capacity | Solar | 9/10/2021 | 9/1/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-136 | TC2 | PHASE 1 | Falcon - Middle Creek 46 kV |  | Big Sandy Renewables LLC | KY |  | Active | Generation Interconnection | AEP | 20 | 20 | 12 |  | Capacity | Solar | 8/25/2021 | 12/31/2024 | [5 empty] | 5/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-163 | TC2 | APPLICATION REVIEW | Millersburg 69 kV |  | Derby Solar Farm, LLC | KY |  | Withdrawn | Generation Interconnection | EKPC | 100 | 100 | 60 |  | Capacity | Solar | 9/1/2021 | 7/31/2025 | [5 empty] | 1/28/2025 | 1/28/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-721 | TC2 | PHASE 1 | Laurel-Cooper 161 kV |  | East Kentucky Power Cooperative, Inc. | KY |  | Active | Generation Interconnection | EKPC | 786 | 786 | 758.9507 |  | Capacity | Natural Gas |  | 12/31/2030 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-749 | TC2 | RRI APPLICATION REVIEW |  |  | East Kentucky Power Cooperative, Inc. | KY |  | Withdrawn | Generation Interconnection | EKPC | 216 | 216 | 216 |  | Capacity | Natural Gas |  | 12/12/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-189 | TC2 | PHASE 1 | Hopkins 138 kV |  | Hobet Solar I, LLC | WV |  | Active | Generation Interconnection | AEP | 140 | 140 | 84 |  | Capacity | Solar | 8/31/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-466 | TC2 | PHASE 1 | Culloden - Wyoming 765 kV |  | Hobet Solar I, LLC | WV |  | Active | Generation Interconnection | AEP | 330 | 330 | 198 |  | Capacity | Solar | 3/30/2021 | 6/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-509 | TC2 | APPLICATION REVIEW | Robinson 69 kV |  | IRGAH Renewables Development LLC | WV |  | Withdrawn | Generation Interconnection | AEP | 55 | 55 | 36.3 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/1/2024 | [5 empty] | 3/4/2025 | 3/4/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-568 | TC2 | PHASE 1 | Stink Run – Sundial 138 kV |  | Sundial Energy, LLC | WV |  | Active | Generation Interconnection | AEP | 80 | 80 | 48 |  | Capacity | Solar | 3/31/2021 | 2/25/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-447 | TC2 | PHASE 1 | Cedar Creek 138 kV VII |  | Freepoint Solar LLC | DE | New Castle | Active | Generation Interconnection | DPL | 134.3 | 20 | 12 |  | Capacity | Solar | 3/30/2021 | 2/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-761 | TC2 | RRI APPLICATION REVIEW |  |  | Freepoint Solar LLC | DE | New Castle | Withdrawn | Generation Interconnection | DPL | 134.3 | 0 | 71 |  | Capacity | Storage |  | 4/30/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-760 | TC2 | RRI APPLICATION REVIEW |  |  | Freepoint Solar LLC | DE | Kent | Withdrawn | Generation Interconnection | DPL | 50 | 0 | 31 |  | Capacity | Storage |  | 10/31/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-027 | TC2 | PHASE 1 | Cartanza 230 kV |  | Calpine | DE | Kent | Active | Generation Interconnection | DPL | 25 | 25 | 15 |  | Capacity | Solar | 5/20/2021 | 6/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-497 | TC1 | PHASE 2 | Cartanza 230 kV |  | Morgan Branch Solar I, LLC | DE | Kent | Withdrawn | Generation Interconnection | DPL | 120 | 120 | 84 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/30/2023 | [5 empty] | 1/24/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-497/AG1-497_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-497/AG1-497_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-061 | TC1 | PHASE 1 | Laurel-Sharptown 69 kV |  | Deere Acres Solar LLC | DE | Sussex | Withdrawn | Generation Interconnection | DPL | 109.3 | 109.3 | 65.58 |  | Capacity | Solar | 7/29/2020 | 12/31/2021 | [5 empty] | 6/27/2024 | 6/25/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-061/AG1-061_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-193 | TC1 | PHASE 1 | Indian River 230 kV I |  | GSOE I, LLC | DE | Sussex | Withdrawn | Generation Interconnection | DPL | 440 | 440 | 119 |  | Capacity | Offshore Wind | 3/23/2020 | 10/31/2026 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-193/AF2-193_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-194 | TC1 | PHASE 1 | Indian River 230 kV II |  | GSOE I, LLC | DE | Sussex | Withdrawn | Generation Interconnection | DPL | 880 | 440 | 119 |  | Capacity | Offshore Wind | 3/23/2020 | 10/31/2026 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-194/AF2-194_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-347 | TC2 | PHASE 1 | Indian River 230 kV II |  | US Wind Inc. | DE | Sussex | Active | Generation Interconnection | DPL | 448.8 | 448.8 | 121.2 |  | Capacity | Offshore Wind | 3/26/2021 | 8/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-348 | TC2 | APPLICATION REVIEW | Indian River 230 kV II |  | US Wind Inc. | DE | Sussex | Withdrawn | Generation Interconnection | DPL | 897.6 | 897.6 | 242.3 |  | Capacity | Offshore Wind | 3/26/2021 | 8/31/2025 | [5 empty] | 4/1/2025 | 2/25/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-672 | TC2 | PHASE 1 | Farmview 138 kV |  | Freeman Solar LLC | DE | Sussex | Active | Generation Interconnection | DPL | 75 | 75 | 48.9 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 5/5/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-634 | TC2 | PHASE 1 | Indian River 230kV I |  | US Wind Inc. | DE | Sussex | Active | Generation Interconnection | DPL | 323.1 | 68 | 17.7 |  | Capacity | Offshore Wind | 9/13/2021 | 12/31/2024 | [5 empty] | 5/20/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-584 | TC2 | PHASE 1 | Nelson-Indian River 138kV |  | RWE LLC | DE | Sussex | Active | Generation Interconnection | DPL | 50 | 50 | 30 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-585 | TC2 | PHASE 1 | Nelson-Indian River 138kV |  | RWE LLC | DE | Sussex | Active | Generation Interconnection | DPL | 100 | 50 | 30 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-586 | TC2 | PHASE 1 | Nelson-Indian River 138kV |  | RWE LLC | DE | Sussex | Active | Generation Interconnection | DPL | 145 | 45 | 45 |  | Capacity | Storage | 9/10/2021 | 12/16/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-393 | TC1 | PHASE 2 | Nelson-Dixon 138 kV |  | Bison Meadows Wind Project, LLC | IL | Adams | Withdrawn | Generation Interconnection | ComEd | 259 | 60 | 55 |  | Capacity | Storage | 3/31/2020 | 9/1/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-393/AF2-393_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-393/AF2-393_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-394 | TC1 | PHASE 2 | Nelson-Dixon 138 kV |  | Bison Meadows Wind Project, LLC | IL | Adams | Withdrawn | Generation Interconnection | ComEd | 299 | 40 | 40 |  | Capacity | Storage | 3/31/2020 | 9/1/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-394/AF2-394_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-394/AF2-394_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AH1-047 | TC2 | PHASE 1 | Marengo - Belvidere 138 kV |  | BLUE STONE RENEWABLE XIV LLC | IL | Boone | Active | Generation Interconnection | ComEd | 58.6 | 58.6 | 37 |  | Capacity | Solar | 7/6/2021 | 9/13/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-069 | TC1 | PHASE 3 | Crescent Ridge 138 kV | Lone Tree Wind Farm | Lone Tree Wind, LLC | IL | Bureau | Active | Generation Interconnection | ComEd | 87.8 | 8.4 | 1.98 |  | Capacity | Wind | 1/31/2020 | 10/4/2021 | [5 empty] | 5/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-069/AF2-069_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-069/AF2-069_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-070 | TC1 | PHASE 2 | Crescent Ridge 138 kV |  | Crescent Ridge LLC | IL | Bureau | Withdrawn | Generation Interconnection | ComEd | 72.6 | 18.15 | 3.1 |  | Capacity | Wind | 1/31/2020 | 10/4/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-070/AF2-070_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-070/AF2-070_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-121 | TC1 | PHASE 1 | Kewanee-Streator 138 kV |  | Leeward Renewable Energy Development, LLC | IL | Bureau | Withdrawn | Generation Interconnection | ComEd | 294.7 | 294.7 | 51.9 |  | Capacity | Wind | 8/31/2020 | 12/31/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-121/AG1-121_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-435 | TC1 | PHASE 1 | Kewanee-Hennepin 138 kV |  | RWE LLC | IL | Bureau | Withdrawn | Generation Interconnection | ComEd | 150 | 150 | 35.2 |  | Capacity | Wind | 9/30/2020 | 12/31/2023 | [5 empty] | 2/21/2025 | 2/21/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-435/AG1-435_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-435/AG1-435_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-460 | TC1 | PHASE 3 | Kincaid-Pana 345 kV |  | Black Diamond Solar Power, LLC | IL | Christian | Active | Generation Interconnection | ComEd | 329 | 30 | 12 |  | Capacity | Storage | 9/30/2020 | 6/1/2022 | [5 empty] | 3/14/2025 |  | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-460/AG1-460_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-460/AG1-460_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-261 | TC1 | PHASE 3 | Kincaid-Pana 345 kV |  | Black Diamond Solar Power, LLC | IL | Christian | Active | Generation Interconnection | ComEd | 299 | 299 | 179.4 |  | Capacity | Solar | 3/28/2019 | 6/1/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-261/AE2-261_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-261/AE2-261_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-252 | TC1 | PHASE 1 | Kincaid-Pana |  | Rolling Farms Wind Project, LLC | IL | Christian | Withdrawn | Generation Interconnection | ComEd | 262.4 | 62.4 | 62.4 |  | Capacity | Storage | 9/30/2019 | 9/1/2022 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-252/AF1-252_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-253 | TC1 | PHASE 1 | Kincaid-Pana |  | Rolling Farms Wind Project, LLC | IL | Christian | Withdrawn | Generation Interconnection | ComEd | 305.6 | 43.2 | 43.2 |  | Capacity | Storage | 9/30/2019 | 9/1/2022 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-253/AF1-253_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-441 | TC1 | PHASE 3 | Burnham 138kV |  | Lincoln Reserve Energy, LLC | IL | Cook | Active | Generation Interconnection | ComEd | 200 | 200 | 80 |  | Capacity | Storage | 3/31/2020 | 5/31/2024 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-441/AF2-441_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-441/AF2-441_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-298 | TC1 | PHASE 2 | Calumet-Burnham 345 kV |  | Big Shoulders Storage LLC | IL | Cook | Withdrawn | Generation Interconnection | ComEd | 500 | 500 | 500 |  | Capacity | Storage | 9/29/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-298/AG1-298_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-298/AG1-298_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AH1-673 | TC2 | PHASE 1 | State Line - River Energy Center 138 kV |  | Big Shoulders Storage LLC | IL | Cook | Active | Generation Interconnection | ComEd | 85 | 85 | 85 |  | Capacity | Storage | 9/30/2020 | 6/1/2023 | [5 empty] | 5/5/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-575 | TC2 | PHASE 1 | Crego Rd. 138 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Active | Generation Interconnection | ComEd | 290 | 100 | 80 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-127 | TC1 | PHASE 3 | Crego Rd 138 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Active | Generation Interconnection | ComEd | 190 | 95.1 | 57.1 |  | Capacity | Solar | 8/31/2020 | 12/29/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-127/AG1-127_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-127/AG1-127_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-118 | TC1 | PHASE 3 | Sugar Grove-Waterman 138kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Active | Generation Interconnection | ComEd | 300 | 300 | 180 |  | Capacity | Solar | 8/31/2020 | 12/29/2023 | [5 empty] | 1/31/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-118/AG1-118_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-118/AG1-118_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-119 | TC1 | PHASE 1 | Wayne-Byron 345 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Withdrawn | Generation Interconnection | ComEd | 300 | 300 | 180 |  | Capacity | Solar | 8/31/2020 | 12/29/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-119/AG1-119_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-120 | TC1 | PHASE 2 | Glidden-Cherry Valley 138 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Withdrawn | Generation Interconnection | ComEd | 118.6 | 118.6 | 71.16 |  | Capacity | Solar | 8/31/2020 | 12/29/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-120/AG1-120_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-120/AG1-120_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-423 | TC1 | PHASE 1 | Byron-Wayne 345 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Withdrawn | Generation Interconnection | ComEd | 200 | 200 | 120 |  | Capacity | Solar | 9/30/2020 | 12/29/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-423/AG1-423_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-107 | TC1 | PHASE 1 | Haumesser Road 138 kV |  | DK Solar LLC | IL | DeKalb | Withdrawn | Generation Interconnection | ComEd | 90 | 90 | 54 |  | Capacity | Solar | 2/28/2019 | 12/31/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-107/AE2-107_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-285 | TC2 | PHASE 1 | Sandwich 138 kV |  | Somonauk Solar LLC | IL | DeKalb | Active | Generation Interconnection | ComEd | 86 | 86 | 11.18 |  | Capacity | Solar | 9/9/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-541 | TC2 | PHASE 1 | Chestnut 345 kV |  | Golden Harvest Energy, LLC | IL | DeWitt | Active | Generation Interconnection | ComEd | 92.4 | 92.4 | 27.72 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-524 | TC2 | PHASE 1 | LaSalle Station - Mazon 138 kV |  | Hog Run Solar, LLC | IL | Grundy | Active | Generation Interconnection | ComEd | 110 | 110 | 110 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-585 | TC2 | PHASE 1 | Kensignton 138kV |  | Grand Marsh Solar 2, LLC | IL | Kankakee | Active | Generation Interconnection | ComEd | 125 | 125 | 75 |  | Capacity | Solar | 3/31/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-095 | TC1 | PHASE 3 | Davis Creek 138 kV |  | AEUG | IL | Kankakee | Active | Generation Interconnection | ComEd | 144 | 144 | 86.4 |  | Capacity | Solar | 2/13/2020 | 5/31/2021 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-095/AF2-095_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-095/AF2-095_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-350 | TC1 | PHASE 3 | Kensington 138 kV |  | Deriva Energy Solar, LLC | IL | Kankakee | Active | Generation Interconnection | ComEd | 100 | 100 | 60 |  | Capacity | Solar | 3/31/2020 | 12/1/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-350/AF2-350_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-350/AF2-350_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-351 | TC1 | PHASE 1 | Kensington 138 kV |  | Deriva Energy Solar, LLC | IL | Kankakee | Withdrawn | Generation Interconnection | ComEd | 120 | 20 | 8 |  | Capacity | Storage | 3/31/2020 | 12/1/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-351/AF2-351_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-329 | TC1 | PHASE 2 | Sandwich-Plano 138 kV |  | Plano Skies Energy Center, LLC | IL | Kendall | Withdrawn | Generation Interconnection | ComEd | 292.2 | 42.2 | 42.2 |  | Capacity | Storage | 3/30/2020 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-329/AF2-329_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-329/AF2-329_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-034 | TC1 | PHASE 2 | Kendall 345kV |  | Kendall Solar BESS LLC | IL | Kendall | Withdrawn | Generation Interconnection | ComEd | 1238.8 | 20 | 10.8 |  | Capacity | Solar,Storage,Hybrid | 10/28/2019 | 6/1/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-034/AF2-034_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-034/AF2-034_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-341 | TC1 | PHASE 3 | Sandwich-Plano 138 kV |  | Plano Skies Energy Center, LLC | IL | Kendall | Active | Generation Interconnection | ComEd | 150 | 150 | 100.6 |  | Capacity | Solar | 3/31/2019 | 12/1/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-341/AE2-341_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-341/AE2-341_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-030 | TC1 | PHASE 3 | Sandwich-Plano 138 kV |  | Plano Skies Energy Center, LLC | IL | Kendall | Active | Generation Interconnection | ComEd | 250 | 100 | 66.9 |  | Capacity | Solar | 5/17/2019 | 12/1/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-030/AF1-030_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-030/AF1-030_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-200 | TC1 | PHASE 2 | Plano 345 kV |  | SOO Green HVDC Link ProjectCo, LLC | IL | Kendall | Withdrawn | Merchant Transmission | ComEd | 2100 | 2100 | 2035 |  | Capacity | Not Specified | 9/25/2019 | 1/31/2025 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-200/AF1-200_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-200/AF1-200_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started | DC | 2035 F/NFTIR/2100 NF/TWR
AG2-453 | TC2 | PHASE 1 | Lasalle - Plano 345 kV |  | FOX VALLEY ENERGY FACILITY, LLC | IL | Kendall | Active | Generation Interconnection | ComEd | 280 | 280 | 196 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-045 | TC2 | APPLICATION REVIEW | Zion Energy Center 345 kV |  | Zion Energy LLC | IL | Lake | Withdrawn | Generation Interconnection | ComEd | 658 | 23 | 13.8 |  | Capacity | Solar | 7/1/2021 | 6/1/2023 | [5 empty] | 2/28/2025 | 2/27/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-714 | TC2 | PHASE 1 | Lasalle 345 kV |  | Constellation Energy Generation, LLC | IL | Lasalle | Active | Generation Interconnection | ComEd | 1360 | 169 | 174.1 |  | Capacity | Nuclear |  | 3/24/2029 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-061 | TC2 | PHASE 1 | Powerton-Nevada 345 kV |  | Aurora | IL | Lasalle | Active | Generation Interconnection | ComEd | 200 | 50 | 20 |  | Capacity | Storage | 12/11/2020 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-128 | TC1 | DP1 | Crescent Ridge-Corbin 138 kV |  | UKA Green Power LLC | IL | Lasalle | Withdrawn | Generation Interconnection | ComEd | 79.5 | 79.5 | 13.992 |  | Capacity | Wind | 2/28/2020 | 8/26/2024 | [5 empty] | 7/15/2024 | 6/25/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-128/AF2-128_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-142 | TC1 | PHASE 3 | Nevada 345 kV |  | Aurora | IL | Lasalle | Active | Generation Interconnection | ComEd | 150 | 150 | 90 |  | Capacity | Solar | 3/12/2020 | 12/31/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-142/AF2-142_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-142/AF2-142_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-143 | TC1 | PHASE 3 | Powerton-Nevada 345 kV |  | Aurora | IL | Lasalle | Active | Generation Interconnection | ComEd | 150 | 150 | 90 |  | Capacity | Solar | 3/12/2020 | 12/31/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-143/AF2-143_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-143/AF2-143_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-319 | TC1 | PHASE 3 | Katydid Road 345 kV |  | Blackstone | IL | Lasalle | Active | Generation Interconnection | ComEd | 50 | 50 | 20 |  | Capacity | Storage | 3/30/2020 | 10/31/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-319/AF2-319_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-319/AF2-319_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-226 | TC1 | PHASE 3 | Katydid Road 345 kV |  | Blackstone | IL | Lasalle | Active | Generation Interconnection | ComEd | 50 | 50 | 20 |  | Capacity | Storage | 3/26/2020 | 10/31/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-226/AF2-226_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-226/AF2-226_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-182 | TC1 | PHASE 3 | Nelson-Lee County 345 kV II |  | Deriva Energy Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 500 | 300 | 0 |  | Energy | Solar | 3/21/2020 | 12/1/2022 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-182/AF2-182_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-182/AF2-182_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-183 | TC1 | PHASE 1 | Nelson-Lee County 345 kV |  | Deriva Energy Solar, LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 600 | 80 | 32 |  | Capacity | Storage | 3/20/2020 | 12/1/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-183/AF2-183_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-392 | TC1 | PHASE 3 | Nelson-Dixon 138 kV |  | Bison Meadows Wind Project, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 199 | 199 | 35.2 |  | Capacity | Wind | 3/31/2020 | 9/1/2024 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-392/AF2-392_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-392/AF2-392_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-199 | TC1 | PHASE 3 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 400 | 100 | 60 |  | Capacity | Solar | 3/24/2020 | 11/1/2023 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-199/AF2-199_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-199/AF2-199_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-200 | TC1 | PHASE 3 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 600 | 200 | 120 |  | Capacity | Solar | 3/24/2020 | 11/1/2023 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-200/AF2-200_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-200/AF2-200_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-041 | TC1 | PHASE 3 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 300 | 300 | 180 |  | Capacity | Solar | 12/9/2019 | 11/1/2023 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-041/AF2-041_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-041/AF2-041_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-280 | TC1 | PHASE 3 | Nelson-Lee County |  | Deriva Energy Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 200 | 200 | 0 |  | Energy | Solar | 9/10/2019 | 12/1/2022 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-280/AF1-280_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-280/AF1-280_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-281 | TC1 | PHASE 1 | Nelson-Lee County |  | Deriva Energy Solar, LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 220 | 20 | 3 |  | Capacity | Storage | 9/10/2019 | 12/1/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-281/AF1-281_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-434 | TC1 | DP2 | Electric Junction-Nelson 345 kV |  | RWE LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 175 | 175 | 35.2 |  | Capacity | Wind | 9/30/2020 | 12/31/2023 | [5 empty] | 2/3/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-434/AG1-434_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-434/AG1-434_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-371 | TC1 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 600 | 0 | 30 |  | Capacity | Storage | 9/30/2020 | 11/1/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-371/AG1-371_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-373 | TC1 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 600 | 0 | 10 |  | Capacity | Storage | 9/30/2020 | 11/1/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-373/AG1-373_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-718 | TC2 | PHASE 1 | Nelson 345 kV |  | Invenergy | IL | Lee | Active | Generation Interconnection | ComEd | 391 | 11 | 38 |  | Capacity | Natural Gas |  | 5/29/2028 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-700 | TC2 | RRI APPLICATION REVIEW |  |  | Invenergy | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 664 | 55 | 37 |  | Capacity | Natural Gas |  | 5/29/2028 | [5 empty] | 5/5/2025 | 4/14/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-660 | TC2 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 600 | 0 | 20 |  | Capacity | Storage | 3/31/2021 | 11/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-044 | TC2 | PHASE 1 | Nelson - Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 800 | 200 | 120 |  | Capacity | Solar | 6/30/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-150 | TC2 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 1000 | 200 | 120 |  | Capacity | Solar | 8/28/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-151 | TC2 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 1200 | 200 | 120 |  | Capacity | Solar | 8/27/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-338 | TC2 | PHASE 1 | New Sub S2354 138kV |  | Prairie Brome Solar LLC | IL | Lee | Active | Generation Interconnection | ComEd | 180 | 180 | 23.4 |  | Capacity | Solar | 9/10/2021 | 11/21/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-543 | TC2 | PHASE 1 | Mulberry – Tazewell 345 kV |  | Golden Harvest Energy, LLC | IL | Livingston | Active | Generation Interconnection | ComEd | 157.4 | 157.4 | 31.48 |  | Capacity | Solar,Storage,Hybrid | 9/11/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-755 | TC2 | RRI APPLICATION REVIEW |  |  | Livingston County Solar, LLC | IL | Livingston | Withdrawn | Generation Interconnection | ComEd | 330 | 330 | 330 |  | Capacity | Solar,Storage,Hybrid |  | 12/1/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG1-321 | TC1 | PHASE 1 | Dresden-Pontiac Midpoint 345 kV |  | CPV LLC | IL | Livingston | Withdrawn | Generation Interconnection | ComEd | 200 | 200 | 126.4 |  | Capacity | Solar | 9/30/2020 | 10/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-321/AG1-321_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE1-172 | TC1 | PHASE 3 | Loretto-Wilton Center | Livingston Wind | EDF Renewables Development, Inc. | IL | Livingston | Active | Generation Interconnection | ComEd | 255 | 255 | 44.88 |  | Capacity | Wind | 9/25/2018 | 10/1/2021 | [5 empty] | 4/29/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE1-172/AE1-172_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-172/AE1-172_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-114 | TC2 | PHASE 1 | Dresden-Pontiac Midpoint 345 kV |  | CPV LLC | IL | Livingston | Active | Generation Interconnection | ComEd | 100 | 100 | 60 |  | Capacity | Solar | 1/29/2021 | 3/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-467 | TC2 | PHASE 1 | Beason 345 kV |  | Invenergy | IL | Logan | Active | Generation Interconnection | ComEd | 115 | 69 | 115 |  | Capacity | Solar | 3/31/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-236 | TC1 | PHASE 3 | Lanesville-Brokaw 345 kV |  | Invenergy | IL | Logan | Active | Generation Interconnection | ComEd | 380 | 180 | 23.4 |  | Capacity | Wind | 9/25/2020 | 12/31/2024 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-236/AG1-236_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-236/AG1-236_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-296 | TC2 | PHASE 1 | Beason 345 kV |  | Invenergy | IL | Logan | Active | Generation Interconnection | ComEd | 175 | 60 | 60 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-196 | TC2 | PHASE 1 | Prairie 345 kV |  | Pleasant Grove Solar 2, LLC | IL | McHenry | Active | Generation Interconnection | ComEd | 150 | 150 | 90 |  | Capacity | Solar | 9/2/2021 | 12/15/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-048 | TC1 | PHASE 2 | Belvidere-Marengo |  | McHenry County Solar Project, LLC | IL | McHenry | Withdrawn | Generation Interconnection | ComEd | 152.2 | 52.2 | 31.32 |  | Capacity | Storage | 6/28/2019 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-048/AF1-048_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-048/AF1-048_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-321 | TC1 | PHASE 3 | Belvidere-Marengo 138 kV |  | McHenry County Solar Project, LLC | IL | McHenry | Active | Generation Interconnection | ComEd | 100 | 100 | 67 |  | Capacity | Solar | 3/30/2019 | 12/1/2021 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-321/AE2-321_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-321/AE2-321_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-349 | TC1 | PHASE 3 | SILVER LAKE- CHERRY VALLEY 345 KV |  | Deriva Energy Solar, LLC | IL | McHenry | Active | Generation Interconnection | ComEd | 300 | 300 | 0 |  | Energy | Solar | 3/31/2020 | 12/1/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-349/AF2-349_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-349/AF2-349_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-544 | TC2 | PHASE 1 | Silver Lake 345 kV |  | Monarch | IL | McHenry | Active | Generation Interconnection | ComEd | 200 | 200 | 80 |  | Capacity | Storage | 3/31/2021 | 11/6/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-545 | TC2 | PHASE 1 | Silver Lake 345 kV |  | Monarch | IL | McHenry | Active | Generation Interconnection | ComEd | 600 | 400 | 160 |  | Capacity | Storage | 3/31/2021 | 11/6/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-225 | TC1 | PHASE 3 | McLean 345 kV |  | Bright Stalk Solar Park LLC | IL | McLean | Active | Generation Interconnection | ComEd | 150 | 150 | 63 |  | Capacity | Solar | 3/26/2020 | 10/31/2022 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-225/AF2-225_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-225/AF2-225_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-223 | TC1 | PHASE 3 | McLean 345 kV |  | Lexington Chenoa Wind Farm II LLC | IL | McLean | Active | Generation Interconnection | ComEd | 150 | 150 | 19.5 |  | Capacity | Wind | 3/22/2019 | 10/31/2022 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-223/AE2-223_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-223/AE2-223_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-173 | TC1 | PHASE 3 | McLean 345 kV |  | Blooming Grove Solar Energy Center LLC | IL | McLean | Active | Generation Interconnection | ComEd | 250 | 50 | 50 |  | Capacity | Storage | 3/18/2019 | 12/31/2022 | [5 empty] | 1/31/2025 |  |  |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-173/AE2-173_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-374 | TC1 | PHASE 3 | Blue Mound 345 kV |  | Deriva Energy Solar, LLC | IL | McLean | Active | Generation Interconnection | ComEd | 300 | 300 | 180 |  | Capacity | Solar | 9/30/2020 | 12/1/2024 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-374/AG1-374_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-374/AG1-374_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-399 | TC1 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Withdrawn | Generation Interconnection | ComEd | 300 | 300 | 52.8 |  | Capacity | Wind | 9/30/2020 | 9/24/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-399/AG1-399_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-400 | TC1 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Withdrawn | Generation Interconnection | ComEd | 150 | 150 | 150 |  | Capacity | Storage | 9/30/2020 | 9/24/2024 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-400/AG1-400_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-670 | TC2 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Active | Generation Interconnection | ComEd | 250 | 250 | 49.6 |  | Capacity | Wind | 9/30/2020 | 9/25/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-402 | TC1 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Withdrawn | Generation Interconnection | ComEd | 150 | 150 | 150 |  | Capacity | Storage | 9/30/2020 | 9/24/2024 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-402/AG1-402_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-404 | TC1 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Withdrawn | Generation Interconnection | ComEd | 100 | 100 | 100 |  | Capacity | Storage | 9/30/2020 | 9/24/2024 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-404/AG1-404_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-294 | TC2 | PHASE 1 | Mclean 345 kV |  | Blooming Grove Solar Energy Center LLC | IL | McLean | Active | Generation Interconnection | ComEd | 350 | 100 | 60 |  | Capacity | Solar | 9/11/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-295 | TC2 | PHASE 1 | Brokaw to Mt Pulaski 345 kV |  | Invenergy | IL | McLean | Active | Generation Interconnection | ComEd | 130 | 130 | 22.88 |  | Capacity | Wind | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-146 | TC2 | PHASE 1 | White Rock - Wayne 345 kV |  | Mound Solar, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 200 | 200 | 120 |  | Capacity | Solar | 8/26/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-147 | TC2 | PHASE 1 | White Rock - Wayne 345 kV |  | Mound Solar, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 400 | 200 | 120 |  | Capacity | Solar | 8/27/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-148 | TC2 | PHASE 1 | White Rock - Wayne 345 kV |  | Mound Solar, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 600 | 200 | 120 |  | Capacity | Solar | 8/26/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-540 | TC2 | PHASE 1 | Byron to Wayne 345 kV |  | Golden Harvest Energy, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 165 | 165 | 33 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-341 | TC2 | PHASE 1 | ESS-H445 3B 138kv |  | ibVEnergy Partners LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 150 | 150 | 96.6 |  | Capacity | Solar | 9/10/2021 | 12/7/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-702 | TC2 | PHASE 1 | Byron 345 kV |  | Constellation Energy Generation, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 2530 | 88 | 43 |  | Capacity | Nuclear |  | 4/2/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE1-114 | TC1 | PHASE 3 | Maryland-Lancaster 138 kV |  | Leaf River Wind, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 150 | 150 | 34 |  | Capacity | Wind | 9/13/2018 | 12/31/2021 | [5 empty] | 4/1/2025 |  | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE1-114/AE1-114_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-114/AE1-114_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-318 | TC1 | PHASE 1 | Crescent Ridge-Corbin |  | Sky Yield LLC | IL | Putnam | Withdrawn | Generation Interconnection | ComEd | 299.97 | 299.97 | 52.7947 |  | Capacity | Wind | 9/30/2019 | 9/15/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-318/AF1-318_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-769 | TC2 | RRI APPLICATION REVIEW |  |  | Marquis Solar LLC | IL | Putnam | Withdrawn | Generation Interconnection | ComEd | 105 | 105 | 101.2 |  | Capacity | Solar,Storage,Hybrid |  | 2/15/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG2-675 | TC2 | PHASE 1 | Cordova 345 kV |  | Gipper | IL | Rock Island | Active | Generation Interconnection | ComEd | 335 | 80 | 32 |  | Capacity | Storage | 3/31/2021 | 10/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-553 | TC1 | PHASE 3 | Cordova 345 kV |  | Beacon Solar, LLC | IL | Rock Island | Active | Generation Interconnection | ComEd | 260 | 260 | 0 |  | Energy | Solar | 9/30/2020 | 12/29/2023 | [5 empty] | 3/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-553/AG1-553_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-553/AG1-553_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-527 | TC2 | PHASE 1 | Kewanee-Toulon 138 kV |  | Invenergy | IL | Stark | Active | Generation Interconnection | ComEd | 200 | 200 | 26 |  | Capacity | Wind | 3/31/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-297 | TC2 | PHASE 1 | Kewanee - E.D. Edwards 138 kV |  | Invenergy | IL | Stark | Active | Generation Interconnection | ComEd | 200 | 200 | 26 |  | Capacity | Wind | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-353 | TC2 | PHASE 1 | Lena 138 kV |  | Blue Violet Energy, LLC | IL | Stephenson | Active | Generation Interconnection | ComEd | 20 | 20 | 12 |  | Capacity | Solar | 9/10/2021 | 9/10/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-354 | TC2 | PHASE 1 | Lena 138 kV |  | Blue Violet Energy, LLC | IL | Stephenson | Active | Generation Interconnection | ComEd | 60 | 40 | 40 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-314 | TC1 | PHASE 2 | Lena - Lancaster 138 kV |  | High Point Wind Farm, LLC | IL | Stephenson | Withdrawn | Generation Interconnection | ComEd | 212 | 212 | 37.2 |  | Capacity | Wind | 9/30/2019 | 9/15/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-314/AF1-314_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-314/AF1-314_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-201 | TC1 | PHASE 2 | Lena - Lancaster 138 kV |  | Blue Violet Energy, LLC | IL | Stephenson | Withdrawn | Generation Interconnection | ComEd | 199 | 199 | 51.4 |  | Capacity | Wind,Solar,Hybrid | 3/24/2020 | 5/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-201/AF2-201_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-201/AF2-201_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-005 | TC1 | PHASE 2 | Corbin-Crescent Ridge 138 kV |  | Sky Yield LLC | IL | Stephenson | Withdrawn | Generation Interconnection | ComEd | 200 | 200 | 120 |  | Capacity | Solar | 4/29/2020 | 10/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-005/AG1-005_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-005/AG1-005_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-363 | TC2 | PHASE 1 | Powerton 345 kV |  | Mackinaw Solar LLC | IL | Tazewell | Active | Generation Interconnection | ComEd | 300 | 300 | 180 |  | Capacity | Solar | 3/26/2021 | 5/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-364 | TC2 | PHASE 1 | Powerton 345 kV |  | Mackinaw Solar LLC | IL | Tazewell | Active | Generation Interconnection | ComEd | 500 | 200 | 120 |  | Capacity | Solar | 3/26/2021 | 5/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-462 | TC1 | PHASE 3 | Cordova 345 kV |  | Gipper | IL | Whiteside | Active | Generation Interconnection | ComEd | 255 | 255 | 153 |  | Capacity | Solar | 10/1/2020 | 10/1/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-462/AG1-462_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-462/AG1-462_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-296 | TC1 | PHASE 3 | Garden Plain 138 kV |  | Gipper | IL | Whiteside | Active | Generation Interconnection | ComEd | 190.89 | 190.89 | 33.6 |  | Capacity | Wind | 9/30/2019 | 9/15/2022 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-296/AF1-296_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-296/AF1-296_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE1-070 | TC1 | PHASE 2 | Elwood 345 kV |  | Elwood Energy, LLC | IL | Will | Withdrawn | Generation Interconnection | ComEd | 1610 | 0 | 135 |  | Capacity | Natural Gas | 7/31/2018 | 12/31/2020 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE1-070/AE1-070_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-070/AE1-070_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-096 | TC1 | PHASE 2 | Braidwood-East Frankfort 345 kV |  | AEUG | IL | Will | Withdrawn | Generation Interconnection | ComEd | 300 | 300 | 180 |  | Capacity | Solar | 2/12/2020 | 5/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-096/AF2-096_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-096/AF2-096_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-357 | TC2 | PHASE 1 | Wilton 345 kV |  | Bluegill Energy Storage LLC | IL | Will | Active | Generation Interconnection | ComEd | 250 | 250 | 250 |  | Capacity | Storage | 3/26/2021 | 11/15/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-560 | TC2 | PHASE 1 | University Park 138 kV |  | University Park Energy, LLC | IL | Will | Active | Generation Interconnection | ComEd | 473 | 150 | 150 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-567 | TC2 | PHASE 1 | University Park 138 kV |  | University Park Energy, LLC | IL | Will | Active | Generation Interconnection | ComEd | 478 | 5 | 5 |  | Capacity | Natural Gas | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-165 | TC2 | PHASE 1 | Will County 138 kV |  | NRG Midwest Storage LLC | IL | Will | Active | Generation Interconnection | ComEd | 72 | 72 | 0 |  | Energy | Storage | 8/31/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-698 | TC2 | PHASE 1 | Braidwood 345 kV |  | Constellation Energy Generation, LLC | IL | Will | Active | Generation Interconnection | ComEd | 2584 | 130 | 57.6 |  | Capacity | Nuclear |  | 5/6/2027 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-762 | TC2 | RRI APPLICATION REVIEW |  |  | Crete Bess, LLC | IL | Will | Withdrawn | Generation Interconnection | ComEd | 225 | 225 | 225 |  | Capacity | Storage |  | 5/31/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-763 | TC2 | RRI APPLICATION REVIEW |  |  | Lincoln Bess, LLC | IL | Will | Withdrawn | Generation Interconnection | ComEd | 100 | 100 | 100 |  | Capacity | Storage |  | 5/31/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-234 | TC2 | PHASE 1 | Wempletown 345 kV |  | Gemini Solar LLC | IL | Winnebago | Active | Generation Interconnection | ComEd | 224 | 224 | 29.12 |  | Capacity | Solar | 9/10/2021 | 11/21/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-564 | TC2 | PHASE 1 | Rockford II 138 kV |  | Rockford Generation, LLC | IL | Winnebago | Active | Generation Interconnection | ComEd | 330 | 150 | 150 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-516 | TC2 | PHASE 1 | Pecatonica 138kV |  | KESTREL SOLAR, LLC | IL | Winnebago | Active | Generation Interconnection | ComEd | 120 | 120 | 72 |  | Capacity | Solar | 3/31/2021 | 10/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-379 | TC1 | PHASE 1 | Minonk 345 kV |  | Minonk Solar, LLC | IL | Woodford | Withdrawn | Generation Interconnection | ComEd | 200 | 200 | 137.2 |  | Capacity | Solar | 9/30/2020 | 8/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-379/AG1-379_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-361 | TC2 | APPLICATION REVIEW | Minonk 345 kV |  | Minonk Solar, LLC | IL | Woodford | Withdrawn | Generation Interconnection | ComEd | 50 | 50 | 50 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 3/13/2025 | 3/12/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG1-225 | TC1 | PHASE 1 | Adams 138 kV |  | ADAMS SOLAR PROJECT, LLC | IN | Adams | Withdrawn | Generation Interconnection | AEP | 346 | 346 | 207 |  | Capacity | Solar | 9/24/2020 | 12/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-225/AG1-225_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-424 | TC1 | PHASE 1 | Sowers 138 kV |  | Leeward Renewable Energy Development, LLC | IN | Allen | Withdrawn | Generation Interconnection | AEP | 100 | 100 | 60 |  | Capacity | Solar | 9/30/2020 | 12/29/2023 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-424/AG1-424_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-370 | TC2 | PHASE 1 | Tillman 138 kV |  | Tillman Storage LLC | IN | Allen | Active | Generation Interconnection | AEP | 50 | 50 | 20 |  | Capacity | Storage | 3/26/2021 | 10/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-400 | TC2 | PHASE 1 | Allen 345 kV |  | EDPR | IN | Allen | Active | Generation Interconnection | AEP | 100 | 100 | 60 |  | Capacity | Solar | 3/30/2021 | 10/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-402 | TC2 | PHASE 1 | Allen 345 kV |  | EDPR | IN | Allen | Active | Generation Interconnection | AEP | 50 | 50 | 20 |  | Capacity | Storage | 3/30/2021 | 10/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-408 | TC2 | PHASE 1 | Allen 345 kV |  | EDPR | IN | Allen | Active | Generation Interconnection | AEP | 100 | 0 | 18 |  | Capacity | Solar | 3/30/2021 | 9/30/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-549 | TC2 | PHASE 1 | Allen - RP Mone 345 kV |  | Leeward Renewable Energy Development, LLC | IN | Allen | Active | Generation Interconnection | AEP | 180 | 180 | 108 |  | Capacity | Solar | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-768 | TC2 | RRI APPLICATION REVIEW |  |  | RWE LLC | IN | Blackford | Withdrawn | Generation Interconnection | AEP | 110 | 110 | 110 |  | Capacity | Storage |  | 5/29/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG1-433 | TC1 | PHASE 3 | Keystone-DeSoto 345 kV |  | RWE LLC | IN | Blackford | Active | Generation Interconnection | AEP | 300 | 100 | 17.6 |  | Capacity | Wind | 9/30/2020 | 12/31/2023 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-433/AG1-433_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-433/AG1-433_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-375 | TC1 | PHASE 3 | Sorenson-Desoto 345 kV |  | Blackford County | IN | Blackford | Active | Generation Interconnection | AEP | 100 | 100 | 60 |  | Capacity | Solar | 9/30/2020 | 10/31/2024 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-375/AG1-375_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-375/AG1-375_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-068 | TC1 | PHASE 3 | Jay 138 kV |  | Leeward Renewable Energy Development, LLC | IN | Blackford | Active | Generation Interconnection | AEP | 150 | 150 | 90 |  | Capacity | Solar | 1/30/2020 | 10/3/2022 | [5 empty] | 2/3/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-068/AF2-068_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-068/AF2-068_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-177 | TC1 | PHASE 3 | Sorenson-DeSoto #2 345 kV |  | Blackford County | IN | Blackford | Active | Generation Interconnection | AEP | 200 | 200 | 26 |  | Capacity | Wind | 3/20/2020 | 10/31/2023 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-177/AF2-177_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-177/AF2-177_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-388 | TC1 | PHASE 3 | Keystone-Desoto 345 kV |  | RWE LLC | IN | Blackford | Active | Generation Interconnection | AEP | 200 | 200 | 35.2 |  | Capacity | Wind | 3/31/2020 | 12/15/2023 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-388/AF2-388_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-388/AF2-388_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-331 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Cobia Solar LLC | IN | Decatur | Active | Generation Interconnection | AEP | 715 | 200 | 156 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-164 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Cobia Solar LLC | IN | Decatur | Active | Generation Interconnection | AEP | 385 | 270 | 35.1 |  | Capacity | Solar | 2/25/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-219 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Cobia Solar LLC | IN | Decatur | Active | Generation Interconnection | AEP | 715 | 330 | 42.9 |  | Capacity | Solar | 3/9/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-085 | TC2 | PHASE 1 | Delaware-Royerton 138 kV |  | Royerton Solar, LLC | IN | Delaware | Active | Generation Interconnection | AEP | 140 | 40 | 24 |  | Capacity | Solar | 1/22/2021 | 12/31/2023 | [5 empty] | 5/16/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-519 | TC2 | PHASE 1 | Royerton - Desoto 138 kV |  | Muncie Solar 1, LLC | IN | Delaware | Active | Generation Interconnection | AEP | 111 | 111 | 87.8 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 2/29/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-370 | TC1 | PHASE 3 | Delaware-Royerton 138 kV |  | Royerton Solar, LLC | IN | Delaware | Active | Generation Interconnection | AEP | 100 | 0 | 20 |  | Capacity | Storage | 3/31/2020 | 12/31/2023 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-370/AF2-370_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-370/AF2-370_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-335 | TC1 | PHASE 3 | Delaware-Royerton 138 kV |  | Royerton Solar, LLC | IN | Delaware | Active | Generation Interconnection | AEP | 100 | 100 | 60 |  | Capacity | Solar | 3/31/2020 | 12/31/2023 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-335/AF2-335_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-335/AF2-335_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-173 | TC1 | PHASE 3 | Desoto 345 kV |  | Esker | IN | Delaware | Active | Generation Interconnection | AEP | 140 | 140 | 84 |  | Capacity | Solar | 3/19/2020 | 10/31/2023 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-173/AF2-173_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-173/AF2-173_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-367 | TC1 | PHASE 3 | DeSoto 345 kV |  | Esker | IN | Delaware | Active | Generation Interconnection | AEP | 100 | 100 | 60 |  | Capacity | Solar | 9/30/2020 | 10/31/2024 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-367/AG1-367_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-367/AG1-367_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-742 | TC2 | RRI APPLICATION REVIEW | Delaware-Royerton 138 kV |  | Royerton Solar, LLC | IN | Delaware | Withdrawn | Generation Interconnection | AEP | 140 | 0 | 20 |  | Capacity | Storage |  | 10/30/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-307 | TC2 | PHASE 1 | Delaware-Van Buren 138 kV |  | Invenergy | IN | Delaware | Active | Generation Interconnection | AEP | 213 | 50 | 50 |  | Capacity | Storage | 9/11/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-304 | TC2 | PHASE 1 | Delaware-Van Buren 138 kV |  | Meadow Forge Solar Energy LLC | IN | Delaware | Active | Generation Interconnection | AEP | 163 | 0 | 9.8 |  | Capacity | Solar | 9/11/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-332 | TC2 | PHASE 1 | East Elkhart – Elcona Tap 138 kV |  | Amberjack Solar LLC | IN | Elkhart | Active | Generation Interconnection | AEP | 200 | 100 | 100 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-248 | TC2 | PHASE 1 | East Elkhart – Elcona Tap 138 kV |  | Amberjack Solar LLC | IN | Elkhart | Active | Generation Interconnection | AEP | 100 | 100 | 0 |  | Energy | Storage | 3/17/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-224 | TC1 | PHASE 1 | Pendleton-Tanners Creek 138 kV |  | RUSH SOLAR PROJECT II, LLC | IN | Fayette | Withdrawn | Generation Interconnection | AEP | 210 | 210 | 126 |  | Capacity | Solar | 9/24/2020 | 12/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-224/AG1-224_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-226 | TC1 | PHASE 3 | Eugene-Dequine 345 kV |  | Dolphin Solar LLC | IN | Fountain | Active | Generation Interconnection | AEP | 450 | 450 | 142 |  | Capacity | Solar | 9/24/2020 | 6/1/2024 | [5 empty] | 4/7/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-226/AG1-226_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-226/AG1-226_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-163 | TC2 | PHASE 1 | Dequine-Eugene 345 kV |  | Dolphin Solar LLC | IN | Fountain | Active | Generation Interconnection | AEP | 700 | 250 | 35 |  | Capacity | Solar | 2/25/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-345 | TC2 | PHASE 1 | Eugene - Dequine 345 kV |  | Dolphin Solar LLC | IN | Fountain | Active | Generation Interconnection | AEP | 150 | 50 | 39 |  | Capacity | Storage | 3/26/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-343 | TC2 | PHASE 1 | Eugene - Dequine 345 kV |  | Dolphin Solar LLC | IN | Fountain | Active | Generation Interconnection | AEP | 100 | 100 | 78 |  | Capacity | Storage | 3/26/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-454 | TC2 | PHASE 1 | Dequine - Eugene 345 kV |  | ALGONQUIN POWER (FOUNTAIN COUNTY SOLAR), LLC | IN | Fountain | Withdrawn | Generation Interconnection | AEP | 300 | 300 | 210 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 5/5/2025 | 4/6/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-455 | TC2 | PHASE 1 | Dequine - Sullivan 345 kV |  | ALGONQUIN POWER (FOUNTAIN COUNTY SOLAR), LLC | IN | Fountain | Withdrawn | Generation Interconnection | AEP | 280 | 280 | 196 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 5/5/2025 | 4/6/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-221 | TC1 | PHASE 2 | College Corner-Drewersburg 138 kV |  | Yellow Perch Solar LLC | IN | Franklin | Withdrawn | Generation Interconnection | AEP | 180 | 180 | 25.2 |  | Capacity | Solar | 9/27/2019 | 6/1/2022 | [5 empty] | 1/28/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-221/AF1-221_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-221/AF1-221_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-191 | TC2 | PHASE 1 | Mississinewa 138 kV |  | BR Solar | IN | Grant | Active | Generation Interconnection | AEP | 30 | 30 | 18 |  | Capacity | Solar,Storage,Hybrid | 2/27/2021 | 11/30/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-192 | TC2 | PHASE 1 | Mississinewa 138 kV |  | BR Solar | IN | Grant | Active | Generation Interconnection | AEP | 19 | 19 | 11.4 |  | Capacity | Solar,Storage,Hybrid | 2/27/2021 | 12/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-306 | TC2 | PHASE 1 | Mississinewa-Gaston 138 kV |  | Golden Aster Solar Energy LLC | IN | Grant | Active | Generation Interconnection | AEP | 160 | 0 | 28.8 |  | Capacity | Solar | 9/11/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-487 | TC2 | PHASE 1 | Madison - Tanners Creek 138 kV |  | Bellflower | IN | Henry | Active | Generation Interconnection | AEP | 152.5 | 0 | 10.6 |  | Capacity | Solar | 3/31/2021 | 5/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-084 | TC2 | APPLICATION REVIEW | Greentown 138 kV |  | Locomotive Solar, LLC | IN | Howard | Withdrawn | Generation Interconnection | AEP | 100 | 100 | 40 |  | Capacity | Storage | 1/22/2021 | 12/31/2023 | [5 empty] | 4/4/2025 | 4/3/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-291 | TC2 | PHASE 1 | Rock Creek-Hummel Creek 138 kV |  | Invenergy | IN | Huntington | Active | Generation Interconnection | AEP | 185 | 185 | 111 |  | Capacity | Solar | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-041 | TC2 | PHASE 1 | Pennville 138 kV |  | ACE | IN | Jay | Active | Generation Interconnection | AEP | 125 | 125 | 75 |  | Capacity | Solar | 6/23/2021 | 7/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-308 | TC2 | PHASE 1 | Pennville - Adams 138 kV |  | Invenergy | IN | Jay | Active | Generation Interconnection | AEP | 205 | 50 | 50 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-447 | TC1 | PHASE 3 | Olive-University Park 345 kV |  | RWE LLC | IN | LaPorte | Active | Generation Interconnection | AEP | 305 | 55 | 55 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-447/AG1-447_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-447/AG1-447_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-436 | TC1 | PHASE 3 | Olive-University Park 345 kV |  | RWE LLC | IN | LaPorte | Active | Generation Interconnection | AEP | 250 | 125 | 75 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-436/AG1-436_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-436/AG1-436_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-407 | TC1 | PHASE 3 | Fall Creek 345 kV |  | Liberty Madison Storage LLC | IN | Madison | Active | Generation Interconnection | AEP | 300 | 300 | 300 |  | Capacity | Storage | 3/31/2020 | 6/1/2022 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-407/AF2-407_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-407/AF2-407_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-165 | TC2 | PHASE 1 | Dumont-Greentown 765 kV |  | Wahoo Solar LLC | IN | Marshall | Active | Generation Interconnection | AEP | 200 | 200 | 26 |  | Capacity | Solar | 2/25/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-212 | TC2 | PHASE 1 | Dumont-Greentown 765 kV |  | Wahoo Solar LLC | IN | Marshall | Active | Generation Interconnection | AEP | 400 | 200 | 26 |  | Capacity | Solar | 3/8/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-330 | TC2 | PHASE 1 | Dumont - Greentown 765 kV |  | Wahoo Solar LLC | IN | Marshall | Active | Generation Interconnection | AEP | 600 | 200 | 156 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-328 | TC2 | PHASE 1 | Dumont - Greentown 765 kV |  | Wahoo Solar LLC | IN | Marshall | Active | Generation Interconnection | AEP | 600 | 200 | 26 |  | Capacity | Solar | 3/25/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-029 | TC2 | PHASE 1 | Forest G. Hipple-Collingwood 345 kV |  | Southern Pike Solar LLC | IN | Noble | Active | Generation Interconnection | AEP | 300 | 300 | 39 |  | Capacity | Solar | 10/23/2020 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-453 | TC1 | PHASE 1 | Guardian 138 kV |  | RWE LLC | IN | Noble | Withdrawn | Generation Interconnection | AEP | 140 | 140 | 84 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-453/AG1-453_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-454 | TC1 | PHASE 1 | Guardian 138 kV |  | RWE LLC | IN | Noble | Withdrawn | Generation Interconnection | AEP | 190 | 50 | 50 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-454/AG1-454_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-482 | TC2 | PHASE 1 | Olive - Reynolds #2 345 kV |  | Lightsource Renewable Energy Development, LLC | IN | Pulaski | Active | Generation Interconnection | AEP | 338 | 78 | 78 |  | Capacity | Storage | 9/10/2021 | 9/25/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-305 | TC2 | PHASE 1 | Olive - Reynolds 345 kV |  | Bottlebrush | IN | Pulaski | Active | Generation Interconnection | AEP | 275 | 0 | 35.72 |  | Capacity | Solar | 9/10/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-302 | TC2 | PHASE 1 | Olive - Reynolds 345 kV |  | Bottlebrush | IN | Pulaski | Active | Generation Interconnection | AEP | 275 | 75 | 75 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-709 | TC2 | RRI APPLICATION REVIEW | Olive-Reynolds #2 345 kV |  | Moss Creek Solar, LLC | IN | Pulaski | Withdrawn | Generation Interconnection | AEP | 200 | 0 | 80 |  | Capacity | Storage |  | 5/31/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG2-637 | TC2 | PHASE 1 | Randolph - Hodgin 138 kV |  | ACE | IN | Randolph | Active | Generation Interconnection | AEP | 150 | 150 | 90 |  | Capacity | Solar | 3/31/2021 | 4/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-432 | TC2 | PHASE 1 | Randolph - Hodgin 138 kV |  | ACE | IN | Randolph | Active | Generation Interconnection | AEP | 150 | 0 | 60 |  | Capacity | Storage | 9/10/2021 | 4/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-337 | TC2 | PHASE 1 | Randolph - Hodgin 138 kV |  | Summit Solar, LLC | IN | Randolph | Active | Generation Interconnection | AEP | 46 | 46 | 39 |  | Capacity | Solar | 9/10/2021 | 9/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-401 | TC2 | PHASE 1 | Losantville 345 kV |  | Riverstart | IN | Randolph | Active | Generation Interconnection | AEP | 200 | 0 | 44 |  | Capacity | Solar | 3/30/2021 | 12/15/2021 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-550 | TC2 | PHASE 1 | Bluff Point - Randolph 138 kV |  | Riverstart | IN | Randolph | Active | Generation Interconnection | AEP | 100 | 100 | 60 |  | Capacity | Solar | 3/31/2021 | 10/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-551 | TC2 | PHASE 1 | Bluff Point - Randolph 138 kV |  | Riverstart | IN | Randolph | Active | Generation Interconnection | AEP | 150 | 50 | 20 |  | Capacity | Storage | 3/31/2021 | 10/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-449 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Salmon Solar LLC | IN | Rush | Active | Generation Interconnection | AEP | 835 | 120 | 15 |  | Capacity | Solar | 3/30/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-162 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Salmon Solar LLC | IN | Rush | Active | Generation Interconnection | AEP | 115 | 115 | 15 |  | Capacity | Solar | 2/25/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-297 | TC1 | PHASE 3 | Hanna-Tanners Creek 345 kV |  | Hectate LLC | IN | Shelby | Active | Generation Interconnection | AEP | 300 | 300 | 75 |  | Capacity | Storage | 9/29/2020 | 12/31/2023 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-297/AG1-297_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-297/AG1-297_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-130 | TC1 | PHASE 1 | Rockport 765 kV |  | Sand Ridge Solar Project LLC | IN | Spencer | Withdrawn | Generation Interconnection | AEP | 800 | 800 | 480 |  | Capacity | Solar,Storage,Hybrid | 2/28/2019 | 12/1/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-130/AE2-130_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-072 | TC2 | PHASE 1 | Rockport 765 kV |  | Bluegrass Power LLC | IN | Spencer | Active | Generation Interconnection | AEP | 700 | 700 | 700 |  | Capacity | Natural Gas | 1/6/2021 | 5/31/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-230 | TC2 | PHASE 1 | Dumont 345 kV |  | Dumont Solar, LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 150 | 150 | 90 |  | Capacity | Solar | 3/12/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-562 | TC2 | PHASE 1 | Elderberry 345 kV |  | St. Joseph Energy Center, LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 786 | 71 | 35 |  | Capacity | Natural Gas | 3/31/2021 | 10/31/2022 | [5 empty] | 6/4/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-391 | TC2 | PHASE 1 | Olive 138 kV | Michiana Solar | ibV Energy Partners LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 100 | 100 | 67 |  | Capacity | Solar | 9/10/2021 | 7/16/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-392 | TC2 | PHASE 1 | Gravel Pit-Kankakee 138 kV |  | ibVEnergy Partners LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 90 | 90 | 60 |  | Capacity | Solar | 9/10/2021 | 7/16/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-152 | TC2 | PHASE 1 | Dumont 345 kV |  | Dumont Solar, LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 150 | 0 | 30 |  | Capacity | Storage | 8/27/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-153 | TC2 | PHASE 1 | Dumont 345 kV |  | Dumont Solar, LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 300 | 150 | 90 |  | Capacity | Solar | 8/27/2021 | 12/31/2025 | [5 empty] | 5/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-154 | TC2 | PHASE 1 | Dumont 345 kV |  | Dumont Solar, LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 300 | 0 | 30 |  | Capacity | Storage | 8/27/2021 | 12/31/2025 | [5 empty] | 5/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-245 | TC2 | PHASE 1 | Olive - Reynolds #1 345 kV |  | Starke Central Project, LLC | IN | Starke | Active | Generation Interconnection | AEP | 210 | 210 | 126 |  | Capacity | Solar | 3/16/2021 | 12/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-522 | TC1 | PHASE 2 | Sullivan-Rockport 765 kV |  | PJM Solar Devco I, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 300 | 300 | 180 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-522/AG1-522_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-522/AG1-522_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-523 | TC1 | PHASE 2 | Sullivan-Rockport 765 kV |  | PJM Solar Devco I, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 600 | 300 | 180 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-523/AG1-523_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-523/AG1-523_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-524 | TC1 | PHASE 2 | Sullivan-Rockport 765 kV |  | PJM Solar Devco I, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 900 | 300 | 180 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-524/AG1-524_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-524/AG1-524_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-525 | TC1 | PHASE 2 | Sullivan-Rockport 765 kV |  | PJM Solar Devco I, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 1200 | 300 | 180 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-525/AG1-525_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-525/AG1-525_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-088 | TC1 | PHASE 3 | Sullivan 345 kV |  | Grain Belt Express LLC | IN | Sullivan | Active | Merchant Transmission | AEP | 1000 | 1000 | 1000 |  | Capacity | Not Specified | 8/30/2019 | 12/31/2025 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-088/AF1-088_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-088/AF1-088_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started | DC | 1000 F/1000 NFTIR/0 F/1000 NFTWR
AF2-008 | TC1 | PHASE 3 | Sullivan 345 kV |  | Grain Belt Express LLC | IN | Sullivan | Active | Merchant Transmission | AEP | 2000 | 1000 | 500 |  | Capacity | Not Specified | 10/3/2019 | 12/31/2025 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-008/AF2-008_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-008/AF2-008_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started | DC | 500 FTIR/1000 NFTIR
AH1-292 | TC2 | PHASE 1 | Sullivan 345 kV |  | Trade Post Solar LLC | IN | Sullivan | Active | Generation Interconnection | AEP | 200 | 0 | 44 |  | Capacity | Solar | 9/10/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-690 | TC2 | APPLICATION REVIEW | Sullivan - Rockport 765 kV |  | Solar Prairie Holdco, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 300 | 300 | 120 |  | Capacity | Storage | 3/31/2021 | 6/1/2024 | [5 empty] | 1/29/2025 | 1/29/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-084 | TC2 | PHASE 1 | Sullivan 345 kV |  | Grain Belt Express LLC | IN | Sullivan | Active | Merchant Transmission | AEP | 2500 | 500 | 500 |  | Capacity | Not Specified | 7/30/2021 | 12/31/2025 | [5 empty] | 5/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started | DC | 500 FTIR
AH1-745 | TC2 | RRI APPLICATION REVIEW | Eugene-Sullivan 345 kV |  | Tenaska | IN | Vermillion | Withdrawn | Generation Interconnection | AEP | 770 | 770 | 707 |  | Capacity | Natural Gas |  | 5/30/2031 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-740 | TC2 | RRI APPLICATION REVIEW | Sullivan-Dequine 345 kV |  | Tenaska | IN | Vermillion | Withdrawn | Generation Interconnection | AEP | 770 | 770 | 707 |  | Capacity | Natural Gas |  | 5/30/2031 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AF1-204 | TC1 | PHASE 3 | Eugene 345 kV |  | Vermilion Grove Wind, LLC | IN | Vermillion | Active | Generation Interconnection | AEP | 255 | 255 | 63.75 |  | Capacity | Wind | 9/25/2019 | 12/31/2022 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-204/AF1-204_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-204/AF1-204_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-126 | TC2 | PHASE 1 | Eugene 345 kV |  | TGE LLC | IN | Vermillion | Active | Generation Interconnection | AEP | 150 | 150 | 90 |  | Capacity | Solar,Storage,Hybrid | 1/29/2021 | 6/30/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-471 | TC1 | PHASE 3 | Up Church-Wayne County 69 kV |  | Barrelhead Solar, LLC | KY |  | Active | Generation Interconnection | EKPC | 54 | 54 | 32.4 |  | Capacity | Solar | 9/30/2020 | 10/2/2023 | [5 empty] | 2/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-471/AG1-471_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-471/AG1-471_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-116 | TC2 | PHASE 1 | Olive-Reynolds 345 #1 345 kV |  | Honey Creek Energy, LLC | IN | White | Active | Generation Interconnection | AEP | 300 | 100 | 60 |  | Capacity | Solar,Storage,Hybrid | 1/29/2021 | 10/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-014 | TC2 | PHASE 1 | Meadow Lake 345 kV |  | Black Prarie | IN | White | Active | Generation Interconnection | AEP | 50 | 50 | 20 |  | Capacity | Storage | 10/19/2020 | 10/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-491 | TC2 | PHASE 1 | Meadow Lake 345 kV |  | Black Prarie | IN | White | Active | Generation Interconnection | AEP | 100 | 100 | 60 |  | Capacity | Solar | 3/31/2021 | 9/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-492 | TC2 | PHASE 1 | Meadow Lake 345 kV |  | Black Prarie | IN | White | Active | Generation Interconnection | AEP | 50 | 50 | 20 |  | Capacity | Storage | 3/31/2021 | 9/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-298 | TC2 | PHASE 1 | Meridian 345 kV |  | Invenergy | IN | Whitley | Active | Generation Interconnection | AEP | 75 | 75 | 75 |  | Capacity | Storage | 9/14/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-239 | TC2 | PHASE 1 | Upchurch - Zula 69 kV |  | Clinton Solar, LLC | KY | Boone | Active | Generation Interconnection | EKPC | 80 | 80 | 48 |  | Capacity | Solar | 9/9/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-428 | TC2 | PHASE 1 | Tommy Gooch - Garrard County 69 kV |  | ACE | KY | Boone | Active | Generation Interconnection | EKPC | 100 | 0 | 40 |  | Capacity | Storage | 9/10/2021 | 9/1/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-466 | TC2 | APPLICATION REVIEW | Baker - Broadford 765 kV |  | Stambaugh | KY | Boone | Withdrawn | Generation Interconnection | AEP | 600 | 600 | 360 |  | Capacity | Solar | 9/10/2021 | 12/31/2024 | [5 empty] | 2/25/2025 | 2/25/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-467 | TC2 | APPLICATION REVIEW | Baker - Broadford 765 kV |  | Stambaugh | KY | Boone | Withdrawn | Generation Interconnection | AEP | 900 | 300 | 120 |  | Capacity | Storage | 9/10/2021 | 12/31/2024 | [5 empty] | 2/25/2025 | 2/25/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-159 | TC2 | PHASE 1 | Williamstown 69 kV |  | Round Trip, LLC | KY | Grant | Active | Generation Interconnection | EKPC | 61 | 61 | 57.6 |  | Capacity | Solar,Storage,Hybrid | 2/25/2021 | 9/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-615 | TC2 | PHASE 1 | Carlos Junction-Garrett 138 kV |  | Squirrel Run Solar, L.L.C. | MD | Allegany | Active | Generation Interconnection | APS | 100 | 100 | 62.6 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-617 | TC2 | PHASE 1 | Waugh Chapel 115 kV |  | Dairy Farm Solar, L.L.C. | MD | Anne Arundel | Active | Generation Interconnection | BGE | 55 | 55 | 33 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-261 | TC2 | PHASE 1 | Northeast - Riverside 230 kV | Pulaski Energy Storage | Pulaski Energy Storage LLC | MD | Baltimore County | Active | Generation Interconnection | BGE | 135 | 135 | 135 |  | Capacity | Storage | 9/10/2021 | 6/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-736 | TC2 | RRI APPLICATION REVIEW |  |  | Carroll Island BESS I LLC | MD | Baltimore County | Withdrawn | Generation Interconnection | BGE | 300 | 300 | 300 |  | Capacity | Storage |  | 8/1/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG2-618 | TC2 | PHASE 1 | Morgantown 230 kV |  | DESRI Tidewater Development, L.L.C. | MD | Charles | Active | Generation Interconnection | PEPCO | 110 | 110 | 71.5 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-181 | TC2 | PHASE 1 | Airey - Golden Hill 69 kV |  | Old Line Energy, LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 28 | 28 | 2.8 |  | Capacity | Solar | 2/26/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-092 | TC2 | PHASE 1 | Todd 69 kV |  | Richfield Solar Energy LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 50 | 0 | 11 |  | Capacity | Solar | 1/26/2021 | 12/31/2021 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-450 | TC1 | PHASE 3 | Airey-Vienna 69 kV II |  | RWE LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 125 | 25 | 25 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 1/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-450/AG1-450_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-450/AG1-450_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-358 | TC1 | PHASE 3 | Airey-Vienna 69 kV |  | RWE LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 100 | 100 | 60 |  | Capacity | Solar | 3/31/2020 | 12/15/2023 | [5 empty] | 1/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-358/AF2-358_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-358/AF2-358_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-739 | TC2 | RRI APPLICATION REVIEW |  |  | Richfield Solar Energy LLC | MD | Dorchester | Withdrawn | Generation Interconnection | DPL | 70 | 20 | 20 |  | Capacity | Storage |  | 12/31/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-316 | TC2 | PHASE 1 | Todd 25 kV |  | Todd Solar LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 20 | 0 | 4.4 |  | Capacity | Solar | 9/11/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-283 | TC2 | PHASE 1 | Mount Storm-Pruntytown 500kV | CPV Wilson Solar | CPV LLC | MD | Garrett | Active | Generation Interconnection | APS | 200 | 200 | 120 |  | Capacity | Solar | 9/9/2021 | 10/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-505 | TC2 | PHASE 1 | Westvaco - Mt Zion 138 kV |  | Fairlawn Hydroelectric Company LLC | MD | Garrett | Active | Generation Interconnection | APS | 14 | 14 | 14 |  | Capacity | Hydro | 3/31/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-587 | TC2 | PHASE 1 | Graceton 230 kV |  | Old Line Energy, LLC | MD | Harford | Active | Generation Interconnection | BGE | 50 | 50 | 20 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-725 | TC2 | PHASE 1 | Conastone 500 kV |  | Cardinal Energy Storage East, LLC | MD | Harford | Active | Generation Interconnection | BGE | 500 | 500 | 500 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-759 | TC2 | RRI APPLICATION REVIEW |  |  | Cardinal Energy Storage East, LLC | MD | Montgomery | Withdrawn | Generation Interconnection | APS | 600 | 600 | 600 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG1-483 | TC1 | FINAL AGREEMENT | Dickerson 230 kV | Fourth Quarter | Fourth Quarter BESS, LLC | MD | Montgomery | EP | Generation Interconnection | PEPCO | 500 | 500 | 500 |  | Capacity | Storage | 10/1/2020 | 6/1/2024 | 2/1/2030 |  | 2/1/2030 | 12/15/2029 | 11/1/2029 | 4/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-483/AG1-483_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-483/AG1-483_imp_PHASE_2.htm | Posted |  | Not Required | https://www.pjm.com//pjmfiles/pub/planning/project-queues/gia/ag1_483_gia.pdf | Posted |  | Not Started
AH1-738 | TC2 | RRI APPLICATION REVIEW | Burches Hill - Chalk Point 500 kV |  | Lighthouse | MD | Prince George's | Withdrawn | Generation Interconnection | PEPCO | 200 | 200 | 200 |  | Capacity | Storage |  | 5/31/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-744 | TC2 | PHASE 1 | Cheltenham 500 kV |  | Parkway Generation Operating LLC | MD | Prince George's | Active | Generation Interconnection | PEPCO | 853.5 | 53.5 | 48.285 |  | Capacity | Natural Gas |  | 11/22/2027 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-552 | TC2 | PHASE 1 | Chalk Point 230 kV |  | Chalk Point Steam, LLC | MD | Prince George's | Active | Generation Interconnection | PEPCO | 670.2 | 670.2 | 670.2 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-536 | TC2 | PHASE 1 | Church-Oil City 138kV |  | Old Line Energy, LLC | MD | Queen Anne's | Active | Generation Interconnection | DPL | 41.8 | 41.8 | 8.5 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-380 | TC2 | PHASE 1 | Carville 138 kV IV |  | Concho Solar I, LLC | MD | Queen Anne's | Active | Generation Interconnection | DPL | 106 | 20 | 20 |  | Capacity | Storage | 3/29/2021 | 9/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-281 | TC2 | PHASE 1 | Church 138 kV |  | Church Storage LLC | MD | Queen Anne's | Active | Generation Interconnection | DPL | 50 | 50 | 50 |  | Capacity | Storage | 3/22/2021 | 5/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-356 | TC2 | PHASE 1 | Kings Creek 138kV |  | Great Bay Solar II, LLC | MD | Somerset | Withdrawn | Generation Interconnection | DPL | 30 | 30 | 30 |  | Capacity | Storage | 9/10/2021 | 9/30/2023 | [5 empty] | 5/5/2025 | 3/14/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-379 | TC2 | PHASE 1 | Easton - Steele 138 kV III |  | Crockett Solar I, LLC | MD | Talbot | Active | Generation Interconnection | DPL | 79 | 20 | 20 |  | Capacity | Storage | 3/29/2021 | 9/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-279 | TC2 | PHASE 1 | Hagerstown-Conservit 34.5 kV |  | Franklin Energy, LLC | MD | Washington | Active | Generation Interconnection | APS | 20 | 20 | 12.9 |  | Capacity | Solar | 3/22/2021 | 9/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-057 | TC2 | PHASE 1 | Edgewood 12.47 kV |  | Kumquat & Citron Cleantech LLC | MD | Wicomico | Active | Generation Interconnection | DPL | 7.2 | 7.2 | 3 |  | Capacity | Solar | 7/15/2021 | 1/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-380 | TC2 | PHASE 1 | Mt Olive - Kenny 69kV |  | Forest Lane Solar, LLC | MD | Worcester | Active | Generation Interconnection | DPL | 20 | 20 | 12 |  | Capacity | Solar | 9/10/2021 | 12/20/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-309 | TC2 | PHASE 1 | Kenzie Creek-Colby 138 kV |  | Wingstem Solar Energy LLC | MI | Cass | Active | Generation Interconnection | AEP | 150 | 0 | 27 |  | Capacity | Solar | 9/11/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-396 | TC1 | PHASE 3 | Stinger 138 kV |  | Steelhead Solar, LLC | MI | Cass | Active | Generation Interconnection | AEP | 200 | 200 | 200 |  | Capacity | Solar,Storage,Hybrid | 3/31/2020 | 12/31/2023 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-396/AF2-396_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-396/AF2-396_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-176 | TC1 | PHASE 3 | Corey 138 kV |  | Three Lakes Solar LLC | MI | St. Joseph | Active | Generation Interconnection | AEP | 300 | 300 | 155.684 |  | Capacity | Solar,Storage,Hybrid | 9/25/2019 | 10/31/2022 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-176/AF1-176_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-176/AF1-176_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-161 | TC1 | PHASE 3 | Valley 138 kV |  | Decatur Storage LLC | MI | Van Buren | Active | Generation Interconnection | AEP | 50 | 50 | 25 |  | Capacity | Storage | 9/20/2019 | 3/1/2022 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-161/AF1-161_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-161/AF1-161_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-325 | TC1 | PHASE 3 | Valley 138 kV |  | Southwest Michigan Solar Project, LLC | MI | Van Buren | Active | Generation Interconnection | AEP | 152.2 | 52.2 | 31.32 |  | Capacity | Storage | 3/30/2019 | 12/1/2022 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-325/AE2-325_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-325/AE2-325_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-109 | TC1 | PHASE 3 | Valley 138 kV |  | Decatur Storage LLC | MI | Van Buren | Active | Generation Interconnection | AEP | 50 | 0 | 25 |  | Capacity | Storage | 8/31/2020 | 3/1/2022 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-109/AG1-109_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-109/AG1-109_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-130 | TC2 | APPLICATION REVIEW | Colby Tap-Valley 138 kV |  | CP Glenwood LLC | MI | Van Buren | Withdrawn | Generation Interconnection | AEP | 55 | 55 | 37.2 |  | Capacity | Solar,Storage,Hybrid | 2/2/2021 | 12/31/2026 | [5 empty] | 4/2/2025 | 3/30/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-131 | TC2 | APPLICATION REVIEW | Almena-Valley 69 kV |  | CP LLC | MI | Van Buren | Withdrawn | Generation Interconnection | AEP | 40 | 40 | 20 |  | Capacity | Solar | 2/1/2021 | 12/31/2026 | [5 empty] | 4/2/2025 | 3/31/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-132 | TC2 | APPLICATION REVIEW | Hartford-South Haven 69 kV |  | CP | MI | Van Buren | Withdrawn | Generation Interconnection | AEP | 15 | 15 | 7.5 |  | Capacity | Solar | 2/1/2021 | 12/31/2026 | [5 empty] | 4/2/2025 | 3/30/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-272 | TC2 | PHASE 1 | Argenta - Twin Branch 345 kV |  | Bankson Solar Project, LLC | MI | Van Buren | Active | Generation Interconnection | AEP | 185 | 185 | 123.9 |  | Capacity | Solar | 9/10/2021 | 5/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-271 | TC2 | PHASE 1 | Cashie 230 kV |  | Merry Hill PV I, LLC | NC | Bertie | Active | Generation Interconnection | Dominion | 110 | 40 | 24 |  | Capacity | Solar | 9/9/2021 | 9/20/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-382 | TC2 | PHASE 1 | Cashie 230 kV |  | Merry Hill PV I, LLC | NC | Bertie | Active | Generation Interconnection | Dominion | 70 | 70 | 42 |  | Capacity | Solar | 3/29/2021 | 9/20/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-437 | TC1 | PHASE 2 | Cashie-Earleys 230 kV |  | RWE LLC | NC | Bertie | Withdrawn | Generation Interconnection | Dominion | 100 | 100 | 60 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-437/AG1-437_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-437/AG1-437_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-438 | TC1 | PHASE 2 | Cashie-Earleys 230 kV |  | RWE LLC | NC | Bertie | Withdrawn | Generation Interconnection | Dominion | 100 | 100 | 60 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-438/AG1-438_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-438/AG1-438_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-442 | TC1 | PHASE 2 | Cashie-Earleys 230 kV |  | RWE LLC | NC | Bertie | Withdrawn | Generation Interconnection | Dominion | 135 | 35 | 35 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-442/AG1-442_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-442/AG1-442_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-443 | TC1 | PHASE 2 | Cashie-Earleys 230 kV |  | RWE LLC | NC | Bertie | Withdrawn | Generation Interconnection | Dominion | 135 | 35 | 35 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-443/AG1-443_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-443/AG1-443_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-081 | TC1 | PHASE 3 | Moyock 230 kV |  | Currituck Solar, LLC | NC | Currituck | Active | Generation Interconnection | Dominion | 80 | 80 | 56 |  | Capacity | Solar | 1/31/2020 | 12/1/2023 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-081/AF2-081_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-081/AF2-081_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-239 | TC2 | PHASE 1 | Hickory-Shawboro 230 kV |  | Ranchland Solar, LLC | NC | Currituck | Active | Generation Interconnection | Dominion | 60 | 0 | 0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-033 | TC2 | PHASE 1 | Sligo 34.5 kV |  | Sligo Solar, LLC | NC | Currituck | Active | Generation Interconnection | Dominion | 19.5 | 19.5 | 13 |  | Capacity | Solar | 6/14/2021 | 8/15/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-728 | TC2 | RRI APPLICATION REVIEW |  |  | Voyager BESS, LLC | NC | Currituck | Withdrawn | Generation Interconnection | Dominion | 185 | 185 | 185 |  | Capacity | Storage |  | 11/29/2027 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-311 | TC2 | PHASE 1 | Heartsease DP - Mayo Dunbar 115kV |  | Edgecombe Solar LLC | NC | Edgecombe | Active | Generation Interconnection | Dominion | 75 | 0 | 2.25 |  | Capacity | Solar | 9/10/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-324 | TC1 | PHASE 2 | Edgecombe 230 kV |  | Bridge Solar, LLC | NC | Edgecombe | Withdrawn | Generation Interconnection | Dominion | 75 | 75 | 45 |  | Capacity | Solar | 3/30/2020 | 11/30/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-324/AF2-324_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-324/AF2-324_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-444 | TC1 | PHASE 2 | Chinquapin 230 kV |  | RWE LLC | NC | Edgecombe | Withdrawn | Generation Interconnection | Dominion | 330 | 80 | 80 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-444/AG1-444_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-444/AG1-444_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-439 | TC1 | PHASE 2 | Chinquapin 230 kV |  | RWE LLC | NC | Edgecombe | Withdrawn | Generation Interconnection | Dominion | 250 | 250 | 150 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-439/AG1-439_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-439/AG1-439_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-008 | TC1 | PHASE 3 | Tunis-Mapleton 115 kV |  | Bells Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 126 | 126 | 83.7 |  | Capacity | Solar | 5/1/2020 | 12/15/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-008/AG1-008_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-008/AG1-008_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-082 | TC1 | PHASE 3 | Ahoskie 34.5 kV |  | NC1 Ahoskie Central, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar,Storage,Hybrid | 7/31/2020 | 12/31/2021 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-082/AG1-082_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-082/AG1-082_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-083 | TC1 | PHASE 2 | Ahoskie 34.5 kV |  | NC-4 Ahoskie North, LLC | NC | Hertford | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar,Storage,Hybrid | 7/31/2020 | 12/31/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-083/AG1-083_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-083/AG1-083_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-046 | TC1 | PHASE 3 | Tunis-Mapleton 115 kV |  | Murphy Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 126 | 126 | 83.7 |  | Capacity | Solar | 12/19/2019 | 6/1/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-046/AF2-046_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-046/AF2-046_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-238 | TC2 | PHASE 1 | Earleys 230 kV |  | Aulander Holloman Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 99.9 | 0 | 0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-091 | TC2 | PHASE 1 | Ahoskie 34.5kV |  | Colice Hall Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 17 | 0 | 0 |  | Energy | Storage | 7/30/2021 | 11/15/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-120 | TC2 | PHASE 1 | Everetts 34.5 kV |  | Wildcat Road Solar, LLC | NC | Martin | Active | Generation Interconnection | Dominion | 21 | 21 | 14 |  | Capacity | Solar | 1/29/2021 | 12/15/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-551 | TC1 | PHASE 3 | Parmele 12.5 kV |  | Parnell Solar, LLC | NC | Martin | Active | Generation Interconnection | Dominion | 19.99 | 19.99 | 13.1 |  | Capacity | Solar | 9/30/2020 | 10/15/2023 | [5 empty] | 2/7/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-551/AG1-551_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-551/AG1-551_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-552 | TC1 | PHASE 3 | Carolina 13.2 kV |  | Ray Solar, LLC | NC | Northhampton | Active | Generation Interconnection | Dominion | 18 | 18 | 12.2 |  | Capacity | Solar | 9/30/2020 | 10/15/2023 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-552/AG1-552_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-552/AG1-552_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-237 | TC2 | PHASE 1 | Thelma 230kV |  | Oak Solar LLC | NC | Northhampton | Active | Generation Interconnection | Dominion | 323 | 0 | 0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-106 | TC1 | PHASE 3 | Thelma 230 kV |  | Oak Solar LLC | NC | Northhampton | Active | Generation Interconnection | Dominion | 323 | 23 | 16 |  | Capacity | Solar | 8/28/2020 | 6/1/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-106/AG1-106_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-106/AG1-106_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-434 | TC2 | PHASE 1 | Carolina- Earleys 115kV | ACE Development Company, LLC | ACE | NC | Northhampton | Active | Generation Interconnection | Dominion | 75 | 75 | 45 |  | Capacity | Solar | 9/10/2021 | 9/1/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-152 | TC1 | PHASE 1 | Swamp 230 kV |  | Aurora | NC | Pasquotank | Withdrawn | Generation Interconnection | Dominion | 50 | 50 | 30 |  | Capacity | Solar | 9/19/2019 | 10/2/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-152/AF1-152_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-152/AF1-152_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-147 | TC1 | PHASE 1 | Swamp 230 kV |  | Aurora | NC | Perquimans | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 3/13/2019 | 12/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-147/AE2-147_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-147/AE2-147_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-080 | TC1 | PHASE 3 | Chinquapin-Everetts 230 kV |  | Pitt Solar, LLC | NC | Pitt | Active | Generation Interconnection | Dominion | 150 | 70 | 48.5 |  | Capacity | Solar | 1/31/2020 | 6/30/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-080/AF2-080_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-080/AF2-080_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-522 | TC2 | PHASE 1 | Five Forks 115 kV |  | Macon PV I LLC | NC | Warren | Active | Generation Interconnection | Dominion | 80 | 80 | 48 |  | Capacity | Solar | 3/31/2021 | 7/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-121 | TC2 | PHASE 1 | Mackeys 230 kV |  | Albemarle Beach Solar, LLC | NC | Washington | Active | Generation Interconnection | Dominion | 140 | 0 | 0 |  | Energy | Storage | 1/29/2021 | 12/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-047 | TC1 | PHASE 1 | Creswell-Riders Creek 115 kV |  | Creswell HWY 64 Solar, LLC | NC | Washington | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 99.8 |  | Capacity | Solar | 12/19/2019 | 6/1/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-047/AF2-047_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-035 | TC2 | PHASE 1 | Plymouth 34.5 kV |  | Park Solar, LLC | NC | Washington | Active | Generation Interconnection | Dominion | 20 | 20 | 13.5 |  | Capacity | Solar | 6/14/2021 | 9/15/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-040 | TC2 | PHASE 1 | Mackeys - Creswell 115 kV |  | ACE | NC | Washington | Active | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 6/23/2021 | 7/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-025 | TC1 | FINAL AGREEMENT | Ontario 69 kV | Missouri Avenue Battery Storage Project | Calpine | NJ | Atlantic | EP | Generation Interconnection | AEC | 20 | 20 | 8 |  | Capacity | Storage | 11/15/2019 | 6/1/2021 | 4/30/2028 |  | 4/30/2028 | 2/1/2028 | 2/15/2028 | 4/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-025/AF2-025_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-025/AF2-025_imp_PHASE_2.htm | Posted |  | Not Required | https://www.pjm.com//pjmfiles/pub/planning/project-queues/gia/af2_025_gia.pdf | Posted |  | Not Started
AF2-016 | TC1 | PHASE 1 | Lewis 138 kV |  | Garden Reserve Energy, LLC | NJ | Atlantic | Withdrawn | Generation Interconnection | AEC | 240 | 240 | 96 |  | Capacity | Storage | 10/1/2019 | 5/31/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-016/AF2-016_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-703 | TC2 | PHASE 1 | Bergen 230kV |  | Parkway Generation Operating LLC | NJ | Bergen | Active | Generation Interconnection | PSEG | 670.61 | 35.61 | 51.254 |  | Capacity | Natural Gas |  | 5/21/2027 | [5 empty] | 5/14/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-265 | TC2 | PHASE 1 | Winslow - Monroe 69kV | Winslow Landfill Solar Farm | Winslow LF Solar Farm, LLC | NJ | Camden | Active | Generation Interconnection | AEC | 29.4 | 29.4 | 12.35 |  | Capacity | Solar | 9/10/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-260 | TC2 | PHASE 1 | New Freedom - Monroe 230 kV |  | Haddy Energy Storage LLC | NJ | Camden | Active | Generation Interconnection | AEC | 300 | 300 | 300 |  | Capacity | Storage | 9/10/2021 | 6/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-238 | TC1 | PHASE 3 | Sherman Ave - West Vineland 69 kV |  | Garden Reserve Energy, LLC | NJ | Cumberland | Active | Generation Interconnection | AEC | 50 | 50 | 20 |  | Capacity | Storage | 9/28/2019 | 5/31/2023 | [5 empty] | 1/30/2025 |  | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-238/AF1-238_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-238/AF1-238_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-297 | TC2 | PHASE 1 | Cumberland 230 kV |  | Calpine | NJ | Cumberland | Active | Generation Interconnection | AEC | 19 | 19 | 11.4 |  | Capacity | Solar | 3/23/2021 | 6/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-627 | TC2 | PHASE 1 | Woodstown-High Street 69 kV |  | South Harrison Solar, LLC | NJ | Gloucester | Active | Generation Interconnection | AEC | 40 | 40 | 24 |  | Capacity | Solar | 3/31/2021 | 6/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-450 | TC2 | PHASE 1 | Bridgeport 230 kV |  | Logan Energy Storage, L.L.C. | NJ | Gloucester | Active | Generation Interconnection | AEC | 219 | 219 | 115.3 |  | Capacity | Storage | 3/30/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-274 | TC2 | PHASE 1 | Butler 69 kV |  | Vineland Newfield Solar Farm, LLC | NJ | Gloucester | Active | Generation Interconnection | AEC | 16.7 | 16.7 | 7 |  | Capacity | Solar | 9/9/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-701 | TC2 | PHASE 1 | Valero 69 kV |  | Paulsboro Refining Company LLC | NJ | Gloucester | Active | Generation Interconnection | AEC | 61 | 0 | 20 |  | Capacity | Natural Gas |  | 4/1/2025 | [5 empty] | 5/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-460 | TC2 | PHASE 1 | East Flemington-Lebanon 34.5 kV II |  | Ftera Energy APD Flemington, LLC | NJ | Hunterdon | Active | Generation Interconnection | JCPL | 20 | 0 | 2 |  | Capacity | Storage | 3/30/2021 | 8/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-459 | TC2 | PHASE 1 | Allenwood-Larrabee 34.5 kV II |  | VESI | NJ | Monmouth | Active | Generation Interconnection | JCPL | 7 | 0 | 0.7 |  | Capacity | Storage | 3/30/2021 | 3/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-258 | TC2 | PHASE 1 | Belford - Keansburg 34.5 kV | Port Belford Solar Farm | Port Belford Solar Farm, LLC | NJ | Monmouth | Active | Generation Interconnection | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Solar | 9/10/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-557 | TC2 | APPLICATION REVIEW | Larrabee Collector Station 230 kV | Larrabee 230 kV IV | Atlantic Shores Offshore Wind Project 2, LLC | NJ | Monmouth | Withdrawn | Generation Interconnection | JCPL | 1300 | 1300 | 228.8 |  | Capacity | Offshore Wind | 9/10/2021 | 10/31/2029 | [5 empty] | 2/14/2025 | 2/14/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-531 | TC2 | APPLICATION REVIEW | Greystone - West Denville 34.5 kV |  | West Denville LLC | NJ | Morris | Withdrawn | Generation Interconnection | JCPL | 20 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 7/31/2022 | [5 empty] | 1/31/2025 | 1/31/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-016 | TC2 | PHASE 1 | Oyster Creek-Whitings 34.5 kV |  | Lacey Holding / Ocean View Acres | NJ | Ocean | Active | Generation Interconnection | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Solar | 10/20/2020 | 12/17/2021 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-021 | TC1 | PHASE 1 | Cedar 69 kV |  | Calpine | NJ | Ocean | Withdrawn | Generation Interconnection | AEC | 20 | 20 | 8 |  | Capacity | Storage | 11/15/2019 | 6/1/2021 | [5 empty] | 7/2/2024 | 5/31/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-021/AF2-021_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-334 | TC2 | PHASE 1 | Lakehurst - Whitings 34.5 kV | Heritage Solar Farm | Heritage Solar Farm, LLC | NJ | Ocean | Active | Generation Interconnection | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Solar | 9/10/2021 | 9/9/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-054 | TC2 | PHASE 1 | Upton-Whitings 34.5 kV |  | Pasadena Pemberton Solar Farm, LLC | NJ | Ocean | Active | Generation Interconnection | JCPL | 8.25 | 8.25 | 3.465 |  | Capacity | Solar | 7/9/2021 | 7/8/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-641 | TC2 | PHASE 1 | Churchtown - Upper Pittsgrove 138kV |  | Goldenrod Energy Center, LLC | NJ | Salem | Active | Generation Interconnection | AEC | 65 | 15 | 15 |  | Capacity | Solar | 9/14/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-710 | TC2 | PHASE 1 | Salem 500kV |  | PSEG Nuclear LLC | NJ | Salem | Active | Generation Interconnection | PSEG | 2650.8 | 256.8 | 228.2 |  | Capacity | Nuclear |  | 12/1/2027 | [5 empty] | 5/14/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-035 | TC2 | APPLICATION REVIEW | Salem - Woodstown 69 kV |  | ACE | NJ | Salem | Withdrawn | Generation Interconnection | AEC | 71 | 33 | 22 |  | Capacity | Solar,Storage,Hybrid | 11/11/2020 | 12/31/2021 | [5 empty] | 2/11/2025 | 2/11/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-616 | TC2 | PHASE 1 | Churchtown - Upper Pittsgrove 138 kV |  | Goldenrod Energy Center, LLC | NJ | Salem | Active | Generation Interconnection | AEC | 50 | 50 | 32.35 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-451 | TC2 | PHASE 1 | Chambers 230 kV |  | Carneys Point Energy Storage, L.L.C. | NJ | Salem | Active | Generation Interconnection | AEC | 240 | 240 | 123 |  | Capacity | Storage | 3/30/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-458 | TC2 | PHASE 1 | Kittatinny-Newton 34.5 kV II |  | VESI | NJ | Sussex | Active | Generation Interconnection | JCPL | 19.8 | 0 | 1.89 |  | Capacity | Storage | 3/30/2021 | 5/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-722 | TC2 | PHASE 1 | Linden 230kV |  | Parkway Generation Operating LLC | NJ | Union | Active | Generation Interconnection | PSEG | 806.4 | 130.4 | 158.1 |  | Capacity | Natural Gas |  | 5/31/2030 | [5 empty] | 5/14/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-715 | TC2 | PHASE 1 | Linden 230kV |  | Parkway Generation Operating LLC | NJ | Union | Active | Generation Interconnection | PSEG | 803.17 | 127.17 | 149.369 |  | Capacity | Natural Gas |  | 5/31/2029 | [5 empty] | 5/14/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-257 | TC2 | PHASE 1 | Broadway - Washington 34.5 kV | Kober Solar Farm | CEP NJ Kober Land LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Solar | 9/9/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-290 | TC2 | PHASE 1 | BASF - Washburn Solar 34.5 kV | Changewater Solar Farm | Changewater Solar Farm LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Solar | 9/9/2021 | 9/9/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-625 | TC2 | PHASE 1 | Pequest River-Furnace Brook Tap 34.5 kV II |  | Chamberlain | NJ | Warren | Active | Generation Interconnection | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Solar | 3/31/2021 | 4/30/2021 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-626 | TC2 | PHASE 1 | Pequest River-Furnace Brook Tap 34.5 kV III |  | Chamberlain | NJ | Warren | Active | Generation Interconnection | JCPL | 12.5 | 12.5 | 5.25 |  | Capacity | Solar | 3/31/2021 | 4/30/2021 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-599 | TC2 | APPLICATION REVIEW | Furnace Brook-Warren 34.5 kV |  | Oxford Textile Solar Farm, LLC | NJ | Warren | Withdrawn | Generation Interconnection | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Solar | 3/31/2021 | 4/30/2021 | [5 empty] | 2/18/2025 | 2/18/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-600 | TC2 | PHASE 1 | American Can-BASF 34.5 kV |  | East Asbury Anderson Solar Farm, LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Solar | 3/31/2021 | 4/30/2021 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-532 | TC2 | PHASE 1 | Pohatcong-Newburgh Tap 34.5 kV |  | V20 Mansfield LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 20 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 8/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-533 | TC2 | PHASE 1 | Newburgh-Pohatcong 34.5 kV |  | AF1327 LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 20 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 8/31/2021 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-534 | TC2 | PHASE 1 | Hackettstown-Pohatcong R722-7 34.5 kV |  | Mansfield 3 LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 20 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 8/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-535 | TC2 | PHASE 1 | Hackettstown-Pohatcong J738-1 34.5 kV II |  | Mansfield 3 LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 40 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 8/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-228 | TC2 | PHASE 1 | Washington-Furnace Brook Tap 34.5kV |  | Reeder Farm Solar Farm, LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 11.2 | 11.2 | 4.704 |  | Capacity | Solar | 3/12/2021 | 3/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-189 | TC2 | PHASE 1 | Washington-Furnace Brook Tap 34.5 kV |  | Harmony Sand Solar Farm, LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Solar | 2/27/2021 | 2/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-758 | TC2 | RRI APPLICATION REVIEW |  |  | Cardinal Energy Storage East, LLC | OH | Adams | Withdrawn | Generation Interconnection | AEP | 500 | 500 | 500 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-069 | TC2 | PHASE 1 | Jerome – Mohicanville 69 kV |  | JR ME LLC | OH | Ashland | Active | Generation Interconnection | ATSI | 17 | 17 | 10.2 |  | Capacity | Solar | 7/28/2021 | 11/30/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-070 | TC2 | PHASE 1 | Jerome – Mohicanville 69 kV |  | JR ME LLC | OH | Ashland | Active | Generation Interconnection | ATSI | 34 | 17 | 10.2 |  | Capacity | Solar | 7/28/2021 | 11/30/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-530 | TC2 | APPLICATION REVIEW | Fairfield – Reily 69 kV |  | Riverlake Energy, LLC | OH | Butler | Withdrawn | Generation Interconnection | DEOK | 28 | 28 | 16.8 |  | Capacity | Solar | 9/10/2021 | 3/1/2025 | [5 empty] | 2/4/2025 | 2/4/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-282 | TC2 | APPLICATION REVIEW | Kuranga Power Generator |  | The Associates Incubator | OH | Butler | Withdrawn | Generation Interconnection | DEOK | 10 | 10 | 3.102 |  | Capacity | Solar,Wind,Hybrid | 3/22/2021 | 2/10/2022 | [5 empty] | 2/12/2025 | 2/12/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-680 | TC2 | PHASE 1 | Sammis - South Canton 345 kV |  | Chestnut Run Energy LLC | OH | Carroll | Active | Generation Interconnection | AEP | 1300 | 1300 | 1300 |  | Capacity | Natural Gas |  | 5/1/2030 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-526 | TC2 | PHASE 1 | Knox - Washington CEC 138 kV | Echelon Solar | Echelon Solar LLC | OH | Carroll | Withdrawn | Generation Interconnection | ATSI | 80 | 80 | 42 |  | Capacity | Solar,Storage,Hybrid | 9/11/2021 | 10/31/2025 | [5 empty] | 6/5/2025 | 6/5/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-216 | TC2 | PHASE 1 | East Sidney-Quincy 138 kV |  | Clearview Solar I, LLC | OH | Champaign | Active | Generation Interconnection | Dayton | 144 | 0 | 25.92 |  | Capacity | Solar | 3/9/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-063 | TC2 | PHASE 1 | North Hampton 69 kV |  | Brookfield Twin Creeks Solar LLC | OH | Clark | Active | Generation Interconnection | ATSI | 54 | 54 | 34.5 |  | Capacity | Solar | 12/16/2020 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-385 | TC2 | PHASE 1 | North Hampton 69 kV |  | Brookfield Twin Creeks Solar LLC | OH | Clark | Active | Generation Interconnection | ATSI | 128 | 54 | 36.5 |  | Capacity | Solar | 3/29/2021 | 7/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-378 | TC2 | PHASE 1 | North Hampton – Medway 69 kV |  | Brookfield Twin Creeks Solar LLC | OH | Clark | Active | Generation Interconnection | ATSI | 74 | 20 | 13.5 |  | Capacity | Solar | 3/29/2021 | 7/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-319 | TC2 | PHASE 1 | East Springfield-London 138 kV II | Sloopy Storage | Invenergy | OH | Clark | Active | Generation Interconnection | ATSI | 54 | 54 | 54 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-699 | TC2 | PHASE 1 | Wellsville 345 kV |  | South Field Energy LLC | OH | Columbiana | Active | Generation Interconnection | ATSI | 1210 | 58 | 69 |  | Capacity | Natural Gas |  | 3/3/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-564 | TC2 | PHASE 1 | Sulphur Springs 138 kV |  | Heartland Solar LLC | OH | Crawford | Active | Generation Interconnection | AEP | 49.99 | 49.99 | 32.9 |  | Capacity | Solar | 3/31/2021 | 7/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-149 | TC2 | PHASE 1 | Galion-South Berwick 345 kV |  | Wombat Solar LLC | OH | Crawford | Active | Generation Interconnection | AEP | 486 | 400 | 52 |  | Capacity | Solar | 2/22/2021 | 12/2/2024 | [5 empty] | 5/30/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-748 | TC2 | RRI APPLICATION REVIEW |  |  | NAPS - Solon | OH | Cuyahoga | Withdrawn | Generation Interconnection | ATSI | 3.2 | 3.2 | 3.2 |  | Capacity | Biomass |  | 6/15/2025 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-735 | TC2 | PHASE 1 | Richland 138 kV |  | Richland-Stryker Generation LLC,Richland-Stryker Generation, LLC | OH | Defiance | Active | Generation Interconnection | ATSI | 447 | 19 | 55 |  | Capacity | Natural Gas |  | 5/1/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-770 | TC2 | RRI APPLICATION REVIEW |  |  | Mink Solar LLC | OH | Defiance | Withdrawn | Generation Interconnection | AEP | 184 | 184 | 12.88 |  | Capacity | Solar |  | 12/31/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AF2-209 | TC1 | DP2 | South Hicksville-Sowers 138 kV |  | Mink Solar LLC | OH | Defiance | Withdrawn | Generation Interconnection | AEP | 140 | 140 | 19.6 |  | Capacity | Solar | 3/25/2020 | 6/2/2023 | [5 empty] | 2/3/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-209/AF2-209_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-209/AF2-209_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-425 | TC1 | PHASE 1 | Groton 138 kV |  | Wheatsborough Solar, LLC | OH | Erie | Withdrawn | Generation Interconnection | ATSI | 125 | 0 | 20 |  | Capacity | Storage | 9/30/2020 | 10/31/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-425/AG1-425_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-498 | TC2 | PHASE 1 | Obetz 138 kV |  | Invenergy | OH | Franklin | Active | Generation Interconnection | AEP | 50 | 50 | 50 |  | Capacity | Storage | 3/31/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-318 | TC2 | PHASE 1 | Cole 345 kV |  | Invenergy | OH | Franklin | Active | Generation Interconnection | AEP | 60 | 60 | 60 |  | Capacity | Storage | 9/11/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-053 | TC2 | PHASE 1 | Fulton 138 kV |  | Orchid Acres Solar Project, LLC | OH | Fulton | Active | Generation Interconnection | ATSI | 300 | 300 | 180 |  | Capacity | Solar | 12/2/2020 | 9/25/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-054 | TC2 | PHASE 1 | Fulton 138 kV |  | Orchid Acres Solar Project, LLC | OH | Fulton | Active | Generation Interconnection | ATSI | 400 | 100 | 100 |  | Capacity | Storage | 12/2/2020 | 9/25/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-375 | TC2 | PHASE 1 | Fostoria Central 345 kV |  | Foster Energy Storage LLC | OH | Hancock | Active | Generation Interconnection | AEP | 500 | 500 | 500 |  | Capacity | Storage | 3/29/2021 | 11/15/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-327 | TC2 | PHASE 1 | Hardin Switch 345 kV |  | Hardin Solar Energy III LLC | OH | Hardin | Active | Generation Interconnection | AEP | 250 | 0 | 8.44 |  | Capacity | Solar | 9/10/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-539 | TC2 | PHASE 1 | South Kenton 138 kV |  | Riverlake Energy, LLC | OH | Hardin | Active | Generation Interconnection | AEP | 129.4 | 129.4 | 25.88 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-767 | TC2 | RRI APPLICATION REVIEW |  |  | RWE LLC | OH | Hardin | Withdrawn | Generation Interconnection | AEP | 140 | 140 | 140 |  | Capacity | Storage |  | 8/31/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-724 | TC2 | RRI APPLICATION REVIEW | Nottingham 138 kV |  | Pogona Power LLC | OH | Harrison | Withdrawn | Generation Interconnection | AEP | 650 | 650 | 650 |  | Capacity | Natural Gas |  | 5/1/2030 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-580 | TC2 | PHASE 1 | Nottingham 138 kV |  | Energy Pastures Solar Project, LLC | OH | Harrison | Active | Generation Interconnection | AEP | 400 | 200 | 134 |  | Capacity | Solar | 9/10/2021 | 5/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-082 | TC2 | PHASE 1 | Nottingham 138 kV |  | Energy Pastures Solar Project, LLC | OH | Harrison | Active | Generation Interconnection | AEP | 200 | 200 | 133.4 |  | Capacity | Solar | 1/22/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-336 | TC2 | PHASE 1 | Midway 138 kV |  | Reserve Energy Exploration Company | OH | Henry | Active | Generation Interconnection | ATSI | 80 | 80 | 48 |  | Capacity | Solar | 3/25/2021 | 11/30/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-337 | TC2 | PHASE 1 | Midway 138 kV II |  | Reserve Energy Exploration Company | OH | Henry | Active | Generation Interconnection | ATSI | 100 | 20 | 12 |  | Capacity | Solar | 3/25/2021 | 11/30/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-319 | TC1 | PHASE 1 | Napoleon Muni 138 kV |  | CG Henry County LLC | OH | Henry | Withdrawn | Generation Interconnection | AMPT | 105 | 65 | 39 |  | Capacity | Solar | 9/30/2020 | 11/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-319/AG1-319_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-319/AG1-319_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-456 | TC1 | PHASE 1 | Wildcat 138 kV |  | Willowbrook Solar I, LLC | OH | Highland | Withdrawn | Generation Interconnection | AEP | 180 | 30 | 30 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-456/AG1-456_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-537 | TC2 | PHASE 1 | Pierce - Kyger Creek 345 kV |  | Riverlake Energy, LLC | OH | Highland | Active | Generation Interconnection | OVEC | 178.5 | 178.5 | 17.85 |  | Capacity | Solar | 9/11/2021 | 3/1/2025 | [5 empty] | 5/13/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-766 | TC2 | RRI APPLICATION REVIEW |  |  | NextEra Energy Resources Interconnection Holdings, LLC | OH | Highland | Withdrawn | Generation Interconnection | AEP | 205 | 205 | 205 |  | Capacity | Storage |  | 5/31/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-094 | TC2 | PHASE 1 | Wells - Shinrock 69 kV I | Norwalk Solar I | Norwalk Solar, LLC | OH | Huron | Active | Generation Interconnection | ATSI | 49.9 | 49.9 | 29.94 |  | Capacity | Solar,Storage,Hybrid | 7/30/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-109 | TC2 | PHASE 1 | Fitchville-New London 69 kV |  | Rosemary Solar, LLC | OH | Huron | Active | Generation Interconnection | ATSI | 40 | 40 | 28.1 |  | Capacity | Solar | 1/29/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-548 | TC2 | PHASE 1 | Corwin - Elk 138 kV |  | Hamden Energy LLC | OH | Jackson | Active | Generation Interconnection | AEP | 90 | 90 | 54 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-055 | TC2 | PHASE 1 | Kyger Creek - Don Marquis 345 kV |  | Furnace Solar, LLC | OH | Jackson | Active | Generation Interconnection | OVEC | 220 | 220 | 154 |  | Capacity | Solar | 7/14/2021 | 11/15/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-665 | TC2 | PHASE 1 | Corwin - Elk 138 kV |  | Hamden Energy LLC | OH | Jackson | Active | Generation Interconnection | AEP | 180 | 90 | 54 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-059 | TC2 | PHASE 1 | Sharp Road 69 kV |  | Frasier Solar, LLC | OH | Knox | Active | Generation Interconnection | AEP | 120 | 40 | 24 |  | Capacity | Solar | 7/16/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-686 | TC2 | PHASE 1 | Hanging Rock 765 kV |  | Hanging Rock Power Company LLC | OH | Lawrence | Active | Generation Interconnection | AEP | 1364 | 24 | 21 |  | Capacity | Natural Gas |  | 6/1/2027 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-325 | TC2 | PHASE 1 | Kirk 138 kV |  | Invenergy | OH | Licking | Active | Generation Interconnection | AEP | 50 | 50 | 50 |  | Capacity | Storage | 9/9/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-328 | TC2 | PHASE 1 | Blue Jacket - Kirby 138 kV |  | Fountain Point Solar Energy LLC | OH | Logan | Active | Generation Interconnection | Dayton | 275.55 | 0 | 21.3 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-320 | TC2 | PHASE 1 | Blue Jacket - Kirby 138 kV |  | Invenergy | OH | Logan | Active | Generation Interconnection | Dayton | 275.55 | 69 | 69 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-323 | TC1 | PHASE 3 | Blue Jacket 138 kV |  | Hodson GreenDefine Blue Jacket LLC | OH | Logan | Active | Generation Interconnection | Dayton | 40 | 40 | 40 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 9/1/2023 | [5 empty] | 3/3/2025 |  |  |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-323/AG1-323_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-270 | TC1 | PHASE 2 | Blue Jacket-Kirby 138 kV |  | Fountain Point Solar Energy LLC | OH | Logan | Withdrawn | Generation Interconnection | Dayton | 279.5 | 50 | 50 |  | Capacity | Solar | 9/30/2019 | 12/31/2022 | [5 empty] | 12/20/2024 | 6/21/2024 | Customer Milestone Not Met |  | Not Applicable |  | Not Specified |  | Not Started |  | Not Started |  | Not Started
AG1-199 | TC1 | PHASE 1 | Allen Junction 345 kV |  | Occasio Power Management LLC | OH | Lucas | Withdrawn | Generation Interconnection | ATSI | 300 | 300 | 300 |  | Capacity | Storage | 9/18/2020 | 6/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-199/AG1-199_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-515 | TC2 | PHASE 1 | Midway 345 kV III |  | STARLING SOLAR PROJECT, LLC | OH | Lucas | Active | Generation Interconnection | ATSI | 100 | 100 | 60 |  | Capacity | Solar | 3/31/2021 | 10/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-690 | TC2 | PHASE 1 | Bay Shore - Lallendorf 345 kV |  | CPV LLC | OH | Lucas | Active | Generation Interconnection | ATSI | 1475 | 1475 | 1440 |  | Capacity | Natural Gas |  | 3/1/2031 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-104 | TC2 | PHASE 1 | Marysville-Flatlick 765 kV |  | Oak Run Solar Project, LLC | OH | Madison | Active | Generation Interconnection | AEP | 400 | 400 | 253.7 |  | Capacity | Solar | 1/29/2021 | 9/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-106 | TC2 | PHASE 1 | Marysville-Flatlick 765 kV |  | Oak Run Solar Project, LLC | OH | Madison | Active | Generation Interconnection | AEP | 400 | 0 | 150 |  | Capacity | Storage | 1/29/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-107 | TC2 | PHASE 1 | Marysville-Flatlick 765 kV |  | Oak Run Solar Project, LLC | OH | Madison | Active | Generation Interconnection | AEP | 400 | 0 | 150 |  | Capacity | Storage | 1/29/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-119 | TC2 | PHASE 1 | Galion-Roberts South 138 kV II |  | Marion County Solar Project II, LLC | OH | Marion | Active | Generation Interconnection | ATSI | 80 | 80 | 53.6 |  | Capacity | Solar | 1/29/2021 | 9/1/2024 | [5 empty] | 5/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-542 | TC2 | PHASE 1 | Crissinger-Delaware Business Park 138kV | Green Camp Solar II | Riverlake Energy, LLC | OH | Marion | Active | Generation Interconnection | ATSI | 110 | 110 | 22 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-572 | TC2 | PHASE 1 | South Morral-Uncapher Switch 69 kV |  | Swamp Fox Solar, LLC | OH | Marion | Active | Generation Interconnection | AEP | 30 | 30 | 19.3 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-573 | TC2 | PHASE 1 | South Morral-Uncapher Switch 69 kV |  | Swamp Fox Solar, LLC | OH | Marion | Active | Generation Interconnection | AEP | 49.99 | 19.99 | 12.9 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-595 | TC2 | PHASE 1 | LaRue - North Waldo 138 kV |  | Riverlake Energy, LLC | OH | Marion | Active | Generation Interconnection | AEP | 65 | 65 | 6.5 |  | Capacity | Solar | 3/31/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-075 | TC2 | PHASE 1 | North Waldo - Wild Creek 138 kV |  | Chestnut LLC | OH | Marion | Active | Generation Interconnection | AEP | 68 | 8 | 24.7 |  | Capacity | Solar | 7/29/2021 | 12/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-589 | TC2 | PHASE 1 | Ravenswood - Hemlock 69 kV |  | Riverlake Energy, LLC | OH | Meigs | Active | Generation Interconnection | AEP | 20 | 20 | 2 |  | Capacity | Solar | 3/31/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-321 | TC2 | PHASE 1 | Eldean 138 kV |  | Invenergy | OH | Miami | Active | Generation Interconnection | Dayton | 232 | 54 | 54 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-704 | TC2 | PHASE 1 | Hannibal 138 kV |  | Long Ridge Energy Generation LLC | OH | Monroe | Active | Generation Interconnection | AEP | 509 | 24 | 20 |  | Capacity | Natural Gas |  | 6/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-355 | TC2 | APPLICATION REVIEW | North Muskingum River - Philo 138 kV |  | IRGAH Renewables Development LLC | OH | Morgan | Withdrawn | Generation Interconnection | AEP | 125 | 125 | 82.4 |  | Capacity | Solar,Storage,Hybrid | 3/26/2021 | 6/1/2024 | [5 empty] | 3/31/2025 | 3/28/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-057 | TC2 | PHASE 1 | Cardington-Liberty 69 kV II |  | Crossroads LLC | OH | Morrow | Active | Generation Interconnection | ATSI | 74 | 10 | 6 |  | Capacity | Solar | 12/7/2020 | 11/30/2022 | [5 empty] | 5/5/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-765 | TC2 | RRI APPLICATION REVIEW |  |  | NextEra Energy Resources Interconnection Holdings, LLC | OH | Morrow | Withdrawn | Generation Interconnection | ATSI | 205 | 205 | 205 |  | Capacity | Storage |  | 5/31/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-060 | TC2 | PHASE 1 | Cardington-Liberty 69 kV III | Crossroads Solar I | Crossroads LLC | OH | Morrow | Active | Generation Interconnection | ATSI | 94 | 20 | 12 |  | Capacity | Solar | 7/20/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-282 | TC2 | PHASE 1 | Galion - Ohio Central 345 kV |  | Woodbury Solar, LLC | OH | Morrow | Active | Generation Interconnection | AEP | 150 | 150 | 90 |  | Capacity | Solar | 9/9/2021 | 5/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-661 | TC2 | PHASE 1 | Cannelville 12.47 kV |  | Tallgrass Muskingum Community Power, LLC | OH | Muskingum | Active | Generation Interconnection | AEP | 10.07 | 10.07 | 9.06 |  | Capacity | Biomass | 9/29/2021 | 7/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-754 | TC2 | RRI APPLICATION REVIEW |  |  | Cardinal Energy Storage East, LLC | OH | Muskingum | Withdrawn | Generation Interconnection | AEP | 500 | 500 | 500 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG2-406 | TC2 | PHASE 1 | Payne 69 kV |  | Timber Road Solar Park LLC | OH | Paulding | Active | Generation Interconnection | AEP | 49.9 | 0 | 10.98 |  | Capacity | Solar | 3/30/2021 | 10/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-376 | TC1 | PHASE 3 | Timber Switch 138 kV |  | Paulding Wind Farm II LLC | OH | Paulding | Active | Generation Interconnection | AEP | 50 | 50 | 20 |  | Capacity | Storage | 3/31/2020 | 10/31/2023 | [5 empty] | 3/12/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG2-444 | TC2 | PHASE 1 | Bixby - Biers Run 345 kV |  | Brook Trout Solar, LLC | OH | Pickaway | Active | Generation Interconnection | AEP | 163 | 163 | 122.5 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-125 | TC2 | PHASE 1 | Camden-Crystal 69 kV |  | Alamo Solar I, LLC | OH | Preble | Active | Generation Interconnection | Dayton | 69.9 | 0 | 15.44 |  | Capacity | Solar | 1/29/2021 | 12/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-405 | TC2 | PHASE 1 | Continental 69 kV |  | Blue Harvest Solar Park LLC | OH | Putnam | Active | Generation Interconnection | AEP | 49.9 | 0 | 10.98 |  | Capacity | Solar | 3/30/2021 | 10/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-669 | TC2 | PHASE 1 | Circleville-Biers Run 138 kV |  | Innergex | OH | Ross | Active | Generation Interconnection | AEP | 50 | 50 | 30 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-289 | TC2 | PHASE 1 | Amsden – Fremont Center 69 kV |  | Chinchilla Solar LLC | OH | Seneca | Active | Generation Interconnection | AEP | 66.6 | 66.6 | 0 |  | Energy | Storage | 3/23/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-290 | TC2 | PHASE 1 | Amsden – Fremont Center 69 kV |  | Chinchilla Solar LLC | OH | Seneca | Active | Generation Interconnection | AEP | 105 | 38.4 | 0 |  | Energy | Storage | 3/22/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-263 | TC1 | PHASE 1 | Shelby 138 kV |  | AEUG | OH | Shelby | Withdrawn | Generation Interconnection | Dayton | 98 | 98 | 58.8 |  | Capacity | Solar | 3/27/2020 | 7/1/2022 | [5 empty] | 8/1/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-263/AF2-263_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-752 | TC2 | RRI APPLICATION REVIEW |  |  | Cardinal Energy Storage East, LLC | OH | Stark | Withdrawn | Generation Interconnection | AEP | 400 | 400 | 400 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-706 | TC2 | PHASE 1 | Lordstown 345 kV |  | Clean Energy Future - Lordstown, LLC | OH | Trumbull | Active | Generation Interconnection | ATSI | 970.453 | 30.453 | 23.823 |  | Capacity | Natural Gas |  | 11/22/2027 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-757 | TC2 | RRI APPLICATION REVIEW |  |  | Cardinal Energy Storage East, LLC | OH | Union | Withdrawn | Generation Interconnection | AEP | 500 | 500 | 500 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-569 | TC2 | PHASE 1 | Tangy - National 138 kV |  | Glacier Ridge Solar, LLC | OH | Union | Active | Generation Interconnection | ATSI | 42 | 42 | 31.3 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE1-092 | TC1 | PHASE 3 | Blue Jacket-Kirby 138 kV |  | Fountain Point Solar Energy LLC | OH | Union | Active | Generation Interconnection | Dayton | 206.55 | 206.6 | 96.4 |  | Capacity | Solar | 8/31/2018 | 12/31/2021 | [5 empty] | 3/26/2025 |  |  |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-092/AE1-092_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-410 | TC1 | PHASE 3 | Maddox Creek-RP Mone 345 kV |  | Butterfly Meadows Solar Project, LLC | OH | Van Wert | Active | Generation Interconnection | AEP | 300 | 300 | 180 |  | Capacity | Solar | 9/30/2020 | 9/25/2024 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-410/AG1-410_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-410/AG1-410_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-411 | TC1 | PHASE 3 | Maddox Creek-RP Mone 345 kV |  | Butterfly Meadows Solar Project, LLC | OH | Van Wert | Active | Generation Interconnection | AEP | 100 | 100 | 100 |  | Capacity | Storage | 9/30/2020 | 9/25/2024 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-411/AG1-411_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-411/AG1-411_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-538 | TC2 | PHASE 1 | East Lima - Haviland 138 kV |  | Riverlake Energy, LLC | OH | Van Wert | Active | Generation Interconnection | AEP | 100 | 100 | 20 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-719 | TC2 | PHASE 1 | Beverly 345 kV |  | Washington Power Generation LLC | OH | Washington | Active | Generation Interconnection | AEP | 694 | 24 | 21 |  | Capacity | Natural Gas |  | 6/1/2027 | [5 empty] | 5/13/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-577 | TC2 | PHASE 1 | Clutch 69 kV |  | Dragonfly Fields Solar Project, LLC | OH | Wayne | Active | Generation Interconnection | AEP | 70 | 70 | 42 |  | Capacity | Solar | 9/10/2021 | 10/15/2028 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-578 | TC2 | PHASE 1 | Clutch 69 kV |  | Dragonfly Fields Solar Project, LLC | OH | Wayne | Active | Generation Interconnection | AEP | 98 | 28 | 28 |  | Capacity | Storage | 9/10/2021 | 10/15/2028 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-764 | TC2 | RRI APPLICATION REVIEW |  |  | Williams County Solar, LLC | OH | Williams | Withdrawn | Generation Interconnection | ATSI | 148 | 148 | 148 |  | Capacity | Solar,Storage,Hybrid |  | 7/1/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AF2-321 | TC1 | PHASE 1 | Stryker-Ridgeville 138 kV |  | Williams County Solar, LLC | OH | Williams | Withdrawn | Generation Interconnection | ATSI | 148 | 148 | 88.8 |  | Capacity | Solar | 3/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-321/AF2-321_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-321/AF2-321_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-126 | TC1 | PHASE 3 | Weston 69 kV II | Juliet Energy | Juliet Energy Project, LLC | OH | Wood | Active | Generation Interconnection | ATSI | 62 | 12 | 8 |  | Capacity | Solar | 2/28/2020 | 12/31/2021 | [5 empty] | 5/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-126/AF2-126_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-126/AF2-126_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-711 | TC2 | PHASE 1 | Lemoyne 345 kV |  | Troy Energy, LLC | OH | Wood | Active | Generation Interconnection | ATSI | 1108.2 | 408.2 | 292.5 |  | Capacity | Natural Gas |  | 5/31/2030 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-565 | TC2 | PHASE 1 | Lemoyne 345kV | Troy Battery Storage | Troy Energy, LLC | OH | Wood | Withdrawn | Generation Interconnection | ATSI | 950 | 250 | 250 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 5/13/2025 | 5/7/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-339 | TC2 | PHASE 1 | West Crawford 69 kV |  | River Otter Solar LLC | OH | Wyandot | Active | Generation Interconnection | AEP | 80 | 80 | 6.76 |  | Capacity | Solar | 9/10/2021 | 11/21/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-148 | TC2 | PHASE 1 | S Berwick - Galion 345 kV |  | Armadillo Solar LLC | OH | Wyandot | Active | Generation Interconnection | AEP | 86 | 86 | 0 |  | Energy | Storage | 2/22/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-329 | TC2 | PHASE 1 | S Berwick - Galion 345 kV |  | Wombat Solar LLC | OH | Wyandot | Active | Generation Interconnection | AEP | 686 | 200 | 156 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 5/30/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-708 | TC2 | RRI APPLICATION REVIEW |  |  | Hunterstown Generation, LLC | PA | Adams | Withdrawn | Generation Interconnection | ME | 960 | 20 | 20 |  | Capacity | Natural Gas |  | 5/31/2025 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-562 | TC2 | PHASE 1 | Springdale 138kV | Springdale Battery Storage II | Springdale Energy, LLC | PA | Allegheny | Active | Generation Interconnection | APS | 356 | 250 | 250 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-150 | TC2 | APPLICATION PHASE | River Dock 23 kV |  | Lock+ Hydro Friends Fund XLII, LLC | PA | Allegheny | Withdrawn | Generation Interconnection | DL | 5.25 | 5.25 | 5.25 |  | Capacity | Hydro | 2/23/2021 | 12/31/2022 | [5 empty] | 4/7/2025 | 4/7/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-037 | TC2 | PHASE 1 | Findlay-Clinton 23 kV |  | PG Solar LLC | PA | Allegheny | Active | Generation Interconnection | DL | 4.7 | 4.7 | 2.82 |  | Capacity | Solar | 11/13/2020 | 12/1/2021 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-549 | TC1 | PHASE 1 | Keystone 230 kV |  | Plum Creek Energy, LLC | PA | Armstrong | Withdrawn | Generation Interconnection | PENELEC | 100 | 100 | 85 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 10/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-549/AG1-549_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-549/AG1-549_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-386 | TC2 | APPLICATION REVIEW | Kittanning-Rural Valley 25 kV |  | IMG Solar LLC | PA | Armstrong | Withdrawn | Generation Interconnection | APS | 30 | 30 | 18 |  | Capacity | Solar | 3/29/2021 | 4/1/2023 | [5 empty] | 3/14/2025 | 3/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AF1-240 | TC1 | PHASE 3 | Timblin 34.5 kV | AR-PIERCE | AR-Pierce LLC | PA | Armstrong | Active | Generation Interconnection | PENELEC | 15.75 | 15.75 | 11 |  | Capacity | Solar | 9/30/2019 | 7/1/2022 | [5 empty] | 6/5/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-240/AF1-240_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-240/AF1-240_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-566 | TC2 | PHASE 1 | South Bend 500kV | Armstrong Battery Storage | Armstrong Power, LLC | PA | Armstrong | Active | Generation Interconnection | APS | 1038.1 | 250 | 250 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-452 | TC2 | PHASE 1 | Clementine-Clementine Jct. 25 kV | McVille Solar | IMG Solar LLC | PA | Armstrong | Active | Generation Interconnection | APS | 19.9 | 19.9 | 8.35 |  | Capacity | Solar | 9/11/2021 | 6/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-654 | TC2 | PHASE 1 | Craigsville - Leards Crossing 12 kV |  | IMG Solar LLC | PA | Armstrong | Active | Generation Interconnection | APS | 14.7 | 14.7 | 8.8 |  | Capacity | Solar | 3/31/2021 | 6/1/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-674 | TC2 | RRI APPLICATION REVIEW |  |  | Shippingport Power Station, LLC | PA | Beaver | Withdrawn | Generation Interconnection | ATSI | 1700 | 1700 | 1650 |  | Capacity | Natural Gas |  | 12/31/2028 | [5 empty] | 5/5/2025 | 4/2/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-621 | TC2 | PHASE 1 | Hoytdale 138 kV |  | ACE | PA | Beaver | Active | Generation Interconnection | ATSI | 150 | 150 | 150 |  | Capacity | Storage | 3/31/2021 | 5/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-162 | TC2 | PHASE 1 | Curryville-RKB-Yellow Creek 23 kV | ASD Woodbury PA2 Solar I | ASD LLC | PA | Bedford | Active | Generation Interconnection | PENELEC | 16 | 16 | 11 |  | Capacity | Solar | 8/31/2021 | 11/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-492 | TC2 | PHASE 1 | Bernville 13 kV | Grand View Solar I | PD Solar 2 LLC | PA | Berks | Withdrawn | Generation Interconnection | ME | 20 | 20 | 12 |  | Capacity | Solar | 9/11/2021 | 7/30/2024 | [5 empty] | 6/9/2025 | 6/9/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-005 | TC2 | PHASE 1 | East Towanda-South Troy 115 kV II | Godfrey Solar III | Franklin Energy, LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 51 | 20 | 14 |  | Capacity | Solar | 4/9/2021 | 9/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-720 | TC2 | PHASE 1 | East Towanda 230 kV |  | Hamilton LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 907.5 | 0 | 60 |  | Capacity | Natural Gas |  | 12/31/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-356 | TC2 | PHASE 1 | South Troy - Canton 34.5 kV |  | Robin Solar LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 20 | 20 | 12 |  | Capacity | Solar | 3/26/2021 | 1/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-327 | TC2 | PHASE 1 | Tennessee Gas-East Towanda 115 kV |  | Agnes Solar LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 58 | 10 | 6 |  | Capacity | Solar | 3/24/2021 | 1/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-220 | TC2 | PHASE 1 | East Towanda-South Troy 115 kV |  | Franklin Energy, LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 31 | 31 | 19.2 |  | Capacity | Solar | 3/10/2021 | 9/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-221 | TC2 | PHASE 1 | South Troy - North Towanda 34.5 kV |  | Franklin Energy, LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 20 | 20 | 13.2 |  | Capacity | Solar | 3/10/2021 | 9/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-206 | TC2 | PHASE 1 | Tennessee Gas-East Towanda 115 kV |  | Agnes Solar LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 48 | 48 | 28.8 |  | Capacity | Solar | 3/4/2021 | 1/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-406 | TC1 | PHASE 1 | Sayre 115 kV |  | Juno Power Management LLC | PA | Bradford | Withdrawn | Generation Interconnection | PENELEC | 75 | 75 | 75 |  | Capacity | Storage | 3/31/2020 | 6/1/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-406/AF2-406_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-050 | TC1 | PHASE 3 | Bearrock-Johnstown 230 kV |  | CPV LLC | PA | Cambria | Active | Generation Interconnection | PENELEC | 150 | 50 | 30 |  | Capacity | Solar | 12/23/2019 | 9/1/2021 | [5 empty] | 3/14/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-050/AF2-050_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-050/AF2-050_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-212 | TC2 | PHASE 1 | Bethlehem - Lilly 46 kV | Noels Creek Solar | Noels Creek Solar, LLC | PA | Cambria | Active | Generation Interconnection | PENELEC | 20 | 20 | 12 |  | Capacity | Solar | 9/7/2021 | 12/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-462 | TC2 | APPLICATION REVIEW | Rachel Hill 115 kV | Black Tulip Storage | Black Tulip Energy, LLC | PA | Cambria | Withdrawn | Generation Interconnection | PENELEC | 60 | 60 | 60 |  | Capacity | Storage | 9/11/2021 | 12/31/2024 | [5 empty] | 3/3/2025 | 2/12/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-074 | TC2 | PHASE 1 | Meckesville Tap 69kV |  | Plainfield Solar, LLC | PA | Carbon | Active | Generation Interconnection | PPL | 38 | 38 | 26.2 |  | Capacity | Solar | 1/15/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-099 | TC2 | APPLICATION REVIEW | Moshannon-Milesburg 230 kV V |  | MPG Solar, LLC | PA | Centre | Withdrawn | Generation Interconnection | APS | 161.98 | 0 | 0 |  | Energy | Storage | 1/28/2021 | 6/30/2022 | [5 empty] | 3/3/2025 | 3/3/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-100 | TC2 | APPLICATION REVIEW | Moshannon-Milesburg 230 kV VI |  | MPG Solar, LLC | PA | Centre | Withdrawn | Generation Interconnection | APS | 161.98 | 0 | 0 |  | Energy | Storage | 1/28/2021 | 6/30/2022 | [5 empty] | 3/3/2025 | 3/3/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG1-377 | TC1 | PHASE 3 | Philipsburg 115 kV |  | CE-Black Moshannon OZ LLC | PA | Centre | Active | Generation Interconnection | PENELEC | 115 | 20 | 6 |  | Capacity | Solar | 9/30/2020 | 8/15/2023 | [5 empty] | 1/31/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-377/AG1-377_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-377/AG1-377_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-378 | TC1 | PHASE 3 | Philipsburg 115 kV |  | CE-Black Moshannon OZ LLC | PA | Centre | Active | Generation Interconnection | PENELEC | 135 | 20 | 6 |  | Capacity | Solar | 9/30/2020 | 8/15/2023 | [5 empty] | 1/31/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-378/AG1-378_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-378/AG1-378_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-668 | TC2 | APPLICATION REVIEW | Madisonburg Jct-Millheim 46 kV |  | Millheim Solar I, LLC | PA | Centre | Withdrawn | Generation Interconnection | APS | 19.9 | 19.9 | 8.3 |  | Capacity | Solar | 9/29/2020 | 8/1/2022 | [5 empty] | 3/13/2025 | 3/7/2025 | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-090 | TC1 | PHASE 3 | Philipsburg 115 kV |  | CE-Black Moshannon OZ LLC | PA | Centre | Active | Generation Interconnection | PENELEC | 95 | 95 | 30 |  | Capacity | Solar,Storage,Hybrid | 8/1/2020 | 8/1/2023 | [5 empty] | 1/31/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-090/AG1-090_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-090/AG1-090_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-313 | TC2 | PHASE 1 | Moshannon-Milesburg 230 kV VII | Nittany North Solar | Invenergy | PA | Centre | Active | Generation Interconnection | APS | 100 | 100 | 60 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-143 | TC2 | APPLICATION REVIEW | Burma-Sligo 25 kV |  | CP | PA | Clarion | Withdrawn | Generation Interconnection | APS | 20 | 20 | 10 |  | Capacity | Solar | 2/16/2021 | 12/31/2026 | [5 empty] | 3/14/2025 | 3/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-429 | TC2 | PHASE 1 | Burma - Armstrong 138 kV | Gardenia | Gardenia Solar, LLC | PA | Clarion | Active | Generation Interconnection | APS | 69 | 69 | 53.86 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 2/29/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-558 | TC2 | APPLICATION REVIEW | Shawville - Phillipsburg 34.5 kV II |  | Morrisdale LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 39.8 | 19.9 | 8.3 |  | Capacity | Solar | 3/31/2021 | 4/1/2023 | [5 empty] | 1/23/2025 | 1/23/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-559 | TC2 | APPLICATION REVIEW | Shawville - Phillipsburg 34.5 kV III |  | Morrisdale LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 59.7 | 19.9 | 8.3 |  | Capacity | Solar | 3/31/2021 | 4/1/2024 | [5 empty] | 1/23/2025 | 1/23/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-560 | TC2 | APPLICATION REVIEW | Phillipsburg (Karthaus) 34.5 kV |  | Morrisdale LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 79.6 | 19.9 | 8.3 |  | Capacity | Solar | 3/31/2021 | 4/1/2025 | [5 empty] | 1/23/2025 | 1/23/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG1-308 | TC1 | PHASE 1 | Shawville-Philipsburg 34.5 kV |  | Morrisdale LLC | PA | Clearfield | Withdrawn | Generation Interconnection | PENELEC | 19.9 | 19.9 | 8.3 |  | Capacity | Solar | 9/29/2020 | 8/1/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-308/AG1-308_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-667 | TC2 | PHASE 1 | Philipsburg-Shawville 34.5 kV |  | CL-Shiloh LLC | PA | Clearfield | Active | Generation Interconnection | PENELEC | 18 | 18 | 10.8 |  | Capacity | Solar | 2/29/2020 | 6/1/2021 | [5 empty] | 5/5/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-296 | TC1 | PHASE 3 | Madera 34.5 kV |  | CL-Belsena LLC | PA | Clearfield | Active | Generation Interconnection | PENELEC | 20 | 20 | 12 |  | Capacity | Solar | 3/28/2020 | 10/1/2021 | [5 empty] | 2/18/2025 |  | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-296/AF2-296_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-296/AF2-296_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-099 | TC1 | PHASE 1 | Moshannon-Milesburg 230 kV III |  | Moonlight Flats Solar Power, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 126.5 | 126.5 | 75.9 |  | Capacity | Solar,Storage,Hybrid | 9/4/2019 | 4/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-099/AF1-099_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-099/AF1-099_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-100 | TC1 | PHASE 1 | Shawville-Moshannon 230 kV |  | Mineral Basin Solar Power, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | PENELEC | 250 | 250 | 150 |  | Capacity | Solar,Storage,Hybrid | 9/4/2019 | 4/1/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-100/AF1-100_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-142 | TC1 | PHASE 1 | Moshannon-Milesburg 230 kV IV |  | Moonlight Flats Solar Power, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 328.9 | 202.4 | 121.44 |  | Capacity | Solar,Storage,Hybrid | 9/4/2019 | 4/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-142/AF1-142_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-142/AF1-142_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-668 | TC2 | PHASE 1 | Harvey Run 34.5 kV |  | Du Bois PV I, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | PENELEC | 20 | 20 | 12.5 |  | Capacity | Solar | 3/31/2021 | 11/1/2023 | [5 empty] | 5/5/2025 | 4/22/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-746 | TC2 | PHASE 1 | Madera - Westover South 115 kV |  | CPV LLC | PA | Clearfield | Active | Generation Interconnection | PENELEC | 109.9 | 0 | 20 |  | Capacity | Wind |  | 4/29/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-675 | TC2 | RRI APPLICATION REVIEW |  |  | Invitium Energy, LLC | PA | Columbia | Withdrawn | Generation Interconnection | PPL | 2175 | 2175 | 2070 |  | Capacity | Natural Gas |  | 6/30/2030 | [5 empty] | 5/5/2025 | 4/23/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-688 | TC2 | RRI APPLICATION REVIEW |  |  | Invitium Energy, LLC | PA | Columbia | Withdrawn | Generation Interconnection | PPL | 1450 | 1450 | 1380 |  | Capacity | Natural Gas |  | 6/30/2030 | [5 empty] | 5/5/2025 | 4/23/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-689 | TC2 | RRI APPLICATION REVIEW |  |  | Invitium Energy, LLC | PA | Columbia | Withdrawn | Generation Interconnection | PPL | 1450 | 1450 | 1380 |  | Capacity | Natural Gas |  | 6/30/2030 | [5 empty] | 5/5/2025 | 4/23/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-594 | TC2 | PHASE 1 | Benton-Scott 69 kV II |  | North Corners Energy, LLC | PA | Columbia | Active | Generation Interconnection | PPL | 20 | 20 | 2 |  | Capacity | Solar | 3/31/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-176 | TC2 | PHASE 1 | Geneva 115 kV |  | Trestle Solar Farm, LLC | PA | Crawford | Active | Generation Interconnection | PENELEC | 150 | 150 | 90 |  | Capacity | Solar | 2/26/2021 | 1/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-247 | TC2 | APPLICATION REVIEW | Northwestern REC Dixonburg-Vernon 34.5 kV |  | Cassidy Solar LLC | PA | Crawford | Withdrawn | Generation Interconnection | PENELEC | 20 | 20 | 12 |  | Capacity | Solar | 3/17/2021 | 1/15/2023 | [5 empty] | 2/6/2025 | 2/6/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-490 | TC2 | PHASE 1 | Venango Junction - Cambridge Springs 34.5 kV | Tamarack Solar 1 | PD Solar 11 LLC | PA | Crawford | Active | Generation Interconnection | PENELEC | 20 | 20 | 12 |  | Capacity | Solar | 9/10/2021 | 7/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-159 | TC2 | PHASE 1 | Conneaut-Conneaut Tap 69 kV | ASD Carmen PA2 Solar | ASD LLC | PA | Crawford | Active | Generation Interconnection | ATSI | 20 | 20 | 13.9 |  | Capacity | Solar | 8/30/2021 | 11/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-166 | TC2 | PHASE 1 | Newville-Nottingham Tap 1 69 kV |  | Costen Solar, Inc | PA | Cumberland | Active | Generation Interconnection | PPL | 10 | 10 | 0 |  | Energy | Solar | 2/25/2021 | 8/18/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-096 | TC2 | PHASE 1 | Dauphin PG Tie-Dauphin Juniata Tie 69 kV |  | Dauphin Solar I, LLC | PA | Dauphin | Active | Generation Interconnection | PPL | 55 | 0 | 0 |  | Energy | Storage | 1/28/2021 | 12/1/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-695 | TC2 | PHASE 1 | Three Mile Island 230 kV |  | Constellation Energy Generation, LLC | PA | Dauphin | Active | Generation Interconnection | ME | 859 | 859 | 803 |  | Capacity | Nuclear |  | 10/1/2027 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-538 | TC2 | APPLICATION REVIEW | Ridgeway - Motion Control 46 kV |  | EL-Jakes Hollow LLC | PA | Elk | Withdrawn | Generation Interconnection | APS | 20 | 20 | 15.42 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 10/15/2022 | [5 empty] | 3/3/2025 | 2/28/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AF1-306 | TC1 | PHASE 1 | Squab Hollow 230 kV |  | Seven Creek Energy, LLC | PA | Elk | Withdrawn | Generation Interconnection | APS | 197.2 | 197.2 | 49.3 |  | Capacity | Storage | 9/30/2019 | 5/31/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-306/AF1-306_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-010 | TC1 | PHASE 3 | Union City-Titusville 115 kV |  | RWE LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 77 | 77 | 46 |  | Capacity | Solar | 10/11/2019 | 12/15/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-010/AF2-010_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-010/AF2-010_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-438 | TC2 | PHASE 1 | Union City 34.5 kV |  | Clemens Solar LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 10 | 10 | 6.7 |  | Capacity | Solar | 3/30/2021 | 6/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-008 | TC2 | PHASE 1 | Erie South-Warren 230 kV |  | Blatche Solar, LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 60 | 60 | 40.2 |  | Capacity | Solar | 10/8/2020 | 3/30/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-009 | TC2 | PHASE 1 | Erie South-Warren 230 kV II |  | Blatche Solar, LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 80 | 20 | 12.9 |  | Capacity | Solar | 10/8/2020 | 3/30/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-548 | TC1 | PHASE 3 | Erie South-Union City 115 kV |  | French Creek Energy, LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 150 | 150 | 45 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 10/31/2022 | [5 empty] | 3/7/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-548/AG1-548_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-548/AG1-548_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-491 | TC2 | PHASE 1 | Union City 34.5 kV | Waterford Solar 1 | PD Solar 11 LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 20 | 20 | 12 |  | Capacity | Solar | 9/11/2021 | 7/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-331 | TC2 | PHASE 1 | Edinboro South-Erie South 25kV | McLane Solar | IMG Solar LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 19.9 | 19.9 | 11.9 |  | Capacity | Solar | 9/9/2021 | 6/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-206 | TC2 | PHASE 1 | Bethelboro 138 kV | Lafayette Storage | Lafayette Energy, LLC | PA | Fayette | Active | Generation Interconnection | APS | 60 | 60 | 60 |  | Capacity | Storage | 9/8/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-247 | TC2 | PHASE 1 | Lardin - Lake Lynn 138kV | Poseidon Solar 1 | Poseidon Energy, LLC | PA | Fayette | Active | Generation Interconnection | APS | 40 | 40 | 24 |  | Capacity | Solar | 9/9/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-248 | TC2 | PHASE 1 | Lardin - Lake Lynn 138kV | Poseidon Solar 2 | Poseidon Energy, LLC | PA | Fayette | Active | Generation Interconnection | APS | 65 | 25 | 15 |  | Capacity | Solar | 9/9/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-249 | TC2 | PHASE 1 | Lardin – Lake Lynn 138kV | Poseidon Storage | Poseidon Energy, LLC | PA | Fayette | Active | Generation Interconnection | APS | 145 | 80 | 80 |  | Capacity | Storage | 9/9/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-367A | TC2 | PHASE 1 | Franklin 138 kV II | Iron Javelin Emerald | Emerald Renewable LLC | PA | Greene | Active | Generation Interconnection | APS | 72 | 72 | 43.2 |  | Capacity | Solar | 9/10/2021 | 9/10/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-590 | TC2 | APPLICATION REVIEW | Shingletown-Lewistown 230 kV |  | North Corners Energy, LLC | PA | Huntingdon | Withdrawn | Generation Interconnection | PENELEC | 92.1 | 38.2 | 22.9 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/1/2024 | [5 empty] | 1/30/2025 | 1/30/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG1-473 | TC1 | PHASE 1 | Shingletown-Lewistown 230 kV |  | North Corners Energy, LLC | PA | Huntingdon | Withdrawn | Generation Interconnection | PENELEC | 53.9 | 53.9 | 32.34 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/1/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-473/AG1-473_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-473/AG1-473_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-561 | TC2 | PHASE 1 | Glory - Glen Campbell 34.5 kV |  | Chestnut LLC | PA | Indiana | Active | Generation Interconnection | PENELEC | 20 | 20 | 12 |  | Capacity | Solar | 3/31/2021 | 12/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-268 | TC2 | PHASE 1 | Seward-Glory 115 kV II | Clark Run Solar BESS | Clarke Run Solar LLC | PA | Indiana | Active | Generation Interconnection | PENELEC | 100 | 0 | 36.6 |  | Capacity | Storage | 9/9/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-102 | TC2 | PHASE 1 | Seward-Glory 115 kV |  | Clarke Run Solar LLC | PA | Indiana | Active | Generation Interconnection | PENELEC | 100 | 100 | 63.4 |  | Capacity | Solar | 7/30/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-734 | TC2 | PHASE 1 | South Bend 500 kV |  | Armstrong Power, LLC | PA | Indiana | Active | Generation Interconnection | APS | 1308.4 | 270.3 | 268.6 |  | Capacity | Natural Gas |  | 5/31/2030 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-484 | TC2 | PHASE 1 | Mifflintown Bus-Mifflintown Tap 69 kV II |  | Cottontail Solar LLC | PA | Juniata | Active | Generation Interconnection | PPL | 20 | 0 | 4.1 |  | Capacity | Solar | 3/31/2021 | 8/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-697 | TC2 | PHASE 1 | Lackawanna 230kV |  | Lackawanna Energy Center LLC | PA | Lackawanna | Active | Generation Interconnection | PPL | 1522 | 39 | 78.6 |  | Capacity | Natural Gas |  | 5/19/2028 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-236 | TC2 | PHASE 1 | Potter-Harlan 69 kV |  | Harlansburg PV I, LLC | PA | Lawrence | Active | Generation Interconnection | ATSI | 60 | 20 | 2 |  | Capacity | Solar | 3/15/2021 | 10/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-098 | TC2 | APPLICATION REVIEW | Copperstone-North Lebanon 230 kV II |  | Lebanon Solar I, LLC | PA | Lebanon | Withdrawn | Generation Interconnection | ME | 70 | 0 | 0 |  | Energy | Storage | 1/28/2021 | 6/30/2022 | [5 empty] | 2/10/2025 | 2/10/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-561 | TC2 | PHASE 1 | Ironwood 230kV | Ironwood Battery Storage | Helix Ironwood, LLC | PA | Lebanon | Active | Generation Interconnection | ME | 1075 | 250 | 250 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-733 | TC2 | RRI APPLICATION REVIEW | Susquehanna-Mountain 230 kV |  | Invenergy | PA | Luzerne | Withdrawn | Generation Interconnection | PPL | 637.8 | 637.8 | 637.8 |  | Capacity | Natural Gas |  | 5/31/2031 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG1-277 | TC1 | PHASE 1 | Salem-Beacon Power 69 kV |  | LU-Tank LLC | PA | Luzerne | Withdrawn | Generation Interconnection | PPL | 40 | 40 | 32 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-277/AG1-277_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-277/AG1-277_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-278 | TC1 | PHASE 2 | Salem-Beacon Power 69 kV |  | LU-Tank LLC | PA | Luzerne | Withdrawn | Generation Interconnection | PPL | 60 | 20 | 15.42 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-278/AG1-278_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-278/AG1-278_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-279 | TC1 | PHASE 1 | Salem-Beacon Power 69 kV |  | LU-Tank LLC | PA | Luzerne | Withdrawn | Generation Interconnection | PPL | 80 | 20 | 15.42 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-279/AG1-279_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-279/AG1-279_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AH1-707 | TC2 | PHASE 1 | Saegers 230 kV |  | Hamilton LLC | PA | Lycoming | Active | Generation Interconnection | PPL | 907 | 0 | 30 |  | Capacity | Natural Gas |  | 12/31/2026 | [5 empty] | 5/14/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-487 | TC2 | PHASE 1 | Camp Reynolds 12.5 kV | Maysville Solar 2 | PD Solar 11 LLC | PA | Mercer | Active | Generation Interconnection | ATSI | 20 | 20 | 12 |  | Capacity | Solar | 9/10/2021 | 7/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-051 | TC1 | DP1 | Maysville 69 kV III |  | MC Solar, LLC | PA | Mercer | Withdrawn | Generation Interconnection | ATSI | 70 | 20 | 20 |  | Capacity | Storage | 7/18/2020 | 6/30/2022 | [5 empty] | 1/29/2025 | 7/18/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-051/AG1-051_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-176 | TC1 | PHASE 1 | Masury-Maysville 138 kV |  | Sanderson Solar LLC | PA | Mercer | Withdrawn | Generation Interconnection | ATSI | 60 | 60 | 36 |  | Capacity | Solar | 3/19/2020 | 9/15/2022 | [5 empty] | 6/25/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-176/AF2-176_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-249 | TC2 | PHASE 1 | Stoneboro-Perry 69 kV |  | Steamboat Solar LLC | PA | Mercer | Active | Generation Interconnection | ATSI | 20 | 20 | 12 |  | Capacity | Solar | 3/17/2021 | 1/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-250 | TC2 | PHASE 1 | Stoneboro-Perry 69 kV II |  | Steamboat Solar LLC | PA | Mercer | Active | Generation Interconnection | ATSI | 40 | 20 | 12 |  | Capacity | Solar | 3/17/2021 | 1/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-602 | TC2 | APPLICATION REVIEW | Maysville 69 kV V |  | MC Solar, LLC | PA | Mercer | Withdrawn | Generation Interconnection | ATSI | 50 | 0 | 0 |  | Energy | Storage | 3/31/2021 | 9/15/2022 | [5 empty] | 3/11/2025 | 3/11/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-365 | TC2 | PHASE 1 | Conneaut Tap-Werner 69 kV |  | Amadeus Solar LLC | PA | Mercer | Active | Generation Interconnection | ATSI | 35 | 35 | 21 |  | Capacity | Solar | 3/26/2021 | 5/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-456 | TC2 | PHASE 1 | Pierce Brook-Lewis Run 230 kV |  | McKean LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 80 | 80 | 55.8 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-457 | TC2 | PHASE 1 | Pierce Brook - Lewis Run 230 kV |  | McKean LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 160 | 80 | 55.8 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-276 | TC1 | PHASE 1 | Lewis Run-Pierce Brook 230 kV |  | McKean LLC | PA | McKean | Withdrawn | Generation Interconnection | PENELEC | 100 | 100 | 67 |  | Capacity | Solar | 9/30/2019 | 6/29/2024 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-276/AF1-276_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-277 | TC1 | PHASE 1 | Lewis Run-Pierce Brook 2 230 kV |  | McKean LLC | PA | McKean | Withdrawn | Generation Interconnection | PENELEC | 200 | 100 | 67 |  | Capacity | Solar | 9/30/2019 | 6/29/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-277/AF1-277_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-357 | TC2 | PHASE 1 | Pierce Brook-Lewis Run 230kV | McKean Solar 1 - 20 MW | McKean LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 180 | 20 | 12 |  | Capacity | Solar | 9/10/2021 | 9/10/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-358 | TC2 | PHASE 1 | Pierce Brook-Lewis Run 230kV | McKean Solar 1 - Energy Storage | McKean LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 200 | 20 | 20 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-359 | TC2 | PHASE 1 | Pierce Brook - Lewis Run 230 kV | McKean Solar 2 - 20 MW | McKean LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 220 | 20 | 12 |  | Capacity | Solar | 9/10/2021 | 9/10/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-360 | TC2 | PHASE 1 | Pierce Brook - Lewis Run 230 kV | McKean Solar 2 - Energy Storage | McKean LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 240 | 20 | 20 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-587 | TC2 | PHASE 1 | Farmers Valley – Ridgeway 115 kV | Wild Hollow Solar | RWE LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 200 | 200 | 120 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-588 | TC2 | PHASE 1 | Lewis Run - Pierce Brook 230 kV | McKean County Solar II | RWE LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 240 | 240 | 144 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-589 | TC2 | PHASE 1 | Lewis Run - Pierce Brook 230 kV | Wild Sky Storage | RWE LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 410 | 170 | 170 |  | Capacity | Storage | 9/10/2021 | 12/16/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-390 | TC2 | APPLICATION REVIEW | TBD 69 kV | THP Solar 1 | PA Project 1, LLC | PA | Northumberland | Withdrawn | Generation Interconnection | PPL | 19.9 | 19.9 | 14.1 |  | Capacity | Solar | 9/10/2021 | 7/31/2023 | [5 empty] | 3/13/2025 | 3/12/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-430 | TC2 | PHASE 1 | Sunbury-Dalmatia 69 kV II |  | Breezeway Solar LLC | PA | Northumberland | Active | Generation Interconnection | PPL | 60 | 60 | 37.7 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-481 | TC2 | PHASE 1 | Derry Tap-Derry Bus 69 kV III |  | Cottontail Solar LLC | PA | Northumberland | Active | Generation Interconnection | PPL | 20 | 0 | 4.1 |  | Capacity | Solar | 3/31/2021 | 7/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-606 | TC2 | PHASE 1 | Sunbury-Juniata 500 kV |  | North Corners Energy, LLC | PA | Perry | Active | Generation Interconnection | PPL | 89 | 89 | 35.6 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-418 | TC2 | PHASE 1 | Blain 115 kV |  | Wills Creek Solar LLC | PA | Perry | Active | Generation Interconnection | PENELEC | 40 | 40 | 20 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 5/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-533 | TC2 | PHASE 1 | Sunbury-Juniata II | Greenwood Solar II | North Corners Energy, LLC | PA | Perry | Active | Generation Interconnection | PPL | 185.2 | 96.2 | 38.5 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-392C | TC1 | PHASE 1 | Gold 115 kV IV |  | PO-Cowburn LLC | PA | Potter | Withdrawn | Generation Interconnection | PENELEC | 90 | 15 | 9 |  | Capacity | Solar | 10/1/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-392C/AG1-392C_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-392C/AG1-392C_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-392B | TC1 | PHASE 1 | Gold 115 kV III |  | PO-Cowburn LLC | PA | Potter | Withdrawn | Generation Interconnection | PENELEC | 75 | 15 | 9 |  | Capacity | Solar | 10/1/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-392B/AG1-392B_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-392B/AG1-392B_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-392A | TC1 | PHASE 1 | Gold 115 kV II |  | PO-Cowburn LLC | PA | Potter | Withdrawn | Generation Interconnection | PENELEC | 60 | 30 | 18 |  | Capacity | Solar | 10/1/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-392A/AG1-392A_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-392A/AG1-392A_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-392 | TC1 | PHASE 1 | Gold 115 kV I |  | PO-Cowburn LLC | PA | Potter | Withdrawn | Generation Interconnection | PENELEC | 30 | 30 | 18 |  | Capacity | Solar | 9/30/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-392/AG1-392_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-392/AG1-392_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-060 | TC1 | PHASE 1 | Eldred 69 kV |  | ANTHRACITE RIDGE LLC | PA | Schuylkill | Withdrawn | Generation Interconnection | PPL | 174.8 | 174.8 | 25.7 |  | Capacity | Solar | 7/29/2020 | 5/31/2022 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-060/AG1-060_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-056 | TC1 | PHASE 1 | Shenandoah Tap 1– Mahanoy Tap 2 69 kV |  | Locust Ridge Solar LLC | PA | Schuylkill | Withdrawn | Generation Interconnection | PPL | 50 | 50 | 33 |  | Capacity | Solar | 1/16/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-056/AF2-056_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-056/AF2-056_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-161 | TC2 | PHASE 1 | Wheelabrator Frackville-Gilberton 69 kV |  | New Boston Solar, LLC | PA | Schuylkill | Active | Generation Interconnection | PPL | 43 | 43 | 18.06 |  | Capacity | Solar | 2/25/2021 | 12/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-479 | TC2 | PHASE 1 | Penns Tap-Richfield Tie 69 kV II |  | Cottontail Solar LLC | PA | Snyder | Active | Generation Interconnection | PPL | 20 | 0 | 4.1 |  | Capacity | Solar | 3/31/2021 | 10/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-705 | TC2 | PHASE 1 | Sunbury #1 500kV |  | Hummel Station, LLC | PA | Snyder | Active | Generation Interconnection | PPL | 1153.4 | 32.4 | 32.4 |  | Capacity | Natural Gas |  | 5/31/2027 | [5 empty] | 5/6/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-460 | TC2 | PHASE 1 | Hooversville - Scalp Level 115 kV | Julius Solar | Julius Energy, LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 66 | 66 | 39.6 |  | Capacity | Solar | 9/10/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-201 | TC2 | PHASE 1 | Allegheny-New Baltimore 115kV | Mountain Ridge Solar | Mango Solar LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 40 | 40 | 24 |  | Capacity | Solar | 9/3/2021 | 8/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-203 | TC2 | PHASE 1 | Allegheny-Somerset 115 kV | Turnpike Solar | Turnpike Solar, LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 70 | 70 | 42 |  | Capacity | Solar | 9/3/2021 | 8/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-205 | TC2 | PHASE 1 | Allegheny-New Baltimore 115kV |  | Mango Solar LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 40 | 0 | 16 |  | Capacity | Storage | 9/3/2021 | 8/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-411 | TC2 | PHASE 1 | Statler Hill 115 kV |  | Iris Energy LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 63 | 63 | 40.7 |  | Capacity | Solar | 3/31/2021 | 7/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-090 | TC2 | PHASE 1 | Scalp Level 23 kV IV |  | Neptune Solar LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 14 | 14 | 8.4 |  | Capacity | Solar | 1/26/2021 | 1/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-091 | TC2 | PHASE 1 | Scalp Level 23 kV V |  | Neptune Solar LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 20 | 6 | 3.6 |  | Capacity | Solar | 1/26/2021 | 1/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-381 | TC1 | PHASE 1 | Bedford North-Central City West 115 kV |  | Panther Run Solar, LLC | PA | Somerset | Withdrawn | Generation Interconnection | PENELEC | 60 | 60 | 40.2 |  | Capacity | Solar | 4/1/2020 | 6/30/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-381/AF2-381_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-412 | TC1 | PHASE 1 | Mainesburg 115 kV |  | Elk Run LLC | PA | Tioga | Withdrawn | Generation Interconnection | PENELEC | 100 | 100 | 100 |  | Capacity | Storage | 3/31/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-412/AF2-412_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-412/AF2-412_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AH1-160 | TC2 | APPLICATION REVIEW | Tower Hill 34.5 kV | ASD Warner PA2 Solar LLC | ASD LLC | PA | Tioga | Withdrawn | Generation Interconnection | PENELEC | 20 | 20 | 13.3 |  | Capacity | Solar | 8/31/2021 | 11/1/2023 | [5 empty] | 3/28/2025 | 3/28/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-158 | TC2 | PHASE 1 | Eclipse-Piney 115 kV III |  | Deal Solar LLC | PA | Venango | Active | Generation Interconnection | PENELEC | 80 | 0 | 30 |  | Capacity | Storage | 9/1/2021 | 8/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-050 | TC2 | PHASE 1 | Eclipse-Piney 115 kV |  | Deal Solar LLC | PA | Venango | Active | Generation Interconnection | PENELEC | 50 | 50 | 30 |  | Capacity | Solar | 7/7/2021 | 7/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-051 | TC2 | PHASE 1 | Eclipse-Piney 115 kV II |  | Deal Solar LLC | PA | Venango | Active | Generation Interconnection | PENELEC | 80 | 30 | 18 |  | Capacity | Solar | 7/7/2021 | 7/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-164 | TC1 | PHASE 1 | Handsome Lake 345 kV |  | Heartland Solar LLC | PA | Venango | Withdrawn | Generation Interconnection | PENELEC | 80 | 80 | 48 |  | Capacity | Solar | 3/17/2020 | 9/15/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-164/AF2-164_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-420 | TC2 | PHASE 1 | Eclipse #2 34.5 kV |  | Bear Oak Solar LLC | PA | Venango | Active | Generation Interconnection | PENELEC | 25 | 25 | 14 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 5/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-200 | TC2 | PHASE 1 | North Warren–Russell 34.5 kV |  | Sugaree Solar LLC | PA | Warren | Active | Generation Interconnection | PENELEC | 20 | 20 | 12 |  | Capacity | Solar | 3/2/2021 | 1/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-545 | TC2 | PHASE 1 | Wylie Ridge-Tidd 345kV | Cornerstone Solar | North Corners Energy, LLC | PA | Washington | Active | Generation Interconnection | APS | 200 | 200 | 20 |  | Capacity | Solar | 9/10/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-140 | TC2 | PHASE 1 | Vasco 138 kV |  | Red Stone Renewables, LLC | PA | Westmoreland | Active | Generation Interconnection | APS | 150 | 150 | 115 |  | Capacity | Solar,Storage,Hybrid | 7/30/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-076 | TC2 | APPLICATION REVIEW | Loyalhanna - Reed Junction 25 kV |  | CP LLC | PA | Westmoreland | Withdrawn | Generation Interconnection | APS | 18 | 18 | 9 |  | Capacity | Solar | 7/29/2021 | 12/31/2023 | [5 empty] | 3/14/2025 | 3/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-439 | TC2 | PHASE 1 | Oxbow 34.5 kV |  | Field Brook Solar LLC | PA | Wyoming | Active | Generation Interconnection | PENELEC | 9.8 | 9.8 | 5.3 |  | Capacity | Solar | 3/30/2021 | 6/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-476 | TC2 | PHASE 1 | Hokes-Grantley 69 kV II |  | Cottontail Solar LLC | PA | York | Active | Generation Interconnection | ME | 20 | 0 | 0.1 |  | Capacity | Solar | 3/31/2021 | 3/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-477 | TC2 | PHASE 1 | Hokes-Jackson 69 kV III |  | Cottontail Solar LLC | PA | York | Active | Generation Interconnection | ME | 20 | 0 | 0.5 |  | Capacity | Solar | 3/31/2021 | 4/30/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-478 | TC2 | PHASE 1 | Hokes-Jackson 69 kV IV |  | Cottontail Solar LLC | PA | York | Active | Generation Interconnection | ME | 20 | 0 | 0.5 |  | Capacity | Solar | 3/31/2021 | 3/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-046 | TC2 | PHASE 1 | Peach Bottom 500 kV |  | Calpine | PA | York | Withdrawn | Generation Interconnection | PECO | 905 | 25 | 15 |  | Capacity | Solar | 7/1/2021 | 6/1/2023 | [5 empty] | 5/5/2025 | 4/25/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-535 | TC2 | PHASE 1 | Nagel - Cane River 230 kV |  | Pecan Flats Energy, LLC | TN | Hawkins | Active | Generation Interconnection | AEP | 100 | 100 | 40 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-302 | TC1 | PHASE 2 | Scottsville-Colleen 138 kV |  | Vista Energy Facility, LLC | VA | Albemarle | Withdrawn | Generation Interconnection | AEP | 75 | 20 | 12 |  | Capacity | Solar | 3/30/2020 | 12/12/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-302/AF2-302_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-302/AF2-302_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-323 | TC1 | PHASE 2 | Scottsville-Colleen 138 kV |  | Vista Energy Facility, LLC | VA | Albemarle | Withdrawn | Generation Interconnection | AEP | 55 | 55 | 33 |  | Capacity | Solar | 9/30/2019 | 12/12/2022 | [5 empty] | 6/5/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-323/AF1-323_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-323/AF1-323_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-022 | TC1 | PHASE 2 | Scottsville-Colleen 138 kV |  | Vista Energy Facility, LLC | VA | Albemarle | Withdrawn | Generation Interconnection | AEP | 95 | 20 | 12 |  | Capacity | Solar | 5/26/2020 | 12/12/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-022/AG1-022_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-022/AG1-022_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-021 | TC1 | PHASE 3 | Jetersville-Ponton 115 kV | Amelia Energy Facility | Amelia Energy Facility, LLC | VA | Amelia | Active | Generation Interconnection | Dominion | 86 | 20 | 10.8 |  | Capacity | Solar | 5/26/2020 | 12/12/2023 | [5 empty] | 6/9/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-021/AG1-021_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-021/AG1-021_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-294 | TC1 | PHASE 3 | Jetersville-Ponton 115 kV | Amelia Energy Facility | Amelia Energy Facility, LLC | VA | Amelia | Active | Generation Interconnection | Dominion | 41 | 41 | 22.2 |  | Capacity | Solar | 9/30/2019 | 12/1/2022 | [5 empty] | 6/9/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-294/AF1-294_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-294/AF1-294_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-115 | TC1 | PHASE 3 | Jetersville-Ponton 115 kV | Amelia Energy Facility | Amelia Energy Facility, LLC | VA | Amelia | Active | Generation Interconnection | Dominion | 66 | 25 | 13.5 |  | Capacity | Solar | 2/28/2020 | 12/1/2022 | [5 empty] | 6/9/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-115/AF2-115_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-115/AF2-115_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-280 | TC2 | PHASE 1 | Jetersville-Ponton 115 kV |  | Amelia Energy Facility, LLC | VA | Amelia | Active | Generation Interconnection | Dominion | 106 | 20 | 12 |  | Capacity | Solar | 9/9/2021 | 12/12/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-123 | TC1 | PHASE 1 | Amherst 69 kV |  | Five Oaks Solar Project, LLC | VA | Amherst | Withdrawn | Generation Interconnection | AEP | 65 | 65 | 38.5 |  | Capacity | Solar | 8/31/2020 | 12/1/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-123/AG1-123_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-494 | TC1 | PHASE 3 | Boxwood-Riverville 138 kV |  | Mainspring Grid, LLC | VA | Amherst | Active | Generation Interconnection | AEP | 50 | 50 | 20 |  | Capacity | Storage | 9/30/2020 | 12/1/2023 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-494/AG1-494_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-494/AG1-494_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-049 | TC2 | PHASE 1 | Van Dorn 34.5 kV | Alexandria | Covanta LLC | VA | Arlington | Active | Generation Interconnection | Dominion | 20 | 0 | 20 |  | Capacity | Biomass | 11/20/2020 | 12/31/2020 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-537 | TC1 | PHASE 2 | Barterbrook-Stuarts Draft 115 kV |  | Chestnut LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 75 | 75 | 32 |  | Capacity | Storage | 9/30/2020 | 10/1/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-537/AG1-537_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-537/AG1-537_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-195 | TC1 | PHASE 1 | Valley 230 kV |  | Hectate LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 150 |  | Capacity | Solar,Storage,Hybrid | 9/18/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-195/AG1-195_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-196 | TC1 | PHASE 1 | Grottoes 115 kV |  | Hectate LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 150 |  | Capacity | Solar,Storage,Hybrid | 9/18/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-196/AG1-196_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-421 | TC1 | PHASE 1 | Lexington-Dooms 230 kV |  | Leeward Renewable Energy Development, LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 200 | 200 | 120 |  | Capacity | Solar | 9/30/2020 | 12/29/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-421/AG1-421_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-422 | TC1 | PHASE 1 | Lexington-Dooms 230 kV |  | Leeward Renewable Energy Development, LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 50 | 50 | 50 |  | Capacity | Storage | 9/30/2020 | 12/29/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-422/AG1-422_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-311 | TC2 | PHASE 1 | Smith Mountain 138 kV |  | Smith Mountain Storage, LLC | VA | Bedford | Active | Generation Interconnection | AEP | 75 | 75 | 52.5 |  | Capacity | Storage | 3/23/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-570 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Zeus LLC | VA | Brunswick | Active | Generation Interconnection | Dominion | 400 | 400 | 100 |  | Capacity | Solar | 3/31/2021 | 3/29/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-571 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Zeus LLC | VA | Brunswick | Active | Generation Interconnection | Dominion | 500 | 100 | 40 |  | Capacity | Storage | 3/31/2021 | 3/29/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-068 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Virginia Electric and Power Company | VA | Brunswick | Active | Generation Interconnection | Dominion | 100 | 100 | 60 |  | Capacity | Solar | 12/30/2020 | 12/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-069 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Virginia Electric and Power Company | VA | Brunswick | Active | Generation Interconnection | Dominion | 250 | 150 | 90 |  | Capacity | Solar | 12/30/2020 | 12/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-580 | TC2 | APPLICATION REVIEW | Rawlings-Clover 500 kV |  | Bellflower | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 1/29/2021 | 10/1/2024 | [5 empty] | 3/6/2025 | 3/6/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-581 | TC2 | PHASE 1 | Rawlings-Clover 500 kV |  | Bellflower | VA | Brunswick | Active | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 1/29/2021 | 10/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-428 | TC1 | PHASE 2 | Danieltown DP–Brunswick 69 kV |  | ACE | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 46.8 | 46.8 | 28.08 |  | Capacity | Solar | 9/30/2020 | 12/31/2024 | [5 empty] | 2/5/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-428/AG1-428_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-428/AG1-428_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-505 | TC1 | PHASE 1 | Rawlings-Clover 500 kV |  | Bellflower | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 9/30/2020 | 7/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-505/AG1-505_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-506 | TC1 | PHASE 1 | Rawlings-Clover 500 kV |  | Bellflower | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 9/30/2020 | 7/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-506/AG1-506_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-153 | TC1 | PHASE 3 | Heritage 500 kV |  | Virginia Electric and Power Company | VA | Brunswick | Active | Generation Interconnection | Dominion | 75 | 75 | 30 |  | Capacity | Storage | 9/10/2020 | 12/1/2023 |  |  |  | 6/22/2028 | 7/8/2028 | 2/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-153/AG1-153_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-153/AG1-153_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/ag1_153_csa.pdf | Posted
AH1-221 | TC2 | PHASE 1 | Heritage 500 kV |  | Virginia Electric and Power Company | VA | Brunswick | Active | Generation Interconnection | Dominion | 75 | 0 | 45 |  | Capacity | Storage | 9/8/2021 | 12/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-640 | TC2 | APPLICATION REVIEW | Danieltown DP–Brunswick 69 kV |  | ACE | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 46.8 | 0 | 18.7 |  | Capacity | Storage | 3/31/2021 | 4/1/2025 | [5 empty] | 3/31/2025 | 2/24/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-678 | TC2 | PHASE 1 | Heritage 500 kV |  | Virginia Electric and Power Company | VA | Brunswick | Active | Generation Interconnection | Dominion | 1525.5 | 0 | 34 |  | Capacity | Natural Gas |  | 12/31/2023 | [5 empty] | 5/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-528 | TC2 | PHASE 1 | Rawlings - Unity 500 kV | Honeybee Solar, LLC | Honeybee Solar Energy, LLC | VA | Brunswick | Active | Generation Interconnection | Dominion | 300.8 | 300.8 | 180 |  | Capacity | Solar | 9/10/2021 | 3/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-408 | TC2 | PHASE 1 | Freeman DP – Lawrenceville 115 kV |  | SR Brunswick, LLC | VA | Brunswick | Active | Generation Interconnection | Dominion | 120 | 120 | 75 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-687 | TC2 | PHASE 1 | Bear Garden 230kV |  | Virginia Electric and Power Company | VA | Buckingham | Active | Generation Interconnection | Dominion | 682 | 0 | 51 |  | Capacity | Natural Gas |  | 6/1/2029 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-546 | TC2 | PHASE 1 | Bremo - Buckingham 230 kV |  | Mountain Pine Arvonia LLC | VA | Buckingham | Active | Generation Interconnection | Dominion | 79.8 | 79.8 | 47.8 |  | Capacity | Solar | 9/10/2021 | 2/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-451 | TC1 | PHASE 2 | Curdsville DP-Willis Mt. 115 kV |  | RWE LLC | VA | Buckingham | Withdrawn | Generation Interconnection | Dominion | 120 | 20 | 20 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-451/AG1-451_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-451/AG1-451_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-432 | TC1 | PHASE 1 | Curdsville DP-Willis Mt. 115 kV |  | ACE | VA | Buckingham | Withdrawn | Generation Interconnection | Dominion | 200 | 200 | 120 |  | Capacity | Solar | 9/30/2020 | 12/31/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-432/AG1-432_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-426 | TC1 | PHASE 1 | Bremo-Scottsville 138 kV |  | Riverstone Solar, LLC | VA | Buckingham | Withdrawn | Generation Interconnection | AEP | 149.5 | 0 | 17 |  | Capacity | Storage | 9/30/2020 | 10/31/2023 | [5 empty] | 8/2/2024 | 8/2/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-426/AG1-426_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-404 | TC1 | PHASE 3 | Gladys DP-Stonemill 69 kV | Pigeon Run Storage | Pigeon Run Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 60 | 0 | 0 |  | Energy | Storage | 3/31/2020 | 12/15/2022 | [5 empty] | 5/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-404/AF2-404_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-404/AF2-404_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-292 | TC1 | PHASE 1 | Grit DP-Perth 115 kV |  | Eno Solar, LLC | VA | Campbell | Withdrawn | Generation Interconnection | Dominion | 127 | 127 | 76.2 |  | Capacity | Solar | 3/29/2019 | 4/1/2021 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-292/AE2-292_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-283 | TC1 | PHASE 3 | Gladys-Stone Mill 69 kV |  | Gladys Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 53 | 53 | 28 |  | Capacity | Solar | 3/29/2019 | 9/30/2021 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-283/AE2-283_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-283/AE2-283_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-185 | TC1 | PHASE 3 | Gladys DP-Stonemill Switching Station 69 kV | Pigeon Run Solar | Pigeon Run Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 60 | 60 | 36 |  | Capacity | Solar | 3/18/2019 | 9/1/2020 | [5 empty] | 5/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-185/AE2-185_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-185/AE2-185_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-111 | TC2 | PHASE 1 | Perth 34.5 kV Substation (Circuit 408) |  | Koala Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 14.5 | 14.5 | 8.7 |  | Capacity | Solar | 1/29/2021 | 2/6/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-352 | TC2 | APPLICATION REVIEW | Red Eye 138 kV |  | Altavista Solar, LLC | VA | Campbell | Withdrawn | Generation Interconnection | AEP | 40 | 40 | 40 |  | Capacity | Storage | 9/10/2021 | 9/30/2023 | [5 empty] | 4/24/2025 | 3/28/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-056 | TC2 | PHASE 1 | Red House D.P. 115kV | Sugar Solar LLC | Sugar Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 100 | 100 | 68.5 |  | Capacity | Solar | 7/14/2021 | 11/15/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-098 | TC2 | PHASE 1 | Wolf Glade-West Carroll 138 kV |  | Pipers Gap Solar, LLC | VA | Carroll | Active | Generation Interconnection | AEP | 40 | 40 | 24 |  | Capacity | Solar,Storage,Hybrid | 7/30/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-603 | TC2 | PHASE 1 | Huffman 138 kV |  | Issa Solar LLC | VA | Carroll | Withdrawn | Generation Interconnection | AEP | 77 | 77 | 77 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 10/31/2024 | [5 empty] | 6/9/2025 | 6/9/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-639 | TC2 | PHASE 1 | Chickahominy 230 kV |  | ACE | VA | Charles City | Active | Generation Interconnection | Dominion | 340 | 20 | 20 |  | Capacity | Storage | 3/31/2021 | 4/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-042 | TC2 | PHASE 1 | Providence Forge-Turner 115kV | Stony Run Solar Project, LLC | Stony Run Solar Project, LLC | VA | Charles City | Active | Generation Interconnection | Dominion | 154 | 154 | 99.9 |  | Capacity | Solar | 6/25/2021 | 9/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-646 | TC2 | PHASE 1 | Chesterfield 230 kV |  | Pine Tree Power Management LLC | VA | Chesterfield | Active | Generation Interconnection | Dominion | 200 | 200 | 200 |  | Capacity | Storage | 3/31/2021 | 6/10/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-106 | TC2 | PHASE 1 | Winterpock 34.5kV | 360 Solar Center, LLC | 360 Solar Center, LLC | VA | Chesterfield | Active | Generation Interconnection | Dominion | 26 | 26 | 15.6 |  | Capacity | Solar | 8/4/2021 | 10/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-107 | TC2 | PHASE 1 | Winterpock 34.5kV | 360 Solar Center, LLC | 360 Solar Center, LLC | VA | Chesterfield | Active | Generation Interconnection | Dominion | 26 | 26 | 15.6 |  | Capacity | Solar | 8/4/2021 | 10/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-384 | TC2 | PHASE 1 | Chesterfield 230 kV |  | Virginia Electric and Power Company | VA | Chesterfield | Active | Generation Interconnection | Dominion | 60 | 60 | 24 |  | Capacity | Storage | 3/29/2021 | 12/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-088 | TC2 | PHASE 1 | Midlothian 230 kV |  | Hermon Energy Center, LLC | VA | Chesterfield | Active | Generation Interconnection | Dominion | 150 | 150 | 150 |  | Capacity | Storage | 1/26/2021 | 4/15/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-128 | TC1 | PHASE 3 | Chesterfield 230 kV |  | Virginia Electric and Power Company | VA | Chesterfield | Active | Generation Interconnection | Dominion | 569 | 569 | 569 |  | Capacity | Natural Gas | 9/18/2019 | 6/1/2023 |  |  |  | 3/31/2028 | 6/30/2028 | 2/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-128/AF1-128_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-128/AF1-128_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af1_128_csa.pdf | Posted
AG1-538 | TC1 | PHASE 1 | Remington-Gordonsville 230 kV |  | Longleaf Storage, LLC | VA | Culpeper | Withdrawn | Generation Interconnection | Dominion | 75 | 75 | 32 |  | Capacity | Storage | 9/30/2020 | 10/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-538/AG1-538_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-188 | TC2 | PHASE 1 | Farmville - Buckingham 230 kV |  | Bear Creek Solar, LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 140 | 140 | 89 |  | Capacity | Solar | 2/27/2021 | 3/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-151 | TC2 | PHASE 1 | Trices Lake - James River Tap 115 kV |  | Cumberland LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 100 | 100 | 60 |  | Capacity | Solar | 2/23/2021 | 2/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-583 | TC2 | PHASE 1 | Bremo - Cartersville 230 kV |  | Boston Hill Solar, LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 115 | 115 | 69 |  | Capacity | Solar | 3/31/2021 | 6/30/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-241 | TC2 | PHASE 1 | Cobbs Creek - James River Industrial 115kV | Energix Westmoreland LLC | Energix Westmoreland, LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 100 | 100 | 60 |  | Capacity | Solar | 9/9/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-439 | TC2 | PHASE 1 | Buckingham- Farmville 230kV | ACE Development Company, LLC | ACE | VA | Cumberland | Active | Generation Interconnection | Dominion | 85 | 85 | 51 |  | Capacity | Solar | 9/10/2021 | 9/1/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-440 | TC2 | PHASE 1 | Buckingham- Farmville 230kV | ACE Development Company, LLC | ACE | VA | Cumberland | Active | Generation Interconnection | Dominion | 85 | 0 | 34 |  | Capacity | Storage | 9/10/2021 | 9/1/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-072 | TC2 | PHASE 1 | Red Onion - VC5 69 kV |  | Bold Camp CF Solar, LLC | VA | Dickenson | Active | Generation Interconnection | AEP | 20 | 20 | 12 |  | Capacity | Solar | 7/29/2021 | 3/31/2024 | [5 empty] | 5/16/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-073 | TC2 | PHASE 1 | Red Onion - VC5 69 kV |  | Bold Camp CF Solar, LLC | VA | Dickenson | Active | Generation Interconnection | AEP | 40 | 20 | 12 |  | Capacity | Solar | 7/29/2021 | 3/31/2024 | [5 empty] | 5/16/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-449 | TC1 | PHASE 2 | Rawlings-Carson 500 kV |  | RWE LLC | VA | Dinwiddie | Withdrawn | Generation Interconnection | Dominion | 436 | 122 | 122 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-449/AG1-449_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-449/AG1-449_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-313 | TC1 | PHASE 2 | Carson-Rawlings 500 kV |  | RWE LLC | VA | Dinwiddie | Withdrawn | Generation Interconnection | Dominion | 314 | 314 | 188.4 |  | Capacity | Solar | 3/29/2019 | 9/15/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-313/AE2-313_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-313/AE2-313_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-266 | TC1 | PHASE 1 | Clubhouse-Sapony 230 kV |  | Invenergy | VA | Dinwiddie | Withdrawn | Generation Interconnection | Dominion | 223.5 | 74.5 | 74.5 |  | Capacity | Storage | 9/30/2019 | 12/31/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-266/AF1-266_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-393 | TC1 | PHASE 3 | Fort Pickett DP 34.5 kV | DW-Lew Jones Solar | DW-Lew Jones LLC | VA | Dinwiddie | Active | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar | 9/30/2020 | 3/1/2022 | [5 empty] | 5/14/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-393/AG1-393_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-393/AG1-393_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-197 | TC2 | APPLICATION REVIEW | Occoquan 230kV |  | Covanta LLC | VA | Fairfax | Withdrawn | Generation Interconnection | Dominion | 98 | 0 | 7.1 |  | Capacity | Biomass | 9/1/2021 | 8/20/2021 | [5 empty] | 3/31/2025 | 3/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-220 | TC2 | PHASE 1 | Remington CT 230 kV |  | Virginia Electric and Power Company | VA | Fauquier | Active | Generation Interconnection | Dominion | 100 | 0 | 60 |  | Capacity | Storage | 9/8/2021 | 12/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-086 | TC2 | PHASE 1 | Morrisville 230kV | Summersweet Energy Center, LLC | Summersweet Energy Center, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 90 | 90 | 90 |  | Capacity | Storage | 7/30/2021 | 7/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-087 | TC2 | PHASE 1 | Morrisville 230kV | Summersweet Energy Center, LLC | Summersweet Energy Center, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 110 | 20 | 20 |  | Capacity | Storage | 7/30/2021 | 7/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-088 | TC2 | PHASE 1 | Morrisville 230kV | Summersweet Energy Center, LLC | Summersweet Energy Center, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 130 | 20 | 20 |  | Capacity | Storage | 7/30/2021 | 7/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-089 | TC2 | PHASE 1 | Morrisville 230kV | Summersweet Energy Center, LLC | Summersweet Energy Center, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 150 | 20 | 20 |  | Capacity | Storage | 7/30/2021 | 7/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-345 | TC2 | PHASE 1 | Remington 324 34.5 kV |  | Bealeton Solar, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 14 | 14 | 8.4 |  | Capacity | Solar | 9/10/2021 | 3/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-684 | TC2 | PHASE 1 | Remington CT 230 kV |  | Virginia Electric and Power Company | VA | Fauquier | Active | Generation Interconnection | Dominion | 190 | 0 | 23 |  | Capacity | Natural Gas |  | 4/15/2028 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-685 | TC2 | PHASE 1 | Remington CT 230 kV |  | Virginia Electric and Power Company | VA | Fauquier | Active | Generation Interconnection | Dominion | 190 | 0 | 26 |  | Capacity | Natural Gas |  | 5/31/2028 | [5 empty] | 6/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-693 | TC2 | PHASE 1 | Remington CT 230 kV |  | Virginia Electric and Power Company | VA | Fauquier | Active | Generation Interconnection | Dominion | 190 | 0 | 20 |  | Capacity | Natural Gas |  | 4/15/2029 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-681 | TC2 | PHASE 1 | Cunningham 500 kV |  | Tenaska | VA | Fluvanna | Active | Generation Interconnection | Dominion | 1000 | 0 | 27.3 |  | Capacity | Natural Gas |  | 5/1/2026 | [5 empty] | 6/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-217 | TC2 | PHASE 1 | Kidds Store - Fork Union 115 kV II |  | Mountain Pine LLC | VA | Fluvanna | Active | Generation Interconnection | Dominion | 57 | 57 | 34.2 |  | Capacity | Solar | 9/9/2021 | 2/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-712 | TC2 | PHASE 1 | Cunningham 500 kV |  | Tenaska | VA | Fluvanna | Active | Generation Interconnection | Dominion | 776 | 776 | 611 |  | Capacity | Natural Gas |  | 5/30/2031 | [5 empty] | 5/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-723 | TC2 | PHASE 1 | Cunningham 500 kV |  | Tenaska | VA | Fluvanna | Active | Generation Interconnection | Dominion | 776 | 776 | 712 |  | Capacity | Natural Gas |  | 5/30/2031 | [5 empty] | 5/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-284 | TC1 | PHASE 1 | Fork Union 115 kV |  | Weber Solar, LLC | VA | Fluvanna | Withdrawn | Generation Interconnection | Dominion | 70 | 70 | 42 |  | Capacity | Solar | 9/28/2020 | 9/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-284/AG1-284_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-293 | TC1 | PHASE 1 | Kidds Store-Fort Union 115 kV |  | Kidds LLC | VA | Fluvanna | Withdrawn | Generation Interconnection | Dominion | 127.86 | 127.86 | 108.37 |  | Capacity | Solar,Storage,Hybrid | 9/30/2019 | 6/30/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-293/AF1-293_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-397 | TC1 | PHASE 1 | Fork Union-Mt. Eagle 230 kV |  | Kidds LLC | VA | Fluvanna | Withdrawn | Generation Interconnection | Dominion | 130 | 130 | 78 |  | Capacity | Solar,Storage,Hybrid | 4/1/2020 | 12/15/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-397/AF2-397_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-403 | TC1 | PHASE 1 | Shockoe DP-Chatham 69 kV | Shockoe Storage / Shockoe DP-Chatham 69 kV | Zenith Solar, LLC | VA | Fluvanna | Withdrawn | Generation Interconnection | Dominion | 60 | 0 | 8 |  | Capacity | Storage | 3/31/2020 | 12/15/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-403/AF2-403_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-403/AF2-403_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AH1-164 | TC2 | PHASE 1 | Oak Level - Tank Hill 138 kV |  | Robin Ridge Solar, LLC | VA | Franklin | Active | Generation Interconnection | AEP | 35 | 35 | 21 |  | Capacity | Solar | 8/31/2021 | 12/20/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-182 | TC2 | PHASE 1 | Doubs-Bismark 500 kV |  | ACE | VA | Frederick | Active | Generation Interconnection | Dominion | 200 | 200 | 133.3333 |  | Capacity | Solar,Storage,Hybrid | 2/26/2021 | 12/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-288 | TC2 | PHASE 1 | Stonewall 138 kV |  | Urban Grid LLC | VA | Frederick | Active | Generation Interconnection | APS | 150 | 150 | 150 |  | Capacity | Storage | 3/22/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-300 | TC2 | PHASE 1 | Meadow Brook 138 kV |  | Meadow Brook Storage, LLC | VA | Frederick | Active | Generation Interconnection | APS | 100 | 100 | 70 |  | Capacity | Storage | 3/23/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-144 | TC2 | PHASE 1 | Peter's Mountain 138 kV |  | Aries Solar Project LLC | VA | Giles | Active | Generation Interconnection | AEP | 120 | 120 | 50.4 |  | Capacity | Solar | 8/26/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-145 | TC2 | PHASE 1 | Peter's Mountain 138 kV |  | Aries Solar Project LLC | VA | Giles | Active | Generation Interconnection | AEP | 200 | 80 | 80 |  | Capacity | Storage | 8/26/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-355 | TC2 | PHASE 1 | Owl Trap Switching Station 115kV | Carvers Creek LLC | Carvers Creek LLC | VA | Gloucester | Withdrawn | Generation Interconnection | Dominion | 40 | 40 | 40 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 5/5/2025 | 3/25/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-201 | TC1 | PHASE 1 | Hayes-White Marsh 115 kV |  | TGE LLC | VA | Gloucester | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar,Storage,Hybrid | 9/24/2019 | 12/31/2021 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-201/AF1-201_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-170 | TC2 | PHASE 1 | Columbia DP 115kV | Horsepen Creek Solar I | Horsepen Creek Solar, LLC | VA | Goochland | Active | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar | 8/27/2021 | 12/20/2024 | [5 empty] | 5/5/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-737 | TC2 | RRI APPLICATION REVIEW |  |  | Melrose Energy Center, LLC | VA | Goochland | Withdrawn | Generation Interconnection | Dominion | 200 | 200 | 200 |  | Capacity | Storage |  | 4/21/2029 | [5 empty] | 5/5/2025 | 4/18/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-677 | TC2 | PHASE 1 | Rogers Road 500 kV |  | Virginia Electric and Power Company | VA | Greensville | Active | Generation Interconnection | Dominion | 1756 | 0 | 67 |  | Capacity | Natural Gas |  | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-250 | TC1 | PHASE 2 | Purdy Sw.-Reams 115 kV |  | Wyatt Mill Solar, LLC | VA | Greensville | Withdrawn | Generation Interconnection | Dominion | 82.5 | 82.5 | 54 |  | Capacity | Solar | 3/26/2019 | 9/30/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-250/AE2-250_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-250/AE2-250_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-299 | TC1 | PHASE 3 | Fields 34.5 kV | Jarratt Energy Facility 2 | Jarratt LLC | VA | Greensville | Active | Generation Interconnection | Dominion | 18 | 18 | 10.8 |  | Capacity | Solar | 3/30/2020 | 12/12/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-299/AF2-299_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-299/AF2-299_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-160 | TC1 | PHASE 1 | Rogers Road 500 kV |  | Virginia Electric and Power Company | VA | Greensville | Withdrawn | Generation Interconnection | Dominion | 75 | 75 | 30 |  | Capacity | Storage | 9/11/2020 | 12/1/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-160/AG1-160_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-075 | TC1 | PHASE 1 | Purdy-Sapony 115 kV |  | Jarratt LLC | VA | Greensville | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 93.2 |  | Capacity | Solar | 7/31/2020 | 10/15/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-075/AG1-075_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-075/AG1-075_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-369 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Virginia Electric and Power Company | VA | Greensville | Active | Generation Interconnection | Dominion | 86 | 86 | 51.6 |  | Capacity | Solar | 3/26/2021 | 12/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-541 | TC2 | PHASE 1 | Perth - Crystal Hill 115 kV |  | Slick Rock Solar LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 65 | 65 | 39 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/3/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-260 | TC2 | APPLICATION REVIEW | Crystal Hill - Perth 115 kV |  | Virginia Electric and Power Company | VA | Halifax | Withdrawn | Generation Interconnection | Dominion | 149 | 149 | 89.4 |  | Capacity | Solar | 3/18/2021 | 12/1/2025 | [5 empty] | 4/22/2025 | 3/31/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-262 | TC2 | PHASE 1 | Dryburg 115 kV |  | Staunton Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 47 | 11 | 6.6 |  | Capacity | Solar | 3/18/2021 | 12/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-270 | TC2 | PHASE 1 | Clover 230 kV |  | Clover Storage, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 150 | 150 | 105 |  | Capacity | Storage | 3/19/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-112 | TC2 | PHASE 1 | Perth 34.5 kV Substation (Circuit 404) |  | Kangaroo Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 15.2 | 15.2 | 9.12 |  | Capacity | Solar | 1/29/2021 | 3/24/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-105 | TC1 | PHASE 3 | Mount Laurel-Barnes Junction 115 kV | Clover Creek Solar | Virginia Electric and Power Company | VA | Halifax | Active | Generation Interconnection | Dominion | 90 | 90 | 54 |  | Capacity | Solar | 8/27/2020 | 12/1/2024 | [5 empty] | 5/22/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-105/AG1-105_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-105/AG1-105_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-342 | TC1 | PHASE 3 | Dryburg 115 kV |  | Staunton Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 36 | 36 | 21.6 |  | Capacity | Solar | 9/30/2020 | 12/1/2023 | [5 empty] | 2/7/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-342/AG1-342_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-342/AG1-342_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-297 | TC1 | PHASE 3 | Sedge Hill 115 kV |  | Sedge Hill Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 80 | 80 | 48 |  | Capacity | Solar | 3/28/2020 | 3/12/2022 | [5 empty] | 2/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-297/AF2-297_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-297/AF2-297_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-042 | TC1 | PHASE 3 | Clover-Rawlings 500 kV | Randolph Solar | Virginia Electric and Power Company | VA | Halifax | Active | Generation Interconnection | Dominion | 500 | 500 | 300 |  | Capacity | Solar | 12/9/2019 | 12/31/2022 | [5 empty] | 6/3/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-042/AF2-042_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-042/AF2-042_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-343 | TC2 | PHASE 1 | Crystal Hill DP- Perth 115kV | CEP Solar, LLC | Boxwood Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 69 | 69 | 41.4 |  | Capacity | Solar | 9/10/2021 | 9/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-092 | TC2 | PHASE 1 | SedgeHill - Person 230 kV |  | Scarlet Oak Solar, LLC | VA | Halifax | Withdrawn | Generation Interconnection | Dominion | 90 | 90 | 54 |  | Capacity | Solar,Storage,Hybrid | 7/30/2021 | 6/1/2025 | [5 empty] | 5/7/2025 | 5/7/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-399 | TC2 | PHASE 1 | North Doswell 12.5 kV |  | Ameresco Inc | VA | Hanover | Active | Generation Interconnection | Dominion | 9.87 | 9.87 | 1.48 |  | Capacity | Solar | 9/22/2021 | 10/2/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-679 | TC2 | PHASE 1 | Four Rivers 230 kV |  | Doswell Limited Partnership | VA | Hanover | Active | Generation Interconnection | Dominion | 1016 | 20 | 20 |  | Capacity | Natural Gas |  | 5/31/2028 | [5 empty] | 5/15/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-558 | TC2 | PHASE 1 | Four Rivers 230kV | Doswell Limited Partnership | Doswell Limited Partnership | VA | Hanover | Active | Generation Interconnection | Dominion | 996 | 250 | 250 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-035 | TC1 | PHASE 3 | St. Johns 115 kV | Anna River Solar | Anna River Solar, LLC | VA | Hanover | Active | Generation Interconnection | Dominion | 72 | 72 | 48 |  | Capacity | Solar | 11/27/2019 | 10/27/2023 | [5 empty] | 6/5/2025 |  | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-035/AF2-035_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-035/AF2-035_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-240 | TC2 | PHASE 1 | Old Church 34.5 kV |  | Mechanicsville Solar, LLC | VA | Hanover | Active | Generation Interconnection | Dominion | 25 | 0 | 0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-193 | TC2 | PHASE 1 | Turner 34.5 kV |  | Virginia Electric and Power Company | VA | Henrico | Active | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar | 2/27/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-531 | TC1 | PHASE 1 | Poolesville-Winchester 230 kV |  | TCE Virginia Development, LLC | VA | Isle of Wight | Withdrawn | Generation Interconnection | Dominion | 54 | 54 | 32.4 |  | Capacity | Solar | 9/30/2020 | 12/12/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-531/AG1-531_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-216 | TC2 | PHASE 1 | Smithfield-Surry 230 kV |  | Mountain Pine LLC | VA | Isle of Wight | Active | Generation Interconnection | Dominion | 99 | 99 | 79.2 |  | Capacity | Solar,Storage,Hybrid | 9/8/2021 | 2/1/2025 | [5 empty] | 5/5/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-185 | TC2 | APPLICATION REVIEW | Benn's Church - Smithfield 34.5 kV |  | Prairie Solar, LLC | VA | Isle of Wight | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar | 8/31/2021 | 12/31/2022 | [5 empty] | 3/31/2025 | 2/25/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-716 | TC2 | PHASE 1 | Surry-Skiffes Creek 500kV |  | Cardinal Energy Storage East, LLC | VA | James City | Active | Generation Interconnection | Dominion | 650 | 650 | 650 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-726 | TC2 | PHASE 1 | Surry-Skiffes Creek 500kV |  | Cardinal Energy Storage East, LLC | VA | James City | Active | Generation Interconnection | Dominion | 600 | 600 | 600 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-397 | TC2 | PHASE 1 | Shacklesfords 34.5 kV |  | Ameresco Inc | VA | King and Queen | Active | Generation Interconnection | Dominion | 19.818 | 19.818 | 2.97 |  | Capacity | Solar | 9/10/2021 | 10/2/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-124 | TC2 | PHASE 1 | Shackleford-Harmony 115 kV |  | Virginia Electric and Power Company | VA | King and Queen | Active | Generation Interconnection | Dominion | 149.9 | 0 | 33.34 |  | Capacity | Solar | 1/29/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-607 | TC2 | PHASE 1 | St. Johns - Dunbrook 34.5 kV |  | Cauthornville PV I, LLC | VA | King and Queen | Active | Generation Interconnection | Dominion | 20 | 20 | 12.74 |  | Capacity | Solar | 3/31/2021 | 11/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-020 | TC2 | PHASE 1 | Arnolds Corner 34.5 kV | Arnolds Corner Energy Storage | Arnold Corner Energy Storage 1 LLC | VA | King George | Active | Generation Interconnection | Dominion | 7 | 7 | 2.8 |  | Capacity | Storage | 10/23/2020 | 12/30/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-019 | TC1 | PHASE 1 | Arnold's Corner-Dahlgren 230 kV |  | Harwood Power, LLC | VA | King George | Withdrawn | Generation Interconnection | Dominion | 200 | 100 | 100 |  | Capacity | Storage | 5/20/2020 | 10/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-019/AG1-019_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-134 | TC1 | PHASE 1 | Kings Dominion DP 115 kV |  | Virginia Electric and Power Company | VA | King William | Withdrawn | Generation Interconnection | Dominion | 100 | 100 | 60 |  | Capacity | Solar | 9/2/2020 | 12/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-134/AG1-134_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-146 | TC1 | PHASE 3 | Garner DP-Lancaster 115 kV |  | Virginia Electric and Power Company | VA | Lancaster | Active | Generation Interconnection | Dominion | 30 | 30 | 18 |  | Capacity | Solar | 9/9/2020 | 12/1/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-146/AG1-146_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-146/AG1-146_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-147 | TC1 | PHASE 3 | Garner DP-Lancaster 115 kV |  | Virginia Electric and Power Company | VA | Lancaster | Active | Generation Interconnection | Dominion | 100 | 70 | 42 |  | Capacity | Solar | 9/9/2020 | 12/1/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-147/AG1-147_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-147/AG1-147_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-005 | TC2 | PHASE 1 | Garner-Lancaster 115 kV |  | Waller Solar I, LLC | VA | Lancaster | Active | Generation Interconnection | Dominion | 196 | 20 | 8.4 |  | Capacity | Solar | 10/2/2020 | 12/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-215 | TC2 | PHASE 1 | Garner DP-Lancaster 115 kV |  | Waller Solar I, LLC | VA | Lancaster | Active | Generation Interconnection | Dominion | 196 | 0 | 36.92 |  | Capacity | Solar | 3/9/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-366 | TC2 | PHASE 1 | Garner Delivery Point - Lancaster 115 kV |  | Virginia Electric and Power Company | VA | Lancaster | Active | Generation Interconnection | Dominion | 50 | 50 | 20 |  | Capacity | Storage | 3/26/2021 | 12/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-223 | TC2 | PHASE 1 | Poland Rd-Runway DP 230 kV |  | Virginia Electric and Power Company | VA | Loudoun | Active | Generation Interconnection | Dominion | 150 | 0 | 20 |  | Capacity | Storage | 9/8/2021 | 12/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-125 | TC2 | PHASE 1 | Sycoline 34.5kV | Evergreen Energy Center, LLC | Evergreen Energy Center, LLC | VA | Loudoun | Active | Generation Interconnection | Dominion | 20 | 20 | 0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-727 | TC2 | PHASE 1 | Brambleton-Goose Creek 500kV |  | Cardinal Energy Storage East, LLC | VA | Loudoun | Active | Generation Interconnection | Dominion | 425 | 425 | 425 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-729 | TC2 | PHASE 1 | Ocean Court 230 kV |  | GSP Sterling Project I, LLC | VA | Loudoun | Active | Generation Interconnection | Dominion | 100 | 100 | 100 |  | Capacity | Storage |  | 5/26/2028 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-012 | TC2 | PHASE 1 | Louisa - North Anna 230 kV |  | Two Oaks LLC | VA | Louisa | Active | Generation Interconnection | Dominion | 50 | 50 | 20 |  | Capacity | Storage | 4/19/2021 | 3/29/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-208 | TC2 | PHASE 1 | Greenwood DP - St. Johns DP 115 kV |  | Busbees Solar, LLC | VA | Louisa | Active | Generation Interconnection | Dominion | 70 | 70 | 44.47 |  | Capacity | Solar | 3/5/2021 | 6/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-305 | TC1 | PHASE 2 | Louisa-North Anna 230 kV |  | Two Oaks LLC | VA | Louisa | Withdrawn | Generation Interconnection | Dominion | 63 | 63 | 37.8 |  | Capacity | Solar | 9/29/2020 | 7/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-305/AG1-305_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-305/AG1-305_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-037 | TC1 | PHASE 2 | Louisa-North Anna 230 kV |  | AURA POWER DEVELOPMENTS (USA), LLC | VA | Louisa | Withdrawn | Generation Interconnection | Dominion | 94 | 94 | 56.4 |  | Capacity | Solar | 11/29/2019 | 7/1/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-037/AF2-037_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-037/AF2-037_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-063 | TC1 | PHASE 2 | Louisa-North Anna 230 kV |  | AURA POWER DEVELOPMENTS (USA), LLC | VA | Louisa | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 1/29/2020 | 2/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-063/AF2-063_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-063/AF2-063_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-301 | TC1 | PHASE 1 | Louisa-South Anna 230 kV |  | Invenergy | VA | Louisa | Withdrawn | Generation Interconnection | Dominion | 117 | 117 | 70 |  | Capacity | Solar | 9/30/2019 | 12/31/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-301/AF1-301_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-213 | TC2 | PHASE 1 | Gary D.P Tap - Gary D.P 115 kV |  | Virginia Electric and Power Company | VA | Lunenburg | Active | Generation Interconnection | Dominion | 80 | 80 | 48 |  | Capacity | Solar | 3/8/2021 | 12/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-171 | TC2 | PHASE 1 | Lunenburg-Nutbush 115 kV |  | Couch Creek Solar LLC | VA | Lunenburg | Active | Generation Interconnection | Dominion | 60 | 60 | 36 |  | Capacity | Solar | 2/26/2021 | 7/3/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-396 | TC2 | PHASE 1 | Gary 24.94 kV |  | Ameresco Inc | VA | Lunenburg | Active | Generation Interconnection | Dominion | 12 | 12 | 1.8 |  | Capacity | Solar | 9/10/2021 | 10/2/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-378 | TC2 | PHASE 1 | Lunenburg- Butcher Creek 115kV | Victoria PV I, LLC | Victoria PV I, LLC | VA | Lunenburg | Withdrawn | Generation Interconnection | Dominion | 51 | 51 | 30.6 |  | Capacity | Solar | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 | 4/16/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-659 | TC2 | PHASE 1 | Kerr Dam – Hawtree 115 kV |  | Bracey PV I, LLC | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 80 | 80 | 48 |  | Capacity | Solar | 3/31/2021 | 7/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-341 | TC2 | PHASE 1 | Ridge Road 115 kV |  | Mighty Blue LLC | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 50 | 50 | 20 |  | Capacity | Storage | 3/25/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-631 | TC2 | PHASE 1 | Boydton Plank Road 115 kV |  | ACE | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 3/31/2021 | 4/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-053 | TC1 | PHASE 1 | Kerr Dam-Ridge Road 115 kV |  | RWE LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 110 | 20 | 20 |  | Capacity | Storage | 2/1/2019 | 9/15/2021 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-053/AE2-053_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE1-148 | TC1 | PHASE 3 | Kerr Dam-Ridge Rd 115 kV | Antlers Road Solar | RWE LLC | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 90 | 90 | 54 |  | Capacity | Solar | 9/24/2018 | 12/1/2021 | [5 empty] | 5/21/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE1-148/AE1-148_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-148/AE1-148_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-098 | TC1 | PHASE 3 | Briery-Clover 230 kV | Finneywood Solar | Virginia Electric and Power Company | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 107 | 107 | 64.2 |  | Capacity | Solar | 8/18/2020 | 12/1/2024 | [5 empty] | 6/5/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-098/ag1-098_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-098/AG1-098_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-427 | TC1 | PHASE 2 | Chase City-Drakes Branch 115 kV |  | ACE | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 118.56 | 118.56 | 71.136 |  | Capacity | Solar | 9/30/2020 | 12/31/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-427/AG1-427_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-427/AG1-427_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-440 | TC1 | PHASE 1 | Palmer Springs 115 kV |  | RWE LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 75 | 75 | 45 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-440/AG1-440_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-441 | TC1 | PHASE 1 | Palmer Springs 115 kV |  | RWE LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 75 | 75 | 45 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-441/AG1-441_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-445 | TC1 | PHASE 1 | Palmer Springs 115 kV |  | Fitzsimons Solar, LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 101 | 26 | 26 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 11/8/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-445/AG1-445_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-446 | TC1 | PHASE 1 | Palmer Springs 115 kV |  | RWE LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 101 | 26 | 26 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-446/AG1-446_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-518 | TC2 | PHASE 1 | Tech Drive 138 kV |  | Delorean Power LLC | VA | Montgomery | Active | Generation Interconnection | AEP | 80 | 80 | 32 |  | Capacity | Storage | 3/31/2021 | 1/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-124 | TC1 | PHASE 3 | Gladstone 138 kV |  | Wild Rose Solar Project, LLC | VA | Nelson | Active | Generation Interconnection | AEP | 90 | 90 | 53.01 |  | Capacity | Solar | 8/31/2020 | 12/1/2024 | [5 empty] | 3/5/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-124/AG1-124_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-124/AG1-124_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-030 | TC1 | PHASE 1 | Victoria DP-Martin DP 115 kV |  | Dickerson Creek Solar LLC | VA | Nottoway | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 6/9/2020 | 1/1/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-030/AG1-030_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-166 | TC1 | PHASE 3 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Active | Generation Interconnection | Dominion | 20 | 20 | 6 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-166/AG1-166_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-166/AG1-166_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-167 | TC1 | PHASE 3 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Active | Generation Interconnection | Dominion | 35 | 15 | 4.5 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-167/AG1-167_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-167/AG1-167_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-168 | TC1 | PHASE 3 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Active | Generation Interconnection | Dominion | 50 | 15 | 4.5 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 4/22/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-168/AG1-168_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-168/AG1-168_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-169 | TC1 | PHASE 2 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Withdrawn | Generation Interconnection | Dominion | 15 | 15 | 4.5 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-169/AG1-169_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-169/AG1-169_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-170 | TC1 | PHASE 2 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Withdrawn | Generation Interconnection | Dominion | 10 | 10 | 3 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-170/AG1-170_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-170/AG1-170_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-288 | TC1 | PHASE 1 | Lake of the Woods DP-Wilderness DP 115 kV |  | Locust Grove Solar, LLC | VA | Orange | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 96.59 |  | Capacity | Solar | 9/28/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-288/AG1-288_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-289 | TC1 | PHASE 1 | Lake of the Woods DP-Wilderness DP 115 kV |  | Locust Grove Solar, LLC | VA | Orange | Withdrawn | Generation Interconnection | Dominion | 150 | 0 | 53.41 |  | Capacity | Storage | 9/28/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-289/AG1-289_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-502 | TC1 | PHASE 2 | Oak Green 115 kV |  | Oak Green Solar LLC | VA | Orange | Withdrawn | Generation Interconnection | Dominion | 80 | 80 | 64 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/30/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-502/AG1-502_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-503 | TC1 | PHASE 2 | Oak Green 115 kV |  | Oak Green Solar LLC | VA | Orange | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 16 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/30/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-503/AG1-503_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AH1-676 | TC2 | PHASE 1 | Gordonsville 230 kV |  | Invenergy | VA | Orange | Active | Generation Interconnection | Dominion | 1294.6 | 1294.6 | 1275.9 |  | Capacity | Natural Gas |  | 5/31/2031 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-447 | TC2 | APPLICATION REVIEW | Axton – Danville #2 138 kV |  | Cascade Energy Storage, LLC | VA | Pittsylvania | Withdrawn | Generation Interconnection | AEP | 60 | 60 | 36 |  | Capacity | Storage | 9/10/2021 | 12/2/2024 | [5 empty] | 3/20/2025 | [9 empty] | Not Started |  | Not Started
AH1-314 | TC2 | PHASE 1 | East Danville 138 kV |  | Pittsylvania Energy Storage LLC | VA | Pittsylvania | Active | Generation Interconnection | AEP | 100 | 100 | 100 |  | Capacity | Storage | 9/11/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-187 | TC1 | PHASE 3 | Shockoe DP-Chatham 69 kV |  | Zenith Solar, LLC | VA | Pittsylvania | Active | Generation Interconnection | Dominion | 60 | 60 | 36 |  | Capacity | Solar | 3/18/2019 | 9/1/2020 | [5 empty] | 5/19/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-187/AE2-187_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-187/AE2-187_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-291 | TC1 | PHASE 3 | Grit DP-Perth 115 kV | Hillandale Solar | Hillandale Solar, LLC | VA | Pittsylvania | Active | Generation Interconnection | Dominion | 102 | 102 | 61.2 |  | Capacity | Solar | 3/29/2019 | 4/1/2021 | [5 empty] | 5/19/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-291/AE2-291_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-291/AE2-291_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-152 | TC2 | PHASE 1 | Banister-Bear Skin 138 kV |  | Virginia Electric and Power Company | VA | Pittsylvania | Active | Generation Interconnection | AEP | 131 | 131 | 79 |  | Capacity | Solar | 2/23/2021 | 2/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-272 | TC2 | PHASE 1 | Berry Hill 138 kV |  | Tupelo Storage, LLC | VA | Pittsylvania | Active | Generation Interconnection | AEP | 55 | 55 | 21.3 |  | Capacity | Storage | 3/19/2021 | 10/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-539 | TC1 | PHASE 1 | Grit DP-Perth 115 kV |  | Sourbark Storage, LLC | VA | Pittsylvania | Withdrawn | Generation Interconnection | Dominion | 75 | 75 | 32 |  | Capacity | Storage | 9/30/2020 | 10/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-539/AG1-539_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-547 | TC1 | PHASE 1 | Mount Airy-Chatham 69 kV |  | Curie Solar, LLC | VA | Pittsylvania | Withdrawn | Generation Interconnection | Dominion | 50 | 50 | 32.54 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 10/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-547/AG1-547_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-071 | TC2 | PHASE 1 | Midlothian 34.5 kV |  | Virginia Electric and Power Company | VA | Powhatan | Active | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar | 7/29/2021 | 7/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-377 | TC2 | PHASE 1 | Clover- Farmville 230kV | Keysville PV I, LLC | Keysville PV I, LLC | VA | Prince Edward | Active | Generation Interconnection | Dominion | 186 | 186 | 111.6 |  | Capacity | Solar | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-731 | TC2 | RRI APPLICATION REVIEW |  |  | Cumberland LLC | VA | Prince Edward | Withdrawn | Generation Interconnection | Dominion | 107 | 107 | 107 |  | Capacity | Storage |  | 5/5/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-750 | TC2 | RRI APPLICATION REVIEW |  |  | Pine Lake Solar LLC | VA | Prince Edward | Withdrawn | Generation Interconnection | Dominion | 100 | 100 | 100 |  | Capacity | Storage |  | 11/10/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG2-198 | TC2 | PHASE 1 | Briery - Finneywood 230 kV |  | Gabriel LLC | VA | Prince Edward | Active | Generation Interconnection | Dominion | 80 | 80 | 48 |  | Capacity | Solar | 2/28/2021 | 2/25/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-566 | TC2 | PHASE 1 | Briery - Finneywood 230 kV |  | Gabriel LLC | VA | Prince Edward | Active | Generation Interconnection | Dominion | 110 | 30 | 12 |  | Capacity | Storage | 3/31/2021 | 3/29/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-171 | TC1 | PHASE 1 | Madisonville 115 kV |  | CPV LLC | VA | Prince Edward | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 90 |  | Capacity | Solar | 3/19/2020 | 3/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-171/AF2-171_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-171/AF2-171_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-095 | TC2 | PHASE 1 | Hopewell 34.5 kV (Circuit 313) |  | Virginia Electric and Power Company | VA | Prince George | Active | Generation Interconnection | Dominion | 18 | 18 | 10.8 |  | Capacity | Solar | 1/28/2021 | 12/8/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-093 | TC2 | PHASE 1 | Colonial Trail-Hopewell 230 kV |  | Admiral Solar LLC | VA | Prince George | Active | Generation Interconnection | Dominion | 100 | 100 | 100 |  | Capacity | Solar,Storage,Hybrid | 1/26/2021 | 12/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-732 | TC2 | RRI APPLICATION REVIEW |  |  | SolAmerica Energy, LLC | VA | Prince George | Withdrawn | Generation Interconnection | Dominion | 50 | 50 | 50 |  | Capacity | Storage |  | 4/30/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-741 | TC2 | RRI APPLICATION REVIEW |  |  | Virginia Electric and Power Company | VA | Prince William | Withdrawn | Generation Interconnection | Dominion | 115 | 115 | 97 |  | Capacity | Natural Gas |  | 12/31/2030 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-696 | TC2 | PHASE 1 | Possum Point 230kV |  | Virginia Electric and Power Company | VA | Prince William | Active | Generation Interconnection | Dominion | 668 | 0 | 94 |  | Capacity | Natural Gas |  | 6/1/2030 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-127 | TC2 | PHASE 1 | Railroad 34.5kV | Railroad Energy Center, LLC | Railroad Energy Center, LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 20 | 20 | 0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-128 | TC2 | PHASE 1 | Railroad 34.5kV | Bethlehem Energy Center, LLC | Bethlehem Energy Center, LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 20 | 20 | 0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-124 | TC2 | PHASE 1 | Vint Hill 34.5kV | Reid Energy Center, LLC | Reid Energy Center, LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 20 | 20 | 0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-284 | TC2 | PHASE 1 | Catharpin 230 kV |  | Urban Grid LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 150 | 150 | 150 |  | Capacity | Storage | 3/22/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-304 | TC2 | PHASE 1 | Liberty 230 kV |  | Urban Grid LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 150 | 150 | 150 |  | Capacity | Storage | 3/23/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-269 | TC2 | PHASE 1 | Claytor 138 kV |  | Claytor Energy Storage, LLC | VA | Pulaski | Active | Generation Interconnection | AEP | 50 | 50 | 50 |  | Capacity | Storage | 9/9/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-536 | TC1 | PHASE 3 | Garner-Northern Neck 115 kV |  | Virginia Electric and Power Company | VA | Richmond | Active | Generation Interconnection | Dominion | 75 | 75 | 32 |  | Capacity | Storage | 9/30/2020 | 10/1/2024 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-536/AG1-536_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-536/AG1-536_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-120 | TC1 | PHASE 3 | Garner-Northern Neck 115 kV |  | Virginia Electric and Power Company | VA | Richmond | Active | Generation Interconnection | Dominion | 62 | 62 | 37.2 |  | Capacity | Solar | 2/28/2020 | 12/1/2023 |  |  |  | 12/1/2025 | 2/6/2026 | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-120/AF2-120_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-120/AF2-120_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af2_120_csa.pdf | Posted
AG1-135 | TC1 | PHASE 3 | Garner-Lancaster 115 kV |  | Virginia Electric and Power Company | VA | Richmond | Active | Generation Interconnection | Dominion | 60 | 60 | 36 |  | Capacity | Solar | 9/3/2020 | 12/1/2024 |  |  |  | 12/1/2025 | 2/1/2026 | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-135/AG1-135_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-135/AG1-135_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/ag1_135_csa.pdf | Posted
AG2-310 | TC2 | PHASE 1 | Matt Funk 138 kV |  | Matt Funk Storage, LLC | VA | Roanoke | Active | Generation Interconnection | AEP | 100 | 100 | 70 |  | Capacity | Storage | 3/23/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-556 | TC1 | PHASE 1 | Lexington 115 kV |  | Sand Dragon Energy LLC | VA | Rockbridge | Withdrawn | Generation Interconnection | Dominion | 100 | 100 | 100 |  | Capacity | Storage | 9/30/2020 | 6/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-556/AG1-556_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-080 | TC2 | PHASE 1 | Lexington 115 kV | Sand Dragon Energy | Sand Dragon Energy LLC | VA | Rockbridge | Active | Generation Interconnection | Dominion | 100 | 100 | 78 |  | Capacity | Storage | 1/21/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-528 | TC2 | PHASE 1 | Bustleburg Tap - Fairfield DP 115 kV |  | Sunday Solar LLC | VA | Rockbridge | Withdrawn | Generation Interconnection | Dominion | 140 | 140 | 72.8 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 10/31/2024 | [5 empty] | 6/6/2025 | 6/6/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-542 | TC2 | APPLICATION REVIEW | North Shenandoah – Merck 115 kV |  | Knight Energy Center, LLC | VA | Rockingham | Withdrawn | Generation Interconnection | Dominion | 70 | 70 | 42 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/3/2024 | [5 empty] | 3/31/2025 | [9 empty] | Not Started |  | Not Started
AG1-151 | TC1 | PHASE 1 | Endless Caverns 115 kV |  | Prospect Power, LLC | VA | Rockingham | Withdrawn | Generation Interconnection | Dominion | 300 | 100 | 100 |  | Capacity | Storage | 9/10/2020 | 10/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-151/AG1-151_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-346 | TC1 | PHASE 2 | Mount Jackson DP 115 kV |  | Ginger Gold Solar LLC | VA | Shenandoah | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar | 9/30/2020 | 12/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-346/AG1-346_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-346/AG1-346_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-086 | TC2 | PHASE 1 | Mt. Jackson DP-Mt. Jackson 115 kV | OFW Solar Farm | OFW Solar Farm, LLC | VA | Shenandoah | Active | Generation Interconnection | Dominion | 75 | 75 | 45 |  | Capacity | Solar,Storage,Hybrid | 1/22/2021 | 12/30/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-179 | TC2 | PHASE 1 | Edinburg - Woodstock DP 34.5 kV |  | Valley Overlook Solar, LLC | VA | Shenandoah | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar | 8/31/2021 | 12/31/2022 | [5 empty] | 5/5/2025 | 4/9/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-743 | TC2 | RRI APPLICATION REVIEW |  |  | Lighthouse | VA | Shenandoah | Withdrawn | Generation Interconnection | APS | 333.78 | 333.78 | 255 |  | Capacity | Natural Gas |  | 4/30/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG2-360 | TC2 | PHASE 1 | Broadford 138 kV |  | Laurel Creek Energy Storage LLC | VA | Smyth | Active | Generation Interconnection | AEP | 250 | 250 | 250 |  | Capacity | Storage | 3/26/2021 | 11/15/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-343 | TC1 | PHASE 2 | Boykins-Murphy 115 kV |  | White Oak Solar Facility LLC | VA | Southampton | Withdrawn | Generation Interconnection | Dominion | 62.5 | 62.5 | 35 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-343/AG1-343_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-343/AG1-343_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-394 | TC1 | PHASE 3 | Boykins 34.5 kV |  | SH-Mehrrin LLC | VA | Southampton | Active | Generation Interconnection | Dominion | 14.2 | 14.2 | 5 |  | Capacity | Solar | 9/30/2020 | 3/1/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-394/AG1-394_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-394/AG1-394_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-133 | TC1 | PHASE 1 | North Anna-Ladysmith 500 kV |  | Virginia Electric and Power Company | VA | Spotsylvania | Withdrawn | Generation Interconnection | Dominion | 128 | 128 | 76.8 |  | Capacity | Solar | 9/2/2020 | 12/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-133/AG1-133_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-251 | TC2 | PHASE 1 | Todds Tavern- Spotsylvania/Goldsdale 115kV | Tavern Energy LLC | Tavern Energy, LLC | VA | Spotsylvania | Active | Generation Interconnection | Dominion | 50 | 50 | 50 |  | Capacity | Storage | 9/9/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-263 | TC2 | PHASE 1 | Chancellor 115 kV |  | Scarlet Energy Storage LLC | VA | Spotsylvania | Active | Generation Interconnection | Dominion | 200 | 200 | 200 |  | Capacity | Storage | 9/9/2021 | 6/30/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-661 | TC2 | PHASE 1 | Hopewell - Colonial Trail 230 kV |  | Wild Indigo Energy Center LLC | VA | Surry | Active | Generation Interconnection | Dominion | 150 | 0 | 20 |  | Capacity | Storage | 3/31/2021 | 10/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-324 | TC2 | PHASE 1 | Colonial Trail – Surry 230 kV |  | Invenergy | VA | Surry | Active | Generation Interconnection | Dominion | 80 | 80 | 48 |  | Capacity | Solar | 9/10/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-717 | TC2 | PHASE 1 | Gravel Neck 230 kV |  | Virginia Electric and Power Company | VA | Surry | Active | Generation Interconnection | Dominion | 453 | 85 | 92.7 |  | Capacity | Natural Gas |  | 12/31/2031 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-011 | TC1 | PHASE 1 | Colonial Trail 230 kV |  | Urban Grid LLC | VA | Surry | Withdrawn | Generation Interconnection | Dominion | 160 | 160 | 160 |  | Capacity | Storage | 5/8/2020 | 6/30/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-011/AG1-011_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-174 | TC1 | PHASE 1 | Hopewell-Surry 230 kV |  | SR-Colonial Trail LLC | VA | Surry | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 12 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-174/AG1-174_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-065 | TC1 | PHASE 1 | Surry-Hopewell 230 kV |  | Violet Wood Solar LLC | VA | Surry | Withdrawn | Generation Interconnection | Dominion | 300 | 150 | 76.5 |  | Capacity | Solar | 1/30/2020 | 10/21/2021 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-065/AF2-065_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-270 | TC1 | PHASE 1 | Hopewell-Surry 230 kV |  | Violet Wood Solar LLC | VA | Surry | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 150 |  | Capacity | Solar,Storage,Hybrid | 3/28/2019 | 9/29/2021 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-270/AE2-270_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-178 | TC1 | PHASE 1 | Carson-Suffolk 500 kV |  | Cabin Point Solar, LLC | VA | Sussex | Withdrawn | Generation Interconnection | Dominion | 500 | 500 | 324.94 |  | Capacity | Solar | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-178/AG1-178_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-179 | TC1 | PHASE 1 | Brunswick-Gasburg 69 kV |  | Merchant Solar, LLC | VA | Sussex | Withdrawn | Generation Interconnection | Dominion | 50 | 50 | 33.66 |  | Capacity | Solar | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-179/AG1-179_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-180 | TC1 | PHASE 1 | Brunswick-Gasburg 69 kV |  | Merchant Solar, LLC | VA | Sussex | Withdrawn | Generation Interconnection | Dominion | 50 | 0 | 16.4 |  | Capacity | Storage | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-180/AG1-180_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-184 | TC1 | PHASE 1 | Carson-Suffolk 500 kV |  | Cabin Point Solar, LLC | VA | Sussex | Withdrawn | Generation Interconnection | Dominion | 500 | 0 | 175.06 |  | Capacity | Storage | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-184/AG1-184_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-338 | TC2 | PHASE 1 | Rogers Road - Carson 500 kV |  | Cassius Blue Solar LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 40 | 40 | 40 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-339 | TC2 | PHASE 1 | Rogers Road - Carson 500 kV |  | Cassius Blue Solar LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 100 | 100 | 100 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-436 | TC2 | PHASE 1 | Carson - Rogers Road 500 kV |  | Monarch | VA | Sussex | Active | Generation Interconnection | Dominion | 400 | 400 | 400 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-426 | TC2 | PHASE 1 | Wakefield - Waverly 115 kV |  | Waverly Solar 1, LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 50 | 50 | 47.66 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 2/29/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-427 | TC2 | PHASE 1 | Waverly 115 kV |  | Old Forty Road Solar LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 85 | 85 | 66.3 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 2/29/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-428 | TC2 | PHASE 1 | Wakefield 115 kV |  | Peter’s Bridge Road Solar 1, LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 170 | 170 | 135.7 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 2/29/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-461 | TC2 | PHASE 1 | Buckhorn 138 kV |  | Lakeside Energy, LLC | VA | Tazewell | Active | Generation Interconnection | AEP | 80 | 80 | 80 |  | Capacity | Storage | 9/10/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-133 | TC2 | PHASE 1 | Saltville - Tazewell 138 kV |  | Hermes Solar LLC | VA | Tazewell | Active | Generation Interconnection | AEP | 100 | 100 | 60 |  | Capacity | Solar | 8/23/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-747 | TC2 | RRI APPLICATION REVIEW |  |  | Cardinal Energy Storage East, LLC | VA | Warren | Withdrawn | Generation Interconnection | Dominion | 300 | 300 | 300 |  | Capacity | Storage |  | 6/11/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-227 | TC2 | PHASE 1 | Flemming - Fremont 69 kV |  | Virginia Electric and Power Company | VA | Wise | Active | Generation Interconnection | AEP | 51.3 | 51.3 | 30.78 |  | Capacity | Solar | 9/8/2021 | 12/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-348 | TC2 | PHASE 1 | Pound 34.5 kV |  | Highlands CF Solar, LLC | VA | Wise | Active | Generation Interconnection | AEP | 10 | 10 | 6 |  | Capacity | Solar | 9/10/2021 | 12/21/2023 | [5 empty] | 5/10/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-462 | TC2 | PHASE 1 | Progress Park - Glen Lyn 138 kV |  | May Solar LLC | VA | Wythe | Withdrawn | Generation Interconnection | AEP | 150 | 150 | 78 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 10/31/2024 | [5 empty] | 6/9/2025 | 6/9/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-157 | TC2 | PHASE 1 | Penniman - Waller 230 kV |  | Delorean Power LLC | VA | York | Active | Generation Interconnection | Dominion | 100 | 100 | 100 |  | Capacity | Storage | 8/31/2021 | 1/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-359 | TC1 | PHASE 1 | Fentress 230 kV |  | Fentress Energy Storage, LLC | VA | City of Chesapeake | Withdrawn | Generation Interconnection | Dominion | 127.5 | 127.5 | 127.5 |  | Capacity | Storage | 9/30/2020 | 12/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-359/AG1-359_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-364 | TC1 | PHASE 1 | Deep Creek 115 kV |  | Crossroads LLC | VA | City of Chesapeake | Withdrawn | Generation Interconnection | Dominion | 100 | 100 | 40 |  | Capacity | Storage | 9/30/2020 | 11/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-364/AG1-364_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-156 | TC1 | PHASE 3 | Yadkin 115 kV | Yadkins Energy Center | Yadkins Energy Center, LLC | VA | City of Chesapeake | Active | Generation Interconnection | Dominion | 100 | 100 | 100 |  | Capacity | Storage | 3/15/2019 | 12/1/2021 | [5 empty] | 5/21/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-156/AE2-156_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-156/AE2-156_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-123 | TC1 | PHASE 3 | Oceana 230 kV |  | Virginia Electric and Power Company | VA | City of Chesapeake | Active | Generation Interconnection | Dominion | 833 | 833 | 253.2 |  | Capacity | Offshore Wind | 9/17/2019 | 12/31/2025 |  |  |  |  | 12/31/2025 | 3/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-123/AF1-123_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-123/AF1-123_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af1_123_csa.pdf | Posted
AF1-124 | TC1 | PHASE 3 | Oceana 230 kV |  | Virginia Electric and Power Company | VA | City of Chesapeake | Active | Generation Interconnection | Dominion | 836 | 836 | 254.1 |  | Capacity | Offshore Wind | 9/17/2019 | 12/31/2026 | [5 empty] | 3/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-124/AF1-124_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-124/AF1-124_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af1_124_csa.pdf | Posted
AF1-125 | TC1 | PHASE 3 | Oceana 230 kV |  | Virginia Electric and Power Company | VA | City of Chesapeake | Active | Generation Interconnection | Dominion | 820 | 820 | 249.3 |  | Capacity | Offshore Wind | 9/17/2019 | 12/31/2024 | [5 empty] | 3/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-125/AF1-125_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-125/AF1-125_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af1_125_csa.pdf | Posted
AH1-226 | TC2 | PHASE 1 | Clubhouse - Sapony 230 kV |  | Virginia Electric and Power Company | VA | City of Emporia | Withdrawn | Generation Interconnection | Dominion | 115 | 115 | 69 |  | Capacity | Solar | 9/8/2021 | 12/1/2025 | [5 empty] | 5/5/2025 | 4/11/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-010 | TC2 | PHASE 1 | Peninsula-Whealton 115 kV | Hampton BESS 3 | Delorean Power LLC | VA | City of Hampton | Active | Generation Interconnection | Dominion | 100 | 100 | 75.96 |  | Capacity | Storage | 10/9/2020 | 1/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-065 | TC2 | PHASE 1 | Hopewell 34.5kV | Churchill Storage Solutions LLC | Churchill Storage Solutions LLC | VA | City of Hopewell | Active | Generation Interconnection | Dominion | 20 | 20 | 8 |  | Capacity | Storage | 7/27/2021 | 5/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-066 | TC2 | PHASE 1 | Hopewell 34.5kV | Churchill Storage Solutions LLC | Churchill Storage Solutions LLC | VA | City of Hopewell | Active | Generation Interconnection | Dominion | 10 | 10 | 4 |  | Capacity | Storage | 7/27/2021 | 5/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-202 | TC2 | APPLICATION REVIEW | Reusens 12.47 kV |  | James Energy Center, LLC | VA | City of Lynchburg | Withdrawn | Generation Interconnection | AEP | 20 | 20 | 20 |  | Capacity | Storage | 3/4/2021 | 10/31/2022 | [5 empty] | 3/11/2025 | 3/11/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-108 | TC2 | PHASE 1 | Spruance NUG 230 kV |  | Spruance Operating Services LLC | VA | City of Richmond | Active | Generation Interconnection | Dominion | 66 | 0 | 9 |  | Capacity | Natural Gas | 8/4/2021 | 6/1/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-323 | TC2 | PHASE 1 | Elmont 230 kV |  | Invenergy | VA | City of Suffolk | Active | Generation Interconnection | Dominion | 100 | 100 | 100 |  | Capacity | Storage | 9/9/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-730 | TC2 | RRI APPLICATION REVIEW |  |  | SolAmerica Energy, LLC | VA | City of Suffolk | Withdrawn | Generation Interconnection | Dominion | 100 | 100 | 100 |  | Capacity | Storage |  | 4/30/2028 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AE2-123 | TC1 | PHASE 1 | Birdneck-Landstown 230 kV |  | Avangrid Renewables, LLC | VA | City of Virginia Beach | Withdrawn | Generation Interconnection | Dominion | 800.1 | 800.1 | 163.3 |  | Capacity | Offshore Wind | 2/28/2019 | 12/31/2027 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-123/AE2-123_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-124 | TC1 | PHASE 1 | Landstown 230 kV |  | Avangrid Renewables, LLC | VA | City of Virginia Beach | Withdrawn | Generation Interconnection | Dominion | 800.1 | 800.1 | 148.5 |  | Capacity | Offshore Wind | 2/28/2019 | 12/31/2029 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-124/AE2-124_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-138 | TC2 | PHASE 1 | Penniman 34.5 kV |  | Virginia Electric and Power Company | VA | City of Williamsburg | Active | Generation Interconnection | Dominion | 20 | 20 | 8.4 |  | Capacity | Solar | 7/30/2021 | 7/15/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-254 | TC2 | PHASE 1 | Greenland Gap 500 kV II | Mount Storm Repower | Renew Development Holdco LLC | WV | Barbour | Active | Generation Interconnection | APS | 171.4 | 171.4 | 36.538 |  | Capacity | Wind | 9/10/2021 | 7/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-423 | TC2 | PHASE 1 | Cherry Run–Harmony 138 kV |  | Falling Waters Solar, LLC | WV | Barbour | Active | Generation Interconnection | APS | 80 | 80 | 48 |  | Capacity | Solar | 3/30/2021 | 6/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-582 | TC2 | PHASE 1 | Flint Run 500 kV |  | CPV LLC | WV | Doddridge | Active | Generation Interconnection | APS | 2100 | 2100 | 2075 |  | Capacity | Natural Gas | 3/31/2021 | 7/1/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-219 | TC1 | PHASE 1 | Layland 69 kV |  | Fayette Solar I, LLC | WV | Fayette | Withdrawn | Generation Interconnection | AEP | 75 | 75 | 39.5 |  | Capacity | Solar,Storage,Hybrid | 9/23/2020 | 12/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-219/AG1-219_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-194 | TC1 | PHASE 2 | Nuttall 138 kV |  | Keeneys Creek Solar I, LLC | WV | Fayette | Withdrawn | Generation Interconnection | AEP | 79 | 79 | 27 |  | Capacity | Solar,Storage,Hybrid | 9/18/2020 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-194/AG1-194_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-194/AG1-194_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-657 | TC2 | PHASE 1 | Carbondale 138 kV |  | Mammoth Solar, LLC | WV | Fayette | Active | Generation Interconnection | AEP | 90 | 90 | 37.8 |  | Capacity | Solar | 3/31/2021 | 6/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-655 | TC2 | PHASE 1 | Mt. Storm-Bismark 500 kV |  | Mountain Storm LLC | WV | Grant | Active | Generation Interconnection | Dominion | 500 | 500 | 210 |  | Capacity | Solar | 3/31/2021 | 6/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-255 | TC2 | PHASE 1 | Greenland Gap III | Mount Storm Repower BESS 1 | Mountain Storm LLC | WV | Grant | Active | Generation Interconnection | APS | 240 | 240 | 240 |  | Capacity | Storage | 9/9/2021 | 7/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-590 | TC2 | PHASE 1 | Cherry Ridge 66 kV | Messenger Brothers Solar I | RWE LLC | WV | Grant | Active | Generation Interconnection | APS | 50 | 50 | 30 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-591 | TC2 | PHASE 1 | Cherry Ridge 66kV | Messenger Brothers Solar II | RWE LLC | WV | Grant | Active | Generation Interconnection | APS | 100 | 50 | 30 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-592 | TC2 | PHASE 1 | Cherry Ridge 66kV | Messenger Brothers Storage | RWE LLC | WV | Grant | Active | Generation Interconnection | APS | 145 | 45 | 45 |  | Capacity | Storage | 9/10/2021 | 12/16/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-713 | TC2 | PHASE 1 | Mt. Storm 500kV |  | Virginia Electric and Power Company | WV | Grant | Active | Generation Interconnection | Dominion | 538 | 0 | 14 |  | Capacity | Coal |  | 6/1/2030 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-062 | TC2 | PHASE 1 | Williams 138 kV |  | Catamount Wind LLC | WV | Grant | Active | Generation Interconnection | APS | 147 | 147 | 21.609 |  | Capacity | Wind | 12/15/2020 | 8/1/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-376 | TC2 | PHASE 1 | Ronceverte - Clenden 46 kV | Trillium PV I | Trillium PV I, LLC | WV | Greenbrier | Withdrawn | Generation Interconnection | APS | 28 | 28 | 16.8 |  | Capacity | Solar | 9/10/2021 | 6/1/2025 | [5 empty] | 5/5/2025 | 4/22/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-387 | TC2 | PHASE 1 | Meadowbrook-Greenland Gap 500kV | CPV Capon Springs Wind | CPV LLC | WV | Hampshire | Active | Generation Interconnection | APS | 150 | 150 | 22.05 |  | Capacity | Wind | 9/10/2021 | 1/9/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-403 | TC2 | PHASE 1 | Meadow Brook - Mt. Storm 500 kV |  | Old Fields Solar, LLC | WV | Hardy | Active | Generation Interconnection | APS | 125 | 125 | 52.5 |  | Capacity | Solar | 3/30/2021 | 6/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-404 | TC2 | PHASE 1 | Meadow Brook - Mt. Storm 500 kV II |  | Old Fields Solar, LLC | WV | Hardy | Active | Generation Interconnection | APS | 250 | 125 | 52.5 |  | Capacity | Solar | 3/30/2021 | 6/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-426 | TC2 | PHASE 1 | Gilboa-Jones Branch 138 kV IV |  | Nicholas County Solar Project, LLC | WV | Kanawha | Active | Generation Interconnection | APS | 64.6 | 64.6 | 64.6 |  | Capacity | Storage | 9/11/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-448 | TC2 | PHASE 1 | Cross School - Westvaco 138 kV |  | Potomac Hills Energy, LLC | WV | Mineral | Active | Generation Interconnection | APS | 50 | 50 | 30 |  | Capacity | Solar | 3/30/2021 | 3/24/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-314 | TC2 | APPLICATION PHASE | Gilboa-Jones Branch 138 kV III |  | Deep Lake Energy Center, LLC | WV | Nicholas | Withdrawn | Generation Interconnection | APS | 150 | 0 | 67 |  | Capacity | Storage | 3/25/2021 | 5/1/2024 | [5 empty] | 12/12/2024 | 11/27/2024 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-426A | TC2 | PHASE 1 | Gilboa-Jones Branch 138 kV V |  | Nicholas County Solar Project, LLC | WV | Nicholas | Active | Generation Interconnection | APS | 96.9 | 32.3 | 32.3 |  | Capacity | Storage | 9/11/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-340 | TC2 | PHASE 1 | Cheat Lake-Ruthbelle 138 kV | Preston County Solar Project | Rockville Solar LLC | WV | Preston | Active | Generation Interconnection | APS | 48.89 | 48.89 | 29.33 |  | Capacity | Solar | 9/10/2021 | 5/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-658 | TC2 | PHASE 1 | Cowen 138 kV |  | Halo Solar WV LLC | WV | Webster | Active | Generation Interconnection | APS | 210 | 210 | 135.3 |  | Capacity | Solar | 3/31/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-138 | TC1 | PHASE 1 | Avon-North Clark 345 kV |  | Geenex Solar, LLC | KY | Clark | Withdrawn | Generation Interconnection | EKPC | 260 | 260 | 20.8 |  | Capacity | Solar | 3/8/2019 | 6/1/2022 | [5 empty] | 1/24/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-138/AE2-138_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-138/AE2-138_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-210 | TC1 | PHASE 1 | Avon-North Clark 345 kV |  | Geenex Solar, LLC | KY | Clark | Withdrawn | Generation Interconnection | EKPC | 90 | 90 | 7.2 |  | Capacity | Solar | 3/20/2019 | 6/1/2022 | [5 empty] | 1/24/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-210/AE2-210_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-210/AE2-210_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-184 | TC2 | PHASE 1 | Harbert Metering 138 kV |  | STMO bn, LLC | KY | Knott | Active | Generation Interconnection | AEP | 210 | 210 | 126 |  | Capacity | Solar | 2/27/2021 | 6/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-111 | TC1 | PHASE 3 | North Clark-Spurlock 345 kV | Goldfinch Solar | Goldfinch Solar, LLC | KY | Mason | Active | Generation Interconnection | EKPC | 250 | 250 | 150 |  | Capacity | Solar | 2/28/2020 | 12/31/2023 | [5 empty] | 5/19/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-111/AF2-111_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-111/AF2-111_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-756 | TC2 | RRI APPLICATION REVIEW |  |  | Goldfinch Solar, LLC | KY | Mason | Withdrawn | Generation Interconnection | Duke | 500 | 250 | 250 |  | Capacity | Storage |  | 12/31/2030 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-281 | TC2 | PHASE 1 | Bluegrass Parkway Tap - Woodlawn 69 kV |  | Soltage KY DevCo, LLC | KY | Nelson | Active | Generation Interconnection | EKPC | 20 | 20 | 12 |  | Capacity | Solar | 9/9/2021 | 6/7/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-446 | TC2 | APPLICATION REVIEW | Sanders DP - Westmoreland 230 kV |  | Kings Highway Solar LLC | VA | Westmoreland | Withdrawn | Generation Interconnection | Dominion | 65 | 65 | 19.5 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 12/2/2024 | [5 empty] | 5/7/2025 | [9 empty] | Not Started |  | Not Started
AH1-637 | TC2 | PHASE 1 | Oak Grove 34.5 kV |  | Solar VA 2019 LLC | VA | Westmoreland | Active | Generation Interconnection | Dominion | 16 | 16 | 9.6 |  | Capacity | Solar | 9/13/2021 | 12/15/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-469 | TC2 | PHASE 1 | Westmoreland – Oak Grove 230 kV |  | Invenergy | VA | Westmoreland | Active | Generation Interconnection | Dominion | 80 | 80 | 48 |  | Capacity | Solar | 3/31/2021 | 12/31/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-753 | TC2 | RRI APPLICATION REVIEW |  |  | Calpine | WV | Marshall | Withdrawn | Generation Interconnection | AEP | 455 | 455 | 396 |  | Capacity | Natural Gas |  | 9/13/2019 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AH1-188 | TC2 | PHASE 1 | Pigeon Creek 138 kV |  | Twisted Gun Solar, LLC | WV | Mingo | Active | Generation Interconnection | AEP | 140 | 140 | 84 |  | Capacity | Solar | 8/31/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-354 | TC2 | APPLICATION REVIEW | Ragland - Grant Branch 138 kV |  | Mountaineer Solar LLC | WV | Mingo | Withdrawn | Generation Interconnection | AEP | 100 | 100 | 72.92 |  | Capacity | Solar,Storage,Hybrid | 3/26/2021 | 9/30/2024 | [5 empty] | 2/6/2025 | 2/6/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-440 | TC2 | PHASE 1 | Twittys Creek - Madisonville 115 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 100 | 100 | 60 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-441 | TC2 | PHASE 1 | Twittys Creek - Madisonville 115 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 225 | 125 | 75 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-442 | TC2 | PHASE 1 | Twittys Creek - Madisonville 115 kV |  | Taro Solar, LLC | VA | Charlotte | Active | Generation Interconnection | Dominion | 140 | 140 | 84 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-077 | TC2 | PHASE 1 | Clover-Rawlings 500 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 700 | 200 | 120 |  | Capacity | Solar | 1/19/2021 | 6/30/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-222 | TC1 | PHASE 3 | Madisonville DP-Twitty's Creek 115 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 167 | 167 | 100 |  | Capacity | Solar | 3/25/2020 | 5/31/2023 |  |  |  | 12/31/2025 | 3/31/2027 | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-222/AF2-222_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-222/AF2-222_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af2_222_csa.pdf | Posted
AG1-272 | TC1 | PHASE 2 | Twitty's Creek 115 kV |  | CV-Tollhouse LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 6 |  | Capacity | Solar,Storage,Hybrid | 9/29/2020 | 3/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-272/AG1-272_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-272/AG1-272_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-273 | TC1 | PHASE 2 | Twitty's Creek 115 kV |  | CV-Tollhouse LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 6 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-273/AG1-273_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-273/AG1-273_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-274 | TC1 | PHASE 2 | Twitty's Creek 115 kV |  | CV-Tollhouse LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 6 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-274/AG1-274_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-274/AG1-274_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-285 | TC1 | PHASE 3 | Chase City-Central 115 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 125 | 125 | 75 |  | Capacity | Solar | 9/28/2020 | 12/1/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-285/AG1-285_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-285/AG1-285_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-185 | TC1 | PHASE 1 | Pamplin-Chase City 115 kV |  | Drakes Branch Solar, LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 150 | 0 | 48.91 |  | Capacity | Storage | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-185/AG1-185_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-181 | TC1 | PHASE 1 | Pamplin-Chase City 115 kV |  | Drakes Branch Solar, LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 150 | 150 | 101.09 |  | Capacity | Solar | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-181/AG1-181_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-384 | TC1 | PHASE 2 | Twitty's Creek 115 kV |  | CV-Tollhouse LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 20 | 20 | 6 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-384/AG1-384_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-384/AG1-384_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AH1-215 | TC2 | PHASE 1 | Central VA-Twitty 115 kV |  | Mountain Pine Chase City LLC | VA | Charlotte | Active | Generation Interconnection | Dominion | 31.5 | 31.5 | 18.9 |  | Capacity | Solar,Storage,Hybrid | 9/9/2021 | 2/1/2025 | [5 empty] | 5/5/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-278 | TC1 | PHASE 1 | Lewis Run-Pierce Brook 3 230 kV |  | McKean LLC | PA | Mc Kean | Withdrawn | Generation Interconnection | PENELEC | 280 | 80 | 53.44 |  | Capacity | Solar | 9/30/2019 | 6/29/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-278/AF1-278_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-666 | TC2 | PHASE 1 | Flemingsburg - Spurlock 138 kV |  | Fleming Solar, LLC | KY | Fleming | Active | Generation Interconnection | EKPC | 80 | 80 | 48 |  | Capacity | Solar | 9/30/2019 | 6/1/2023 | [5 empty] | 5/15/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-233 | TC1 | PHASE 3 | Flemingsburg – Spurlock 138kV | AEUG Fleming Solar | AEUG | KY | Fleming | Active | Generation Interconnection | EKPC | 188.5 | 188.5 | 113.1 |  | Capacity | Solar | 9/27/2019 | 5/31/2022 | [5 empty] | 2/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-233/AF1-233_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-233/AF1-233_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-665 | TC2 | PHASE 1 | Goddard-Plumsville 138 kV II |  | Hummingbird Energy LLC | KY | Fleming | Active | Generation Interconnection | EKPC | 180 | 80 | 53.5 |  | Capacity | Solar | 1/23/2019 | 6/1/2022 | [5 empty] | 5/16/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-664 | TC2 | PHASE 1 | Goddard-Plumville 138 kV |  | Hummingbird Energy LLC | KY | Fleming | Active | Generation Interconnection | EKPC | 100 | 100 | 66.8 |  | Capacity | Solar | 9/24/2018 | 6/1/2022 | [5 empty] | 5/5/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-429 | TC2 | PHASE 1 | Flemingsburg - Spurlock 138 kV |  | ACE | KY | Fleming | Active | Generation Interconnection | EKPC | 90 | 90 | 54 |  | Capacity | Solar | 9/10/2021 | 9/1/2026 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-034 | TC2 | PHASE 1 | Patton Road Junction - Summer Shade 69 kV | Scotland Solar | Scotland Solar, LLC | KY | Barren | Active | Generation Interconnection | EKPC | 100 | 100 | 70 |  | Capacity | Solar | 6/14/2021 | 11/15/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-070 | TC1 | PHASE 3 | Bon Ayr 69 kV |  | Wood Duck Solar LLC | KY | Barren | Active | Generation Interconnection | EKPC | 45 | 45 | 32.7 |  | Capacity | Solar | 7/30/2020 | 6/1/2024 | [5 empty] | 2/25/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-071 | TC1 | PHASE 3 | Bon Ayr 69 kV |  | Wood Duck Solar LLC | KY | Barren | Active | Generation Interconnection | EKPC | 55 | 55 | 37.5 |  | Capacity | Solar | 7/30/2020 | 6/1/2024 | [5 empty] | 2/25/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-154 | TC1 | PHASE 3 | Ladysmith CT 230 kV |  | Virginia Electric and Power Company | VA | Caroline | Active | Generation Interconnection | Dominion | 50 | 50 | 20 |  | Capacity | Storage | 9/10/2020 | 12/1/2023 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-154/AG1-154_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-154/AG1-154_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-412 | TC1 | PHASE 2 | Ladysmith CT-Mine Road 230 kV |  | Matta Grid, LLC | VA | Caroline | Withdrawn | Generation Interconnection | Dominion | 200 | 200 | 80 |  | Capacity | Storage | 9/30/2020 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-412/AG1-412_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-412/AG1-412_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-320 | TC2 | PHASE 1 | Ladysmith 230 kV |  | Ladysmith Storage, LLC | VA | Caroline | Active | Generation Interconnection | Dominion | 150 | 150 | 105 |  | Capacity | Storage | 3/24/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-222 | TC2 | PHASE 1 | Ladysmith CT 230 kV |  | Virginia Electric and Power Company | VA | Caroline | Withdrawn | Generation Interconnection | Dominion | 50 | 0 | 30 |  | Capacity | Storage | 9/8/2021 | 12/1/2023 | [5 empty] | 5/5/2025 | 4/29/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-626 | TC2 | APPLICATION REVIEW | Ladysmith 230 kV |  | Idemitsu Renewables America Development LLC | VA | Caroline | Withdrawn | Generation Interconnection | Dominion | 62.5 | 62.5 | 62.5 |  | Capacity | Storage | 9/10/2021 | 3/21/2025 | [5 empty] | 1/14/2025 | 1/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-627 | TC2 | APPLICATION REVIEW | Ladysmith 230 kV II |  | Idemitsu Renewables America Development LLC | VA | Caroline | Withdrawn | Generation Interconnection | Dominion | 125 | 62.5 | 62.5 |  | Capacity | Storage | 9/10/2021 | 3/21/2025 | [5 empty] | 1/14/2025 | 1/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-694 | TC2 | PHASE 1 | Ladysmith CT 230 kV |  | Virginia Electric and Power Company | VA | Caroline | Active | Generation Interconnection | Dominion | 190 | 0 | 18 |  | Capacity | Natural Gas |  | 10/15/2028 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-691 | TC2 | PHASE 1 | Ladysmith CT 230 kV |  | Virginia Electric and Power Company | VA | Caroline | Active | Generation Interconnection | Dominion | 209 | 0 | 26 |  | Capacity | Natural Gas |  | 5/31/2029 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-692 | TC2 | PHASE 1 | Ladysmith CT 230 kV |  | Virginia Electric and Power Company | VA | Caroline | Active | Generation Interconnection | Dominion | 209 | 0 | 26 |  | Capacity | Natural Gas |  | 11/30/2028 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-682 | TC2 | PHASE 1 | Ladysmith CT 230 kV |  | Virginia Electric and Power Company | VA | Caroline | Active | Generation Interconnection | Dominion | 190 | 0 | 21 |  | Capacity | Natural Gas |  | 11/30/2027 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-683 | TC2 | PHASE 1 | Ladysmith CT 230 kV |  | Virginia Electric and Power Company | VA | Caroline | Active | Generation Interconnection | Dominion | 190 | 0 | 25 |  | Capacity | Natural Gas |  | 10/15/2027 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-081 | TC2 | PHASE 1 | Knob Lick 69kV |  | Wildrye Solar LLC | KY | Metcalfe | Withdrawn | Generation Interconnection | EKPC | 60 | 60 | 36 |  | Capacity | Solar | 7/30/2021 | 12/20/2024 | [5 empty] | 5/6/2025 | 5/5/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-082 | TC2 | PHASE 1 | Knob Lick 69kV |  | Wildrye Solar LLC | KY | Metcalfe | Withdrawn | Generation Interconnection | EKPC | 104 | 44 | 26.4 |  | Capacity | Solar | 7/30/2021 | 12/20/2024 | [5 empty] | 5/6/2025 | 5/5/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-083 | TC2 | PHASE 1 | Summer Shade - Green County 161 kV |  | Coneflower LLC | KY | Metcalfe | Withdrawn | Generation Interconnection | EKPC | 250 | 100 | 60 |  | Capacity | Solar | 7/30/2021 | 12/20/2024 | [5 empty] | 5/6/2025 | 5/5/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-094 | TC2 | PHASE 1 | Summer Shade-Green County 161 kV |  | Coneflower LLC | KY | Metcalfe | Withdrawn | Generation Interconnection | EKPC | 150 | 150 | 90 |  | Capacity | Solar | 1/27/2021 | 4/1/2024 | [5 empty] | 5/6/2025 | 5/5/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-341 | TC1 | PHASE 3 | Summer Shade 161 kV |  | Naturgy Candela DevCo LLC | KY | Metcalfe | Active | Generation Interconnection | EKPC | 106 | 106 | 63.6 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/15/2023 | [5 empty] | 2/7/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-306 | TC1 | PHASE 1 | Fawkes-Dale 138 kV |  | AEUG | KY | Madison | Withdrawn | Generation Interconnection | EKPC | 65 | 65 | 39 |  | Capacity | Solar | 9/29/2020 | 10/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-306/AG1-306_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-275 | TC1 | PHASE 1 | J.K. Smith-Fawkes 138 kV |  | Geenex Solar, LLC | KY | Madison | Withdrawn | Generation Interconnection | EKPC | 90 | 90 | 7.2 |  | Capacity | Solar | 3/28/2019 | 6/1/2022 | [5 empty] | 1/25/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-275/AE2-275_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-275/AE2-275_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-308 | TC1 | PHASE 3 | Three Forks-Dale 138 kV | Madison Solar 1 | AEUG | KY | Madison | Active | Generation Interconnection | EKPC | 100 | 100 | 60 |  | Capacity | Solar | 3/29/2019 | 5/31/2021 |  |  |  |  | 1/31/2026 | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-308/AE2-308_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-308/AE2-308_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-348 | TC1 | DP2 | North Clark-Spurlock 345 kV |  | AEUG | KY | Madison | Withdrawn | Generation Interconnection | EKPC | 250 | 250 | 150 |  | Capacity | Solar | 3/31/2020 | 7/1/2022 | [5 empty] | 2/3/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-348/AF2-348_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-348/AF2-348_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-355 | TC1 | DP2 | West Gerrard-J.K. Smith 345 kV |  | AEUG | KY | Madison | Withdrawn | Generation Interconnection | EKPC | 225 | 225 | 135 |  | Capacity | Solar | 3/31/2020 | 7/1/2022 | [5 empty] | 2/3/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-355/AF2-355_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-355/AF2-355_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG2-073 | TC2 | PHASE 1 | Crooksville 69 kV |  | SR LLC | KY | Madison | Active | Generation Interconnection | EKPC | 100 | 100 | 60 |  | Capacity | Solar | 1/11/2021 | 5/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-526 | TC1 | PHASE 3 | West Garrard 345 kV |  | PJM Solar Devco I, LLC | KY | Garrard | Active | Generation Interconnection | EKPC | 222 | 222 | 133.2 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 2/21/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-526/AG1-526_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-526/AG1-526_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-004 | TC2 | PHASE 1 | Avon - Renaker 138 kV |  | SR LLC | KY | Fayette | Active | Generation Interconnection | EKPC | 40 | 40 | 24 |  | Capacity | Solar | 4/7/2021 | 12/1/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-670 | TC2 | PHASE 1 | Greensburg 69 kV |  | Innergex | KY | Green | Active | Generation Interconnection | EKPC | 75 | 75 | 45 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-751 | TC2 | RRI APPLICATION REVIEW |  |  | Exie Solar, LLC | KY | Green | Withdrawn | Generation Interconnection | EKPC | 300 | 150 | 150 |  | Capacity | Storage |  | 9/30/2029 | [5 empty] | 5/5/2025 | 5/2/2025 | Queue Not Required | [7 empty] | Not Started |  | Not Started
AG1-354 | TC1 | PHASE 3 | Summershade-Green County 161 kV |  | Exie Solar, LLC | KY | Green | Active | Generation Interconnection | EKPC | 150 | 150 | 90 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 2/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-354/AG1-354_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-354/AG1-354_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-553 | TC2 | PHASE 1 | Bullitt County 161 kV |  | EDP Renewables North America LLC | KY | Bullitt | Active | Generation Interconnection | EKPC | 50 | 50 | 20 |  | Capacity | Storage | 3/31/2021 | 9/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-365 | TC1 | PHASE 3 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | Thoroughbred Solar, LLC | KY | Hart | Active | Generation Interconnection | EKPC | 50 | 50 | 30 |  | Capacity | Solar | 3/31/2020 | 12/31/2022 | [5 empty] | 3/3/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AF2-391 | TC1 | PHASE 2 | Central Hardin 69 kV |  | Naturgy Candela DevCo LLC | KY | Hardin | Withdrawn | Generation Interconnection | EKPC | 120 | 120 | 72 |  | Capacity | Solar,Storage,Hybrid | 3/31/2020 | 6/15/2023 | [5 empty] | 1/14/2025 | 1/14/2025 | Customer Initiated Withdrawal |  | Not Applicable |  | Not Specified |  | Not Started |  | Not Started |  | Not Started
AG1-320 | TC1 | PHASE 3 | Glendale-Stephensburg 69 kV | Stonecrop Solar | CPV LLC | KY | Hardin | Active | Generation Interconnection | EKPC | 82 | 82 | 54.8 |  | Capacity | Solar | 9/30/2020 | 10/1/2023 | [5 empty] | 6/9/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG2-081 | TC2 | PHASE 1 | Mt. Sterling-Fogg Pike 69 kV |  | SR LLC | KY | Montgomery | Active | Generation Interconnection | EKPC | 30 | 30 | 18 |  | Capacity | Solar | 1/21/2021 | 5/1/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-298 | TC2 | PHASE 1 | Sulphur Creek-Loretto 69 kV |  | Crab Run Solar Project, LLC | KY | Marion | Active | Generation Interconnection | EKPC | 60 | 60 | 40 |  | Capacity | Solar | 3/23/2021 | 9/1/2024 | [5 empty] | 5/29/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-488 | TC1 | PHASE 1 | Marion Co 161 kV |  | BrightNight, LLC | KY | Marion | Withdrawn | Generation Interconnection | EKPC | 70 | 70 | 42 |  | Capacity | Solar | 9/30/2020 | 9/30/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-488/AG1-488_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-405 | TC1 | PHASE 3 | Walnut Grove-Asahi 69 kV |  | Sunflower Prairie Solar Project, LLC | KY | McLean | Active | Generation Interconnection | EKPC | 57 | 57 | 34.2 |  | Capacity | Solar | 9/30/2020 | 9/25/2024 | [5 empty] | 2/24/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-406 | TC1 | PHASE 3 | Walnut Grove-Asahi 69 kV |  | Sunflower Prairie Solar Project, LLC | KY | McLean | Active | Generation Interconnection | EKPC | 79 | 22 | 22 |  | Capacity | Storage | 9/30/2020 | 9/25/2024 | [5 empty] | 2/12/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-353 | TC1 | PHASE 1 | Green County-Marion County 161 kV |  | Creekview Solar, LLC | KY | Taylor | Withdrawn | Generation Interconnection | EKPC | 98 | 98 | 58.8 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 1/24/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-353/AG1-353_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-353/AG1-353_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-307 | TC1 | PHASE 3 | Hope-Belvins Valley Tap 69 kV |  | Flat Top Solar Project, LLC | KY | Bath | Active | Generation Interconnection | EKPC | 64.2 | 64.2 | 39.6 |  | Capacity | Solar | 3/30/2020 | 9/1/2023 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-307/AF2-307_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-307/AF2-307_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-463 | TC2 | PHASE 1 | Owingsville - Preston 69 kV |  | Preston Solar, LLC | KY | Bath | Withdrawn | Generation Interconnection | EKPC | 65 | 65 | 39 |  | Capacity | Solar | 9/10/2021 | 12/31/2024 | [5 empty] | 5/5/2025 | 4/22/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-116 | TC1 | PHASE 2 | Marion County 161 kV |  | Logan Branch Solar, LLC | KY | Washington | Withdrawn | Generation Interconnection | EKPC | 120 | 120 | 72 |  | Capacity | Solar | 9/12/2019 | 12/29/2023 | [5 empty] | 4/1/2025 | 2/28/2025 | Customer Milestone Not Met |  | Not Applicable |  | Not Applicable |  | Not Started |  | Not Started |  | Not Started
AG2-179 | TC2 | PHASE 1 | Coburg 69 kV |  | Round Trip, LLC | KY | Adair | Active | Generation Interconnection | EKPC | 60 | 60 | 57 |  | Capacity | Solar,Storage,Hybrid | 2/26/2021 | 9/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-424 | TC2 | PHASE 1 | Bonnieville - Lebanon 138 kV |  | Magnolia Solar and Grazing Farm LLC | KY | Larue | Active | Generation Interconnection | EKPC | 63.25 | 63.25 | 34.95 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 5/31/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started