## Sheet1
Project ID | Cycle | Stage | Name | Commercial Name | Developer | State | County | Status | Project Type | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Fuel | Submitted Date | Requested In-Service Date | Revised In-Service Date | Actual In-Service Date | Commercial Operation Milestone | Backfeed Date | Test Energy Date | Last Updated | Withdrawn Date | Withdrawn Remarks | Phase 1 SIS Report | Phase 1 SIS Report Status | Phase 2 SIS Report | Phase 2 SIS Report Status | Phase 3 SIS Report | Phase 3 SIS Report Status | GIA/WMPA Report | GIA/WMPA Report Status | CSA/USCA Report | CSA/USCA Report Status | Transmission Type | Rights (MW) | Long-Term Firm Service Start Date | Long-Term Firm Service End Date
AF2-182 | TC1 | PHASE 3 | Nelson-Lee County 345 kV II |  | Deriva Energy Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 500 | 300 | 0 |  | Energy | Solar | 3/21/2020 | 12/1/2022 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-182/AF2-182_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-182/AF2-182_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-280 | TC1 | PHASE 3 | Nelson-Lee County |  | Deriva Energy Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 200 | 200 | 0 |  | Energy | Solar | 9/10/2019 | 12/1/2022 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-280/AF1-280_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-280/AF1-280_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-349 | TC1 | PHASE 3 | SILVER LAKE- CHERRY VALLEY 345 KV |  | Deriva Energy Solar, LLC | IL | McHenry | Active | Generation Interconnection | ComEd | 300 | 300 | 0 |  | Energy | Solar | 3/31/2020 | 12/1/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-349/AF2-349_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-349/AF2-349_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-553 | TC1 | PHASE 3 | Cordova 345 kV |  | Beacon Solar, LLC | IL | Rock Island | Active | Generation Interconnection | ComEd | 260 | 260 | 0 |  | Energy | Solar | 9/30/2020 | 12/29/2023 | [5 empty] | 3/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-553/AG1-553_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-553/AG1-553_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AH1-165 | TC2 | PHASE 1 | Will County 138 kV |  | NRG Midwest Storage LLC | IL | Will | Active | Generation Interconnection | ComEd | 72 | 72 | 0 |  | Energy | Storage | 8/31/2021 | 6/1/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-248 | TC2 | PHASE 1 | East Elkhart – Elcona Tap 138 kV |  | Amberjack Solar LLC | IN | Elkhart | Active | Generation Interconnection | AEP | 100 | 100 | 0 |  | Energy | Storage | 3/17/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-239 | TC2 | PHASE 1 | Hickory-Shawboro 230 kV |  | Ranchland Solar, LLC | NC | Currituck | Active | Generation Interconnection | Dominion | 60 | 0 | 0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-238 | TC2 | PHASE 1 | Earleys 230 kV |  | Aulander Holloman Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 99.9 | 0 | 0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-091 | TC2 | PHASE 1 | Ahoskie 34.5kV |  | Colice Hall Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 17 | 0 | 0 |  | Energy | Storage | 7/30/2021 | 11/15/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-237 | TC2 | PHASE 1 | Thelma 230kV |  | Oak Solar LLC | NC | Northhampton | Active | Generation Interconnection | Dominion | 323 | 0 | 0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-121 | TC2 | PHASE 1 | Mackeys 230 kV |  | Albemarle Beach Solar, LLC | NC | Washington | Active | Generation Interconnection | Dominion | 140 | 0 | 0 |  | Energy | Storage | 1/29/2021 | 12/15/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-531 | TC2 | APPLICATION REVIEW | Greystone - West Denville 34.5 kV |  | West Denville LLC | NJ | Morris | Withdrawn | Generation Interconnection | JCPL | 20 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 7/31/2022 | [5 empty] | 1/31/2025 | 1/31/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-532 | TC2 | PHASE 1 | Pohatcong-Newburgh Tap 34.5 kV |  | V20 Mansfield LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 20 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 8/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-533 | TC2 | PHASE 1 | Newburgh-Pohatcong 34.5 kV |  | AF1327 LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 20 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 8/31/2021 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-534 | TC2 | PHASE 1 | Hackettstown-Pohatcong R722-7 34.5 kV |  | Mansfield 3 LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 20 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 8/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-535 | TC2 | PHASE 1 | Hackettstown-Pohatcong J738-1 34.5 kV II |  | Mansfield 3 LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 40 | 20 | 0 |  | Energy | Storage | 3/31/2021 | 8/31/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-289 | TC2 | PHASE 1 | Amsden – Fremont Center 69 kV |  | Chinchilla Solar LLC | OH | Seneca | Active | Generation Interconnection | AEP | 66.6 | 66.6 | 0 |  | Energy | Storage | 3/23/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-290 | TC2 | PHASE 1 | Amsden – Fremont Center 69 kV |  | Chinchilla Solar LLC | OH | Seneca | Active | Generation Interconnection | AEP | 105 | 38.4 | 0 |  | Energy | Storage | 3/22/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-148 | TC2 | PHASE 1 | S Berwick - Galion 345 kV |  | Armadillo Solar LLC | OH | Wyandot | Active | Generation Interconnection | AEP | 86 | 86 | 0 |  | Energy | Storage | 2/22/2021 | 12/2/2024 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-099 | TC2 | APPLICATION REVIEW | Moshannon-Milesburg 230 kV V |  | MPG Solar, LLC | PA | Centre | Withdrawn | Generation Interconnection | APS | 161.98 | 0 | 0 |  | Energy | Storage | 1/28/2021 | 6/30/2022 | [5 empty] | 3/3/2025 | 3/3/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-100 | TC2 | APPLICATION REVIEW | Moshannon-Milesburg 230 kV VI |  | MPG Solar, LLC | PA | Centre | Withdrawn | Generation Interconnection | APS | 161.98 | 0 | 0 |  | Energy | Storage | 1/28/2021 | 6/30/2022 | [5 empty] | 3/3/2025 | 3/3/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-166 | TC2 | PHASE 1 | Newville-Nottingham Tap 1 69 kV |  | Costen Solar, Inc | PA | Cumberland | Active | Generation Interconnection | PPL | 10 | 10 | 0 |  | Energy | Solar | 2/25/2021 | 8/18/2023 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-096 | TC2 | PHASE 1 | Dauphin PG Tie-Dauphin Juniata Tie 69 kV |  | Dauphin Solar I, LLC | PA | Dauphin | Active | Generation Interconnection | PPL | 55 | 0 | 0 |  | Energy | Storage | 1/28/2021 | 12/1/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-098 | TC2 | APPLICATION REVIEW | Copperstone-North Lebanon 230 kV II |  | Lebanon Solar I, LLC | PA | Lebanon | Withdrawn | Generation Interconnection | ME | 70 | 0 | 0 |  | Energy | Storage | 1/28/2021 | 6/30/2022 | [5 empty] | 2/10/2025 | 2/10/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-602 | TC2 | APPLICATION REVIEW | Maysville 69 kV V |  | MC Solar, LLC | PA | Mercer | Withdrawn | Generation Interconnection | ATSI | 50 | 0 | 0 |  | Energy | Storage | 3/31/2021 | 9/15/2022 | [5 empty] | 3/11/2025 | 3/11/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AF2-404 | TC1 | PHASE 3 | Gladys DP-Stonemill 69 kV | Pigeon Run Storage | Pigeon Run Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 60 | 0 | 0 |  | Energy | Storage | 3/31/2020 | 12/15/2022 | [5 empty] | 5/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-404/AF2-404_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-404/AF2-404_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG2-240 | TC2 | PHASE 1 | Old Church 34.5 kV |  | Mechanicsville Solar, LLC | VA | Hanover | Active | Generation Interconnection | Dominion | 25 | 0 | 0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-125 | TC2 | PHASE 1 | Sycoline 34.5kV | Evergreen Energy Center, LLC | Evergreen Energy Center, LLC | VA | Loudoun | Active | Generation Interconnection | Dominion | 20 | 20 | 0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-127 | TC2 | PHASE 1 | Railroad 34.5kV | Railroad Energy Center, LLC | Railroad Energy Center, LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 20 | 20 | 0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-128 | TC2 | PHASE 1 | Railroad 34.5kV | Bethlehem Energy Center, LLC | Bethlehem Energy Center, LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 20 | 20 | 0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-124 | TC2 | PHASE 1 | Vint Hill 34.5kV | Reid Energy Center, LLC | Reid Energy Center, LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 20 | 20 | 0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 5/5/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started